## X
task | task name | stage | resource type req | selected option | selected duration
A_PDW-01A1A.1.0 | 1. Frame | 1 | ['worker', 'robot arm'] | 2 | 45
A_PDW-01A1A.11.0 | 11. Install bath tub / shower pan | 1 | ['worker'] | 0 | 6
A_PDW-01A1A.13.0 | 13. Install ceiling CLG-01A | 1 | ['worker'] | 0 | 10
A_PDW-01A1A.14.0 | 14. Connect Fire Sprinkler Ceiling Assemblies | 1 | ['worker'] | 0 | 22
A_PDW-01A1A.17.0 | 17. Install electrical panel | 1 | ['worker', 'robot arm'] | 1 | 21
A_PDW-01A1A.21.0 | 21. Conduct Plumbing & sprinkler Pressure Test | 1 | ['worker'] | 0 | 5
A_PDW-01A1A.27.0 | 27. Install Lid LID-01A | 1 | ['worker'] | 0 | 13
A_PDW-01A1A.30.0 | 30. Move Pod to Finish Station | 1 | ['worker', 'robot arm'] | 1 | 6
A_PDW2 | Bathroom insulation, drywall and tape/bed | 1 | ['dryer'] | 0 | 12
A_PDW3 | kitchen insulation, drywall and tape/bed | 1 | ['dryer'] | 0 | 19
A_PDW-01A1AIF.1.0 | 1. Set-up for finishing stage | 1 | ['worker'] | 0 | 5
A_PDW8 | skim bathroom | 1 | ['worker'] | 1 | 13
B_PDW-01A1A.1.0 | 1. Frame | 1 | ['worker', 'robot arm'] | 2 | 40
B_PDW-01A1A.30.0 | 30. Move Pod to Finish Station | 1 | ['worker', 'robot arm'] | 1 | 6
B_PDW8 | skim bathroom | 1 | ['worker'] | 0 | 22
B_PDW9 | skim kitchen | 1 | ['worker'] | 1 | 8
B_PDW13 | skim outside | 1 | ['worker'] | 0 | 35
B_PDW12 | install doors and casing Bathroom | 1 | ['dryer'] | 0 | 20
C_PDW-01A1A.1.0 | 1. Frame | 1 | ['worker', 'robot arm'] | 2 | 45
C_PDW-01A1A.14.0 | 14. Connect Fire Sprinkler Ceiling Assemblies | 1 | ['worker'] | 0 | 22
C_PDW-01A1A.17.0 | 17. Install electrical panel | 1 | ['worker', 'robot arm'] | 1 | 21
C_PDW-01A1A.21.0 | 21. Conduct Plumbing & sprinkler Pressure Test | 1 | ['worker'] | 0 | 5
C_PDW-01A1A.27.0 | 27. Install Lid LID-01A | 1 | ['worker'] | 0 | 13
C_PDW-01A1A.30.0 | 30. Move Pod to Finish Station | 1 | ['worker', 'robot arm'] | 1 | 6
C_PDW2 | Bathroom insulation, drywall and tape/bed | 1 | ['worker'] | 0 | 12
C_PDW3 | kitchen insulation, drywall and tape/bed | 1 | ['worker'] | 0 | 19
C_PDW-01A1AIF.1.0 | 1. Set-up for finishing stage | 1 | ['worker'] | 0 | 5
C_PDW8 | skim bathroom | 1 | ['worker'] | 1 | 19
C_PDW9 | skim kitchen | 1 | ['dryer'] | 0 | 20
A_PDW4 | exterior insulation, drywall and tape/bed | 2 | ['dryer'] | 0 | 19
A_PDW9 | skim kitchen | 2 | ['worker'] | 0 | 17
A_PDW13 | skim outside | 2 | ['worker'] | 0 | 35
A_PDW12 | install doors and casing Bathroom | 2 | ['dryer'] | 0 | 20
A_PDW10 | skim dry bathroom | 2 | ['dryer'] | 0 | 125
A_PDW15 | sand bathroom | 2 | ['worker'] | 0 | 22
A_PDW16 | sand kitchen | 2 | ['worker'] | 0 | 17
A_PDW17 | sand outside | 2 | ['worker'] | 0 | 35
A_PDW19 | Prime paint bathroom | 2 | ['worker'] | 0 | 22
A_PDW20 | Prime paint kitchen | 2 | ['worker'] | 0 | 22
A_PDW22 | Prime dry bathroom | 2 | ['dryer'] | 0 | 155
A_PDW25 | Paint kitchen | 2 | ['worker'] | 0 | 37
A_PDW42 | Batt Insulation in walls | 2 | ['worker'] | 0 | 28
A_PDW43 | 40. Execute final interior punch - close NCRs | 2 | ['worker'] | 0 | 20
A_PDW44 | 42. Final clean-up entire module | 2 | ['worker'] | 0 | 10
A_PDW45 | Wrap, document and move to ship | 2 | ['worker'] | 0 | 31
B_PDW-01A1A.13.0 | 13. Install ceiling CLG-01A | 2 | ['worker'] | 0 | 10
B_PDW-01A1A.17.0 | 17. Install electrical panel | 2 | ['worker'] | 0 | 40
B_PDW-01A1A.21.0 | 21. Conduct Plumbing & sprinkler Pressure Test | 2 | ['worker'] | 0 | 5
B_PDW-01A1A.27.0 | 27. Install Lid LID-01A | 2 | ['worker'] | 0 | 13
B_PDW12.1 | install doors and casing Kitchen | 2 | ['worker'] | 0 | 20
B_PDW10 | skim dry bathroom | 2 | ['dryer'] | 0 | 110
B_PDW15 | sand bathroom | 2 | ['worker'] | 0 | 22
B_PDW17 | sand outside | 2 | ['worker'] | 0 | 35
B_PDW19 | Prime paint bathroom | 2 | ['worker'] | 0 | 22
B_PDW20 | Prime paint kitchen | 2 | ['worker'] | 0 | 22
B_PDW22 | Prime dry bathroom | 2 | ['dryer'] | 0 | 155
B_PDW32 | Install Interior Cabinets & Countertops | 2 | ['worker'] | 0 | 45
C_PDW-01A1A.11.0 | 11. Install bath tub / shower pan | 2 | ['worker'] | 0 | 6
C_PDW-01A1A.13.0 | 13. Install ceiling CLG-01A | 2 | ['worker'] | 0 | 10
C_PDW4 | exterior insulation, drywall and tape/bed | 2 | ['worker'] | 0 | 19
C_PDW13 | skim outside | 2 | ['worker'] | 0 | 22
C_PDW12 | install doors and casing Bathroom | 2 | ['worker'] | 0 | 17
C_PDW12.1 | install doors and casing Kitchen | 2 | ['worker'] | 0 | 20
C_PDW10 | skim dry bathroom | 2 | ['dryer'] | 0 | 125
C_PDW15 | sand bathroom | 2 | ['worker'] | 0 | 22
C_PDW17 | sand outside | 2 | ['worker'] | 0 | 20
C_PDW18.1 | Install Tub/Shower Surround | 2 | ['worker'] | 0 | 14
C_PDW19 | Prime paint bathroom | 2 | ['worker'] | 0 | 22
C_PDW20 | Prime paint kitchen | 2 | ['worker'] | 0 | 22
C_PDW22 | Prime dry bathroom | 2 | ['dryer'] | 0 | 155
C_PDW32 | Install Interior Cabinets & Countertops | 2 | ['worker'] | 0 | 45
C_PDW42 | Batt Insulation in walls | 2 | ['worker'] | 0 | 28
C_PDW43 | 40. Execute final interior punch - close NCRs | 2 | ['worker'] | 0 | 20
C_PDW44 | 42. Final clean-up entire module | 2 | ['worker'] | 0 | 10
C_PDW45 | Wrap, document and move to ship | 2 | ['worker'] | 0 | 31
A_PDW5 | dry bathroom | 3 | ['dryer'] | 0 | 130
A_PDW12.1 | install doors and casing Kitchen | 3 | ['dryer'] | 0 | 20
A_PDW18 | Install Tub/Shower Surround | 3 | ['dryer'] | 0 | 10
A_PDW21 | Apply wall covering | 3 | ['worker'] | 0 | 2
A_PDW24 | Paint bathroom | 3 | ['worker'] | 0 | 43
A_PDW26 | Paint dry | 3 | ['dryer', 'worker'] | 1 | 80
A_PDW28 | cove base bathroom | 3 | ['worker'] | 0 | 14
A_PDW29 | cove base kitchen | 3 | ['worker'] | 0 | 14
A_PDW30 | bathroom plumbing | 3 | ['worker'] | 0 | 25
A_PDW31 | bathroom trim | 3 | ['worker'] | 0 | 25
A_PDW32 | Install Interior Cabinets & Countertops | 3 | ['worker'] | 0 | 45
A_PDW33 | Kitchen plumbing and appliances | 3 | ['worker'] | 0 | 25
A_PDW34 | Install Electrical Fixtures & trim | 3 | ['worker'] | 0 | 16
A_PDW36 | 25. Connect POD to POD | 3 | ['worker'] | 0 | 10
A_PDW37 | 26. Install interior pod to pod connection finishes | 3 | ['worker'] | 0 | 1
A_PDW38 | 27. Connect pod to pod electrical | 3 | ['worker'] | 0 | 10
A_PDW39 | 28. Install Batt Insulation in lids and Inspection | 3 | ['worker'] | 0 | 14
A_PDW40 | 30. Install Sheathing on top of lids | 3 | ['worker'] | 0 | 5
A_PDW41 | Perform test | 3 | ['worker'] | 0 | 125
B_PDW5 | dry bathroom | 3 | ['dryer'] | 0 | 110
B_PDW-01A1AIF.1.0 | 1. Set-up for finishing stage | 3 | ['worker'] | 0 | 5
B_PDW16 | sand kitchen | 3 | ['worker'] | 0 | 17
B_PDW18 | Install Tub/Shower Surround | 3 | ['worker'] | 0 | 10
B_PDW21 | Apply wall covering | 3 | ['worker'] | 0 | 2
B_PDW24 | Paint bathroom | 3 | ['worker'] | 0 | 43
B_PDW25 | Paint kitchen | 3 | ['worker'] | 0 | 37
B_PDW26 | Paint dry | 3 | ['dryer'] | 0 | 130
B_PDW28 | cove base bathroom | 3 | ['worker'] | 0 | 14
B_PDW29 | cove base kitchen | 3 | ['worker'] | 0 | 14
B_PDW30 | bathroom plumbing | 3 | ['worker'] | 1 | 15
B_PDW31 | bathroom trim | 3 | ['worker'] | 0 | 25
B_PDW33 | Kitchen plumbing and appliances | 3 | ['worker'] | 0 | 25
B_PDW34 | Install Electrical Fixtures & trim | 3 | ['worker'] | 0 | 16
B_PDW36 | 25. Connect POD to POD | 3 | ['worker'] | 0 | 10
B_PDW37 | 26. Install interior pod to pod connection finishes | 3 | ['worker'] | 0 | 1
B_PDW38 | 27. Connect pod to pod electrical | 3 | ['worker'] | 0 | 10
B_PDW39 | 28. Install Batt Insulation in lids and Inspection | 3 | ['worker'] | 0 | 14
B_PDW40 | 30. Install Sheathing on top of lids | 3 | ['worker'] | 0 | 5
B_PDW41 | Perform test | 3 | ['worker'] | 0 | 125
B_PDW42 | Batt Insulation in walls | 3 | ['worker'] | 0 | 28
B_PDW43 | 40. Execute final interior punch - close NCRs | 3 | ['worker'] | 0 | 20
B_PDW44 | 42. Final clean-up entire module | 3 | ['worker'] | 0 | 10
B_PDW45 | Wrap, document and move to ship | 3 | ['worker'] | 0 | 31
C_PDW5 | dry bathroom | 3 | ['dryer'] | 0 | 130
C_PDW16 | sand kitchen | 3 | ['worker'] | 0 | 17
C_PDW18 | Install Tub/Shower Surround | 3 | ['worker'] | 0 | 10
C_PDW18.2 | Install Tub/Shower Surround | 3 | ['worker'] | 0 | 10
C_PDW21 | Apply wall covering | 3 | ['worker'] | 0 | 2
C_PDW24 | Paint bathroom | 3 | ['worker'] | 0 | 43
C_PDW25 | Paint kitchen | 3 | ['worker'] | 0 | 37
C_PDW26 | Paint dry | 3 | ['dryer', 'worker'] | 1 | 80
C_PDW28 | cove base bathroom | 3 | ['worker'] | 0 | 14
C_PDW29 | cove base kitchen | 3 | ['worker'] | 0 | 14
C_PDW30 | bathroom plumbing | 3 | ['worker'] | 1 | 15
C_PDW31 | bathroom trim | 3 | ['worker'] | 0 | 25
C_PDW33 | Kitchen plumbing and appliances | 3 | ['worker'] | 0 | 25
C_PDW34 | Install Electrical Fixtures & trim | 3 | ['worker'] | 0 | 16
C_PDW36 | 25. Connect POD to POD | 3 | ['worker'] | 0 | 10
C_PDW37 | 26. Install interior pod to pod connection finishes | 3 | ['worker'] | 0 | 1
C_PDW38 | 27. Connect pod to pod electrical | 3 | ['worker'] | 0 | 10
C_PDW39 | 28. Install Batt Insulation in lids and Inspection | 3 | ['worker'] | 0 | 14
C_PDW40 | 30. Install Sheathing on top of lids | 3 | ['worker'] | 0 | 5
C_PDW41 | Perform test | 3 | ['worker'] | 0 | 125

## Y
worker | stage | number of station | team cost | stage team cost
1 | 1 | 1 | 55 | 55
2 | 1 | 1 | 55 | 55
4 | 1 | 1 | 50 | 50
8 | 1 | 1 | 90 | 90
1 | 2 | 3 | 55 | 165
5 | 2 | 3 | 50 | 150
1 | 3 | 2 | 55 | 110
2 | 3 | 2 | 50 | 100
2 | 3 | 2 | 55 | 110

## T
task | task name | start time
A_PDW-01A1A.1.0 | 1. Frame | 0
A_PDW-01A1A.11.0 | 11. Install bath tub / shower pan | 50
A_PDW-01A1A.13.0 | 13. Install ceiling CLG-01A | 64
A_PDW-01A1A.14.0 | 14. Connect Fire Sprinkler Ceiling Assemblies | 64
A_PDW-01A1A.17.0 | 17. Install electrical panel | 74
A_PDW-01A1A.21.0 | 21. Conduct Plumbing & sprinkler Pressure Test | 45
A_PDW-01A1A.27.0 | 27. Install Lid LID-01A | 45
A_PDW-01A1A.30.0 | 30. Move Pod to Finish Station | 58
A_PDW2 | Bathroom insulation, drywall and tape/bed | 64
A_PDW3 | kitchen insulation, drywall and tape/bed | 76
A_PDW4 | exterior insulation, drywall and tape/bed | 0
A_PDW5 | dry bathroom | 30
A_PDW-01A1AIF.1.0 | 1. Set-up for finishing stage | 95
A_PDW8 | skim bathroom | 100
A_PDW9 | skim kitchen | 0
A_PDW13 | skim outside | 106
A_PDW12 | install doors and casing Bathroom | 144
A_PDW12.1 | install doors and casing Kitchen | 10
A_PDW10 | skim dry bathroom | 19
A_PDW15 | sand bathroom | 183
A_PDW16 | sand kitchen | 166
A_PDW17 | sand outside | 227
A_PDW18 | Install Tub/Shower Surround | 0
A_PDW19 | Prime paint bathroom | 144
A_PDW20 | Prime paint kitchen | 205
A_PDW21 | Apply wall covering | 1
A_PDW22 | Prime dry bathroom | 166
A_PDW24 | Paint bathroom | 68
A_PDW25 | Paint kitchen | 321
A_PDW26 | Paint dry | 160
A_PDW28 | cove base bathroom | 29
A_PDW29 | cove base kitchen | 13
A_PDW30 | bathroom plumbing | 68
A_PDW31 | bathroom trim | 43
A_PDW32 | Install Interior Cabinets & Countertops | 93
A_PDW33 | Kitchen plumbing and appliances | 43
A_PDW34 | Install Electrical Fixtures & trim | 27
A_PDW36 | 25. Connect POD to POD | 5
A_PDW37 | 26. Install interior pod to pod connection finishes | 0
A_PDW38 | 27. Connect pod to pod electrical | 3
A_PDW39 | 28. Install Batt Insulation in lids and Inspection | 15
A_PDW40 | 30. Install Sheathing on top of lids | 0
A_PDW41 | Perform test | 111
A_PDW42 | Batt Insulation in walls | 47
A_PDW43 | 40. Execute final interior punch - close NCRs | 27
A_PDW44 | 42. Final clean-up entire module | 17
A_PDW45 | Wrap, document and move to ship | 75
B_PDW-01A1A.1.0 | 1. Frame | 0
B_PDW-01A1A.13.0 | 13. Install ceiling CLG-01A | 5
B_PDW-01A1A.17.0 | 17. Install electrical panel | 48
B_PDW-01A1A.21.0 | 21. Conduct Plumbing & sprinkler Pressure Test | 0
B_PDW-01A1A.27.0 | 27. Install Lid LID-01A | 15
B_PDW-01A1A.30.0 | 30. Move Pod to Finish Station | 40
B_PDW5 | dry bathroom | 0
B_PDW-01A1AIF.1.0 | 1. Set-up for finishing stage | 118
B_PDW8 | skim bathroom | 54
B_PDW9 | skim kitchen | 46
B_PDW13 | skim outside | 54
B_PDW12 | install doors and casing Bathroom | 54
B_PDW12.1 | install doors and casing Kitchen | 28
B_PDW10 | skim dry bathroom | 0
B_PDW15 | sand bathroom | 154
B_PDW16 | sand kitchen | 58
B_PDW17 | sand outside | 176
B_PDW18 | Install Tub/Shower Surround | 6
B_PDW19 | Prime paint bathroom | 110
B_PDW20 | Prime paint kitchen | 132
B_PDW21 | Apply wall covering | 0
B_PDW22 | Prime dry bathroom | 132
B_PDW24 | Paint bathroom | 75
B_PDW25 | Paint kitchen | 78
B_PDW26 | Paint dry | 110
B_PDW28 | cove base bathroom | 30
B_PDW29 | cove base kitchen | 44
B_PDW30 | bathroom plumbing | 22
B_PDW31 | bathroom trim | 53
B_PDW32 | Install Interior Cabinets & Countertops | 287
B_PDW33 | Kitchen plumbing and appliances | 153
B_PDW34 | Install Electrical Fixtures & trim | 37
B_PDW36 | 25. Connect POD to POD | 12
B_PDW37 | 26. Install interior pod to pod connection finishes | 0
B_PDW38 | 27. Connect pod to pod electrical | 2
B_PDW39 | 28. Install Batt Insulation in lids and Inspection | 16
B_PDW40 | 30. Install Sheathing on top of lids | 1
B_PDW41 | Perform test | 115
B_PDW42 | Batt Insulation in walls | 178
B_PDW43 | 40. Execute final interior punch - close NCRs | 133
B_PDW44 | 42. Final clean-up entire module | 123
B_PDW45 | Wrap, document and move to ship | 206
C_PDW-01A1A.1.0 | 1. Frame | 0
C_PDW-01A1A.11.0 | 11. Install bath tub / shower pan | 0
C_PDW-01A1A.13.0 | 13. Install ceiling CLG-01A | 6
C_PDW-01A1A.14.0 | 14. Connect Fire Sprinkler Ceiling Assemblies | 50
C_PDW-01A1A.17.0 | 17. Install electrical panel | 76
C_PDW-01A1A.21.0 | 21. Conduct Plumbing & sprinkler Pressure Test | 45
C_PDW-01A1A.27.0 | 27. Install Lid LID-01A | 45
C_PDW-01A1A.30.0 | 30. Move Pod to Finish Station | 58
C_PDW2 | Bathroom insulation, drywall and tape/bed | 64
C_PDW3 | kitchen insulation, drywall and tape/bed | 72
C_PDW4 | exterior insulation, drywall and tape/bed | 43
C_PDW5 | dry bathroom | 0
C_PDW-01A1AIF.1.0 | 1. Set-up for finishing stage | 91
C_PDW8 | skim bathroom | 97
C_PDW9 | skim kitchen | 96
C_PDW13 | skim outside | 82
C_PDW12 | install doors and casing Bathroom | 26
C_PDW12.1 | install doors and casing Kitchen | 104
C_PDW10 | skim dry bathroom | 0
C_PDW15 | sand bathroom | 181
C_PDW16 | sand kitchen | 47
C_PDW17 | sand outside | 161
C_PDW18 | Install Tub/Shower Surround | 2
C_PDW18.1 | Install Tub/Shower Surround | 147
C_PDW18.2 | Install Tub/Shower Surround | 22
C_PDW19 | Prime paint bathroom | 125
C_PDW20 | Prime paint kitchen | 203
C_PDW21 | Apply wall covering | 0
C_PDW22 | Prime dry bathroom | 147
C_PDW24 | Paint bathroom | 111
C_PDW25 | Paint kitchen | 74
C_PDW26 | Paint dry | 154
C_PDW28 | cove base bathroom | 44
C_PDW29 | cove base kitchen | 30
C_PDW30 | bathroom plumbing | 32
C_PDW31 | bathroom trim | 64
C_PDW32 | Install Interior Cabinets & Countertops | 302
C_PDW33 | Kitchen plumbing and appliances | 89
C_PDW34 | Install Electrical Fixtures & trim | 58
C_PDW36 | 25. Connect POD to POD | 12
C_PDW37 | 26. Install interior pod to pod connection finishes | 0
C_PDW38 | 27. Connect pod to pod electrical | 6
C_PDW39 | 28. Install Batt Insulation in lids and Inspection | 16
C_PDW40 | 30. Install Sheathing on top of lids | 1
C_PDW41 | Perform test | 114
C_PDW42 | Batt Insulation in walls | 225
C_PDW43 | 40. Execute final interior punch - close NCRs | 62
C_PDW44 | 42. Final clean-up entire module | 16
C_PDW45 | Wrap, document and move to ship | 253

## A
worker | task | stage
1 | A_PDW-01A1A.1.0 | 1
1 | A_PDW-01A1A.11.0 | 1
1 | A_PDW-01A1A.13.0 | 1
1 | A_PDW-01A1A.17.0 | 1
1 | A_PDW-01A1A.21.0 | 1
1 | A_PDW-01A1A.30.0 | 1
1 | A_PDW8 | 1
1 | B_PDW-01A1A.1.0 | 1
1 | B_PDW-01A1A.30.0 | 1
1 | B_PDW8 | 1
1 | B_PDW9 | 1
1 | C_PDW-01A1A.14.0 | 1
1 | C_PDW-01A1A.21.0 | 1
1 | C_PDW3 | 1
1 | C_PDW-01A1AIF.1.0 | 1
1 | C_PDW8 | 1
2 | A_PDW-01A1A.1.0 | 1
2 | A_PDW-01A1A.14.0 | 1
2 | A_PDW-01A1A.27.0 | 1
2 | A_PDW-01A1A.30.0 | 1
2 | A_PDW-01A1AIF.1.0 | 1
2 | A_PDW8 | 1
2 | B_PDW9 | 1
2 | B_PDW13 | 1
2 | C_PDW-01A1A.1.0 | 1
2 | C_PDW-01A1A.17.0 | 1
2 | C_PDW-01A1A.27.0 | 1
2 | C_PDW-01A1A.30.0 | 1
2 | C_PDW2 | 1
2 | C_PDW8 | 1
4 | A_PDW2 | 1
4 | A_PDW3 | 1
4 | B_PDW12 | 1
4 | C_PDW9 | 1
8 | A_PDW-01A1A.1.0 | 1
8 | A_PDW-01A1A.17.0 | 1
8 | A_PDW-01A1A.30.0 | 1
8 | B_PDW-01A1A.1.0 | 1
8 | B_PDW-01A1A.30.0 | 1
8 | C_PDW-01A1A.1.0 | 1
8 | C_PDW-01A1A.17.0 | 1
8 | C_PDW-01A1A.30.0 | 1
1 | A_PDW9 | 2
1 | A_PDW13 | 2
1 | A_PDW15 | 2
1 | A_PDW16 | 2
1 | A_PDW17 | 2
1 | A_PDW19 | 2
1 | A_PDW20 | 2
1 | A_PDW25 | 2
1 | A_PDW42 | 2
1 | A_PDW43 | 2
1 | A_PDW44 | 2
1 | A_PDW45 | 2
1 | B_PDW-01A1A.13.0 | 2
1 | B_PDW-01A1A.17.0 | 2
1 | B_PDW-01A1A.21.0 | 2
1 | B_PDW-01A1A.27.0 | 2
1 | B_PDW12.1 | 2
1 | B_PDW15 | 2
1 | B_PDW17 | 2
1 | B_PDW19 | 2
1 | B_PDW20 | 2
1 | B_PDW32 | 2
1 | C_PDW-01A1A.11.0 | 2
1 | C_PDW-01A1A.13.0 | 2
1 | C_PDW4 | 2
1 | C_PDW13 | 2
1 | C_PDW12 | 2
1 | C_PDW12.1 | 2
1 | C_PDW15 | 2
1 | C_PDW17 | 2
1 | C_PDW18.1 | 2
1 | C_PDW19 | 2
1 | C_PDW20 | 2
1 | C_PDW32 | 2
1 | C_PDW42 | 2
1 | C_PDW43 | 2
1 | C_PDW44 | 2
1 | C_PDW45 | 2
6 | A_PDW4 | 2
6 | A_PDW12 | 2
6 | A_PDW10 | 2
6 | A_PDW22 | 2
6 | B_PDW10 | 2
6 | B_PDW22 | 2
6 | C_PDW10 | 2
6 | C_PDW22 | 2
1 | A_PDW21 | 3
1 | A_PDW26 | 3
1 | A_PDW29 | 3
1 | A_PDW30 | 3
1 | A_PDW32 | 3
1 | A_PDW33 | 3
1 | A_PDW34 | 3
1 | A_PDW37 | 3
1 | A_PDW38 | 3
1 | B_PDW-01A1AIF.1.0 | 3
1 | B_PDW16 | 3
1 | B_PDW18 | 3
1 | B_PDW24 | 3
1 | B_PDW28 | 3
1 | B_PDW29 | 3
1 | B_PDW33 | 3
1 | B_PDW37 | 3
1 | B_PDW39 | 3
1 | B_PDW40 | 3
1 | B_PDW42 | 3
1 | B_PDW43 | 3
1 | B_PDW44 | 3
1 | B_PDW45 | 3
1 | C_PDW16 | 3
1 | C_PDW18 | 3
1 | C_PDW18.2 | 3
1 | C_PDW21 | 3
1 | C_PDW30 | 3
1 | C_PDW31 | 3
1 | C_PDW33 | 3
1 | C_PDW36 | 3
1 | C_PDW41 | 3
2 | A_PDW24 | 3
2 | A_PDW28 | 3
2 | A_PDW31 | 3
2 | A_PDW36 | 3
2 | A_PDW39 | 3
2 | A_PDW40 | 3
2 | A_PDW41 | 3
2 | B_PDW21 | 3
2 | B_PDW25 | 3
2 | B_PDW30 | 3
2 | B_PDW31 | 3
2 | B_PDW34 | 3
2 | B_PDW36 | 3
2 | B_PDW38 | 3
2 | B_PDW41 | 3
2 | C_PDW24 | 3
2 | C_PDW25 | 3
2 | C_PDW26 | 3
2 | C_PDW28 | 3
2 | C_PDW29 | 3
2 | C_PDW34 | 3
2 | C_PDW37 | 3
2 | C_PDW38 | 3
2 | C_PDW39 | 3
2 | C_PDW40 | 3
5 | A_PDW5 | 3
5 | A_PDW12.1 | 3
5 | A_PDW18 | 3
5 | A_PDW26 | 3
5 | B_PDW5 | 3
5 | B_PDW26 | 3
5 | C_PDW5 | 3
5 | C_PDW26 | 3

## B
task | task
A_PDW-01A1A.1.0 | A_PDW-01A1A.11.0
A_PDW-01A1A.1.0 | A_PDW-01A1A.13.0
A_PDW-01A1A.1.0 | A_PDW-01A1A.14.0
A_PDW-01A1A.1.0 | A_PDW-01A1A.17.0
A_PDW-01A1A.1.0 | A_PDW-01A1A.21.0
A_PDW-01A1A.1.0 | A_PDW-01A1A.27.0
A_PDW-01A1A.1.0 | A_PDW-01A1A.30.0
A_PDW-01A1A.1.0 | A_PDW-01A1AIF.1.0
A_PDW-01A1A.1.0 | A_PDW8
A_PDW-01A1A.11.0 | A_PDW-01A1A.13.0
A_PDW-01A1A.11.0 | A_PDW-01A1A.17.0
A_PDW-01A1A.11.0 | A_PDW-01A1A.30.0
A_PDW-01A1A.11.0 | A_PDW8
A_PDW-01A1A.13.0 | A_PDW-01A1A.17.0
A_PDW-01A1A.13.0 | A_PDW8
A_PDW-01A1A.14.0 | A_PDW-01A1AIF.1.0
A_PDW-01A1A.14.0 | A_PDW8
A_PDW-01A1A.17.0 | A_PDW8
A_PDW-01A1A.21.0 | A_PDW-01A1A.11.0
A_PDW-01A1A.21.0 | A_PDW-01A1A.13.0
A_PDW-01A1A.21.0 | A_PDW-01A1A.17.0
A_PDW-01A1A.21.0 | A_PDW-01A1A.30.0
A_PDW-01A1A.21.0 | A_PDW8
A_PDW-01A1A.27.0 | A_PDW-01A1A.14.0
A_PDW-01A1A.27.0 | A_PDW-01A1A.30.0
A_PDW-01A1A.27.0 | A_PDW-01A1AIF.1.0
A_PDW-01A1A.27.0 | A_PDW8
A_PDW-01A1A.30.0 | A_PDW-01A1A.13.0
A_PDW-01A1A.30.0 | A_PDW-01A1A.14.0
A_PDW-01A1A.30.0 | A_PDW-01A1A.17.0
A_PDW-01A1A.30.0 | A_PDW-01A1AIF.1.0
A_PDW-01A1A.30.0 | A_PDW8
A_PDW2 | A_PDW3
A_PDW4 | A_PDW12
A_PDW4 | A_PDW10
A_PDW4 | A_PDW22
A_PDW5 | A_PDW26
A_PDW-01A1AIF.1.0 | A_PDW8
A_PDW9 | A_PDW13
A_PDW9 | A_PDW15
A_PDW9 | A_PDW16
A_PDW9 | A_PDW17
A_PDW9 | A_PDW19
A_PDW9 | A_PDW20
A_PDW9 | A_PDW25
A_PDW9 | A_PDW42
A_PDW9 | A_PDW43
A_PDW9 | A_PDW44
A_PDW9 | A_PDW45
A_PDW13 | A_PDW15
A_PDW13 | A_PDW16
A_PDW13 | A_PDW17
A_PDW13 | A_PDW19
A_PDW13 | A_PDW20
A_PDW13 | A_PDW25
A_PDW12 | A_PDW22
A_PDW12.1 | A_PDW5
A_PDW12.1 | A_PDW26
A_PDW10 | A_PDW12
A_PDW10 | A_PDW22
A_PDW15 | A_PDW17
A_PDW15 | A_PDW20
A_PDW15 | A_PDW25
A_PDW16 | A_PDW15
A_PDW16 | A_PDW17
A_PDW16 | A_PDW20
A_PDW16 | A_PDW25
A_PDW17 | A_PDW25
A_PDW18 | A_PDW5
A_PDW18 | A_PDW12.1
A_PDW18 | A_PDW26
A_PDW19 | A_PDW15
A_PDW19 | A_PDW16
A_PDW19 | A_PDW17
A_PDW19 | A_PDW20
A_PDW19 | A_PDW25
A_PDW20 | A_PDW17
A_PDW20 | A_PDW25
A_PDW21 | A_PDW26
A_PDW21 | A_PDW28
A_PDW21 | A_PDW30
A_PDW21 | A_PDW31
A_PDW21 | A_PDW32
A_PDW21 | A_PDW34
A_PDW21 | A_PDW36
A_PDW24 | A_PDW41
A_PDW28 | A_PDW26
A_PDW28 | A_PDW30
A_PDW28 | A_PDW31
A_PDW28 | A_PDW32
A_PDW28 | A_PDW34
A_PDW29 | A_PDW24
A_PDW29 | A_PDW33
A_PDW29 | A_PDW41
A_PDW30 | A_PDW26
A_PDW30 | A_PDW32
A_PDW31 | A_PDW26
A_PDW31 | A_PDW30
A_PDW31 | A_PDW32
A_PDW32 | A_PDW26
A_PDW33 | A_PDW24
A_PDW33 | A_PDW41
A_PDW34 | A_PDW26
A_PDW34 | A_PDW30
A_PDW34 | A_PDW31
A_PDW34 | A_PDW32
A_PDW36 | A_PDW26
A_PDW36 | A_PDW28
A_PDW36 | A_PDW30
A_PDW36 | A_PDW31
A_PDW36 | A_PDW32
A_PDW36 | A_PDW34
A_PDW37 | A_PDW24
A_PDW37 | A_PDW29
A_PDW37 | A_PDW33
A_PDW37 | A_PDW38
A_PDW37 | A_PDW39
A_PDW37 | A_PDW40
A_PDW37 | A_PDW41
A_PDW38 | A_PDW24
A_PDW38 | A_PDW29
A_PDW38 | A_PDW33
A_PDW38 | A_PDW39
A_PDW38 | A_PDW41
A_PDW39 | A_PDW24
A_PDW39 | A_PDW29
A_PDW39 | A_PDW33
A_PDW39 | A_PDW41
A_PDW40 | A_PDW24
A_PDW40 | A_PDW29
A_PDW40 | A_PDW33
A_PDW40 | A_PDW38
A_PDW40 | A_PDW39
A_PDW40 | A_PDW41
A_PDW42 | A_PDW13
A_PDW42 | A_PDW15
A_PDW42 | A_PDW16
A_PDW42 | A_PDW17
A_PDW42 | A_PDW19
A_PDW42 | A_PDW20
A_PDW42 | A_PDW25
A_PDW42 | A_PDW45
A_PDW43 | A_PDW13
A_PDW43 | A_PDW15
A_PDW43 | A_PDW16
A_PDW43 | A_PDW17
A_PDW43 | A_PDW19
A_PDW43 | A_PDW20
A_PDW43 | A_PDW25
A_PDW43 | A_PDW42
A_PDW43 | A_PDW45
A_PDW44 | A_PDW13
A_PDW44 | A_PDW15
A_PDW44 | A_PDW16
A_PDW44 | A_PDW17
A_PDW44 | A_PDW19
A_PDW44 | A_PDW20
A_PDW44 | A_PDW25
A_PDW44 | A_PDW42
A_PDW44 | A_PDW43
A_PDW44 | A_PDW45
A_PDW45 | A_PDW13
A_PDW45 | A_PDW15
A_PDW45 | A_PDW16
A_PDW45 | A_PDW17
A_PDW45 | A_PDW19
A_PDW45 | A_PDW20
A_PDW45 | A_PDW25
B_PDW-01A1A.1.0 | B_PDW-01A1A.30.0
B_PDW-01A1A.1.0 | B_PDW8
B_PDW-01A1A.1.0 | B_PDW9
B_PDW-01A1A.13.0 | B_PDW-01A1A.17.0
B_PDW-01A1A.13.0 | B_PDW-01A1A.27.0
B_PDW-01A1A.13.0 | B_PDW12.1
B_PDW-01A1A.13.0 | B_PDW15
B_PDW-01A1A.13.0 | B_PDW17
B_PDW-01A1A.13.0 | B_PDW19
B_PDW-01A1A.13.0 | B_PDW20
B_PDW-01A1A.13.0 | B_PDW32
B_PDW-01A1A.17.0 | B_PDW15
B_PDW-01A1A.17.0 | B_PDW17
B_PDW-01A1A.17.0 | B_PDW19
B_PDW-01A1A.17.0 | B_PDW20
B_PDW-01A1A.17.0 | B_PDW32
B_PDW-01A1A.21.0 | B_PDW-01A1A.13.0
B_PDW-01A1A.21.0 | B_PDW-01A1A.17.0
B_PDW-01A1A.21.0 | B_PDW-01A1A.27.0
B_PDW-01A1A.21.0 | B_PDW12.1
B_PDW-01A1A.21.0 | B_PDW15
B_PDW-01A1A.21.0 | B_PDW17
B_PDW-01A1A.21.0 | B_PDW19
B_PDW-01A1A.21.0 | B_PDW20
B_PDW-01A1A.21.0 | B_PDW32
B_PDW-01A1A.27.0 | B_PDW-01A1A.17.0
B_PDW-01A1A.27.0 | B_PDW12.1
B_PDW-01A1A.27.0 | B_PDW15
B_PDW-01A1A.27.0 | B_PDW17
B_PDW-01A1A.27.0 | B_PDW19
B_PDW-01A1A.27.0 | B_PDW20
B_PDW-01A1A.27.0 | B_PDW32
B_PDW-01A1A.30.0 | B_PDW8
B_PDW-01A1A.30.0 | B_PDW9
B_PDW5 | B_PDW26
B_PDW-01A1AIF.1.0 | B_PDW31
B_PDW-01A1AIF.1.0 | B_PDW41
B_PDW-01A1AIF.1.0 | B_PDW42
B_PDW-01A1AIF.1.0 | B_PDW43
B_PDW-01A1AIF.1.0 | B_PDW44
B_PDW-01A1AIF.1.0 | B_PDW45
B_PDW8 | B_PDW15
B_PDW8 | B_PDW17
B_PDW8 | B_PDW20
B_PDW9 | B_PDW8
B_PDW9 | B_PDW13
B_PDW9 | B_PDW15
B_PDW9 | B_PDW17
B_PDW9 | B_PDW20
B_PDW13 | B_PDW15
B_PDW13 | B_PDW17
B_PDW13 | B_PDW20
B_PDW13 | B_PDW32
B_PDW12.1 | B_PDW-01A1A.17.0
B_PDW12.1 | B_PDW15
B_PDW12.1 | B_PDW17
B_PDW12.1 | B_PDW19
B_PDW12.1 | B_PDW20
B_PDW12.1 | B_PDW32
B_PDW10 | B_PDW22
B_PDW15 | B_PDW17
B_PDW15 | B_PDW32
B_PDW16 | B_PDW-01A1AIF.1.0
B_PDW16 | B_PDW15
B_PDW16 | B_PDW19
B_PDW16 | B_PDW20
B_PDW16 | B_PDW24
B_PDW16 | B_PDW25
B_PDW16 | B_PDW31
B_PDW16 | B_PDW33
B_PDW16 | B_PDW41
B_PDW16 | B_PDW42
B_PDW16 | B_PDW43
B_PDW16 | B_PDW44
B_PDW16 | B_PDW45
B_PDW17 | B_PDW32
B_PDW18 | B_PDW-01A1AIF.1.0
B_PDW18 | B_PDW15
B_PDW18 | B_PDW17
B_PDW18 | B_PDW20
B_PDW18 | B_PDW24
B_PDW18 | B_PDW28
B_PDW18 | B_PDW29
B_PDW18 | B_PDW30
B_PDW18 | B_PDW34
B_PDW18 | B_PDW36
B_PDW18 | B_PDW41
B_PDW18 | B_PDW42
B_PDW18 | B_PDW43
B_PDW18 | B_PDW44
B_PDW18 | B_PDW45
B_PDW19 | B_PDW15
B_PDW19 | B_PDW17
B_PDW19 | B_PDW20
B_PDW19 | B_PDW32
B_PDW20 | B_PDW15
B_PDW20 | B_PDW17
B_PDW20 | B_PDW32
B_PDW21 | B_PDW-01A1AIF.1.0
B_PDW21 | B_PDW15
B_PDW21 | B_PDW16
B_PDW21 | B_PDW17
B_PDW21 | B_PDW18
B_PDW21 | B_PDW19
B_PDW21 | B_PDW20
B_PDW21 | B_PDW24
B_PDW21 | B_PDW25
B_PDW21 | B_PDW28
B_PDW21 | B_PDW29
B_PDW21 | B_PDW30
B_PDW21 | B_PDW31
B_PDW21 | B_PDW33
B_PDW21 | B_PDW34
B_PDW21 | B_PDW36
B_PDW21 | B_PDW38
B_PDW21 | B_PDW39
B_PDW21 | B_PDW41
B_PDW21 | B_PDW42
B_PDW21 | B_PDW43
B_PDW21 | B_PDW44
B_PDW21 | B_PDW45
B_PDW24 | B_PDW-01A1AIF.1.0
B_PDW24 | B_PDW41
B_PDW24 | B_PDW43
B_PDW24 | B_PDW44
B_PDW25 | B_PDW15
B_PDW25 | B_PDW31
B_PDW25 | B_PDW42
B_PDW25 | B_PDW43
B_PDW25 | B_PDW44
B_PDW25 | B_PDW45
B_PDW28 | B_PDW-01A1AIF.1.0
B_PDW28 | B_PDW15
B_PDW28 | B_PDW16
B_PDW28 | B_PDW17
B_PDW28 | B_PDW20
B_PDW28 | B_PDW25
B_PDW28 | B_PDW31
B_PDW28 | B_PDW33
B_PDW28 | B_PDW41
B_PDW28 | B_PDW42
B_PDW28 | B_PDW43
B_PDW28 | B_PDW44
B_PDW28 | B_PDW45
B_PDW29 | B_PDW-01A1AIF.1.0
B_PDW29 | B_PDW20
B_PDW29 | B_PDW24
B_PDW29 | B_PDW30
B_PDW29 | B_PDW31
B_PDW29 | B_PDW33
B_PDW29 | B_PDW34
B_PDW29 | B_PDW41
B_PDW29 | B_PDW42
B_PDW29 | B_PDW43
B_PDW29 | B_PDW44
B_PDW29 | B_PDW45
B_PDW30 | B_PDW-01A1AIF.1.0
B_PDW30 | B_PDW20
B_PDW30 | B_PDW24
B_PDW30 | B_PDW34
B_PDW30 | B_PDW41
B_PDW30 | B_PDW42
B_PDW30 | B_PDW43
B_PDW30 | B_PDW44
B_PDW30 | B_PDW45
B_PDW31 | B_PDW42
B_PDW31 | B_PDW45
B_PDW33 | B_PDW-01A1AIF.1.0
B_PDW33 | B_PDW17
B_PDW33 | B_PDW20
B_PDW33 | B_PDW25
B_PDW33 | B_PDW31
B_PDW33 | B_PDW42
B_PDW33 | B_PDW43
B_PDW33 | B_PDW44
B_PDW33 | B_PDW45
B_PDW34 | B_PDW-01A1AIF.1.0
B_PDW34 | B_PDW15
B_PDW34 | B_PDW17
B_PDW34 | B_PDW24
B_PDW34 | B_PDW31
B_PDW34 | B_PDW41
B_PDW34 | B_PDW42
B_PDW34 | B_PDW43
B_PDW34 | B_PDW44
B_PDW34 | B_PDW45
B_PDW36 | B_PDW-01A1AIF.1.0
B_PDW36 | B_PDW15
B_PDW36 | B_PDW16
B_PDW36 | B_PDW17
B_PDW36 | B_PDW24
B_PDW36 | B_PDW29
B_PDW36 | B_PDW30
B_PDW36 | B_PDW31
B_PDW36 | B_PDW34
B_PDW36 | B_PDW41
B_PDW36 | B_PDW42
B_PDW36 | B_PDW43
B_PDW36 | B_PDW44
B_PDW36 | B_PDW45
B_PDW37 | B_PDW-01A1AIF.1.0
B_PDW37 | B_PDW15
B_PDW37 | B_PDW16
B_PDW37 | B_PDW17
B_PDW37 | B_PDW18
B_PDW37 | B_PDW20
B_PDW37 | B_PDW24
B_PDW37 | B_PDW25
B_PDW37 | B_PDW28
B_PDW37 | B_PDW29
B_PDW37 | B_PDW30
B_PDW37 | B_PDW31
B_PDW37 | B_PDW33
B_PDW37 | B_PDW34
B_PDW37 | B_PDW36
B_PDW37 | B_PDW38
B_PDW37 | B_PDW39
B_PDW37 | B_PDW40
B_PDW37 | B_PDW41
B_PDW37 | B_PDW42
B_PDW37 | B_PDW43
B_PDW37 | B_PDW44
B_PDW37 | B_PDW45
B_PDW38 | B_PDW-01A1AIF.1.0
B_PDW38 | B_PDW15
B_PDW38 | B_PDW16
B_PDW38 | B_PDW17
B_PDW38 | B_PDW20
B_PDW38 | B_PDW25
B_PDW38 | B_PDW28
B_PDW38 | B_PDW31
B_PDW38 | B_PDW33
B_PDW38 | B_PDW34
B_PDW38 | B_PDW39
B_PDW38 | B_PDW41
B_PDW38 | B_PDW42
B_PDW38 | B_PDW43
B_PDW38 | B_PDW44
B_PDW38 | B_PDW45
B_PDW39 | B_PDW-01A1AIF.1.0
B_PDW39 | B_PDW16
B_PDW39 | B_PDW17
B_PDW39 | B_PDW25
B_PDW39 | B_PDW28
B_PDW39 | B_PDW30
B_PDW39 | B_PDW31
B_PDW39 | B_PDW33
B_PDW39 | B_PDW34
B_PDW39 | B_PDW41
B_PDW39 | B_PDW42
B_PDW39 | B_PDW43
B_PDW39 | B_PDW44
B_PDW39 | B_PDW45
B_PDW40 | B_PDW-01A1AIF.1.0
B_PDW40 | B_PDW15
B_PDW40 | B_PDW16
B_PDW40 | B_PDW17
B_PDW40 | B_PDW20
B_PDW40 | B_PDW25
B_PDW40 | B_PDW28
B_PDW40 | B_PDW31
B_PDW40 | B_PDW33
B_PDW40 | B_PDW34
B_PDW40 | B_PDW38
B_PDW40 | B_PDW39
B_PDW40 | B_PDW41
B_PDW40 | B_PDW42
B_PDW40 | B_PDW43
B_PDW40 | B_PDW44
B_PDW40 | B_PDW45
B_PDW42 | B_PDW45
B_PDW43 | B_PDW31
B_PDW43 | B_PDW42
B_PDW43 | B_PDW45
B_PDW44 | B_PDW31
B_PDW44 | B_PDW42
B_PDW44 | B_PDW43
B_PDW44 | B_PDW45
C_PDW-01A1A.1.0 | C_PDW-01A1A.17.0
C_PDW-01A1A.1.0 | C_PDW-01A1A.21.0
C_PDW-01A1A.1.0 | C_PDW-01A1A.27.0
C_PDW-01A1A.1.0 | C_PDW-01A1A.30.0
C_PDW-01A1A.1.0 | C_PDW2
C_PDW-01A1A.1.0 | C_PDW8
C_PDW-01A1A.11.0 | C_PDW-01A1A.13.0
C_PDW-01A1A.11.0 | C_PDW4
C_PDW-01A1A.11.0 | C_PDW13
C_PDW-01A1A.11.0 | C_PDW12
C_PDW-01A1A.11.0 | C_PDW12.1
C_PDW-01A1A.11.0 | C_PDW15
C_PDW-01A1A.11.0 | C_PDW17
C_PDW-01A1A.11.0 | C_PDW18.1
C_PDW-01A1A.11.0 | C_PDW19
C_PDW-01A1A.11.0 | C_PDW20
C_PDW-01A1A.11.0 | C_PDW32
C_PDW-01A1A.11.0 | C_PDW42
C_PDW-01A1A.11.0 | C_PDW43
C_PDW-01A1A.11.0 | C_PDW44
C_PDW-01A1A.11.0 | C_PDW45
C_PDW-01A1A.13.0 | C_PDW4
C_PDW-01A1A.13.0 | C_PDW13
C_PDW-01A1A.13.0 | C_PDW12
C_PDW-01A1A.13.0 | C_PDW12.1
C_PDW-01A1A.13.0 | C_PDW15
C_PDW-01A1A.13.0 | C_PDW17
C_PDW-01A1A.13.0 | C_PDW18.1
C_PDW-01A1A.13.0 | C_PDW19
C_PDW-01A1A.13.0 | C_PDW20
C_PDW-01A1A.13.0 | C_PDW32
C_PDW-01A1A.13.0 | C_PDW42
C_PDW-01A1A.13.0 | C_PDW43
C_PDW-01A1A.13.0 | C_PDW44
C_PDW-01A1A.13.0 | C_PDW45
C_PDW-01A1A.14.0 | C_PDW3
C_PDW-01A1A.14.0 | C_PDW-01A1AIF.1.0
C_PDW-01A1A.14.0 | C_PDW8
C_PDW-01A1A.17.0 | C_PDW8
C_PDW-01A1A.21.0 | C_PDW-01A1A.14.0
C_PDW-01A1A.21.0 | C_PDW-01A1A.30.0
C_PDW-01A1A.21.0 | C_PDW3
C_PDW-01A1A.21.0 | C_PDW-01A1AIF.1.0
C_PDW-01A1A.21.0 | C_PDW8
C_PDW-01A1A.27.0 | C_PDW-01A1A.17.0
C_PDW-01A1A.27.0 | C_PDW-01A1A.30.0
C_PDW-01A1A.27.0 | C_PDW2
C_PDW-01A1A.27.0 | C_PDW8
C_PDW-01A1A.30.0 | C_PDW-01A1A.17.0
C_PDW-01A1A.30.0 | C_PDW2
C_PDW-01A1A.30.0 | C_PDW3
C_PDW-01A1A.30.0 | C_PDW8
C_PDW2 | C_PDW-01A1A.17.0
C_PDW2 | C_PDW-01A1AIF.1.0
C_PDW2 | C_PDW8
C_PDW3 | C_PDW-01A1AIF.1.0
C_PDW3 | C_PDW8
C_PDW4 | C_PDW13
C_PDW4 | C_PDW12.1
C_PDW4 | C_PDW15
C_PDW4 | C_PDW17
C_PDW4 | C_PDW18.1
C_PDW4 | C_PDW19
C_PDW4 | C_PDW20
C_PDW4 | C_PDW32
C_PDW4 | C_PDW42
C_PDW4 | C_PDW43
C_PDW4 | C_PDW45
C_PDW5 | C_PDW26
C_PDW-01A1AIF.1.0 | C_PDW8
C_PDW9 | C_PDW22
C_PDW13 | C_PDW12.1
C_PDW13 | C_PDW15
C_PDW13 | C_PDW17
C_PDW13 | C_PDW18.1
C_PDW13 | C_PDW19
C_PDW13 | C_PDW20
C_PDW13 | C_PDW32
C_PDW13 | C_PDW42
C_PDW13 | C_PDW45
C_PDW12 | C_PDW4
C_PDW12 | C_PDW13
C_PDW12 | C_PDW12.1
C_PDW12 | C_PDW15
C_PDW12 | C_PDW17
C_PDW12 | C_PDW18.1
C_PDW12 | C_PDW19
C_PDW12 | C_PDW20
C_PDW12 | C_PDW32
C_PDW12 | C_PDW42
C_PDW12 | C_PDW43
C_PDW12 | C_PDW45
C_PDW12.1 | C_PDW15
C_PDW12.1 | C_PDW17
C_PDW12.1 | C_PDW18.1
C_PDW12.1 | C_PDW19
C_PDW12.1 | C_PDW20
C_PDW12.1 | C_PDW32
C_PDW12.1 | C_PDW42
C_PDW12.1 | C_PDW45
C_PDW10 | C_PDW22
C_PDW15 | C_PDW20
C_PDW15 | C_PDW32
C_PDW15 | C_PDW42
C_PDW15 | C_PDW45
C_PDW16 | C_PDW20
C_PDW16 | C_PDW25
C_PDW16 | C_PDW41
C_PDW17 | C_PDW15
C_PDW17 | C_PDW20
C_PDW17 | C_PDW32
C_PDW17 | C_PDW42
C_PDW17 | C_PDW45
C_PDW18 | C_PDW24
C_PDW18 | C_PDW26
C_PDW18 | C_PDW28
C_PDW18 | C_PDW29
C_PDW18 | C_PDW31
C_PDW18 | C_PDW33
C_PDW18.1 | C_PDW15
C_PDW18.1 | C_PDW17
C_PDW18.1 | C_PDW20
C_PDW18.1 | C_PDW32
C_PDW18.1 | C_PDW42
C_PDW18.1 | C_PDW45
C_PDW18.2 | C_PDW16
C_PDW18.2 | C_PDW20
C_PDW18.2 | C_PDW25
C_PDW18.2 | C_PDW30
C_PDW18.2 | C_PDW31
C_PDW18.2 | C_PDW34
C_PDW18.2 | C_PDW39
C_PDW18.2 | C_PDW41
C_PDW18.2 | C_PDW45
C_PDW19 | C_PDW15
C_PDW19 | C_PDW17
C_PDW19 | C_PDW18.1
C_PDW19 | C_PDW20
C_PDW19 | C_PDW32
C_PDW19 | C_PDW42
C_PDW19 | C_PDW45
C_PDW20 | C_PDW32
C_PDW20 | C_PDW42
C_PDW20 | C_PDW45
C_PDW21 | C_PDW18
C_PDW21 | C_PDW18.1
C_PDW21 | C_PDW24
C_PDW21 | C_PDW25
C_PDW21 | C_PDW26
C_PDW21 | C_PDW28
C_PDW21 | C_PDW29
C_PDW21 | C_PDW30
C_PDW21 | C_PDW31
C_PDW21 | C_PDW33
C_PDW21 | C_PDW36
C_PDW21 | C_PDW38
C_PDW21 | C_PDW39
C_PDW21 | C_PDW41
C_PDW24 | C_PDW26
C_PDW25 | C_PDW41
C_PDW28 | C_PDW24
C_PDW28 | C_PDW26
C_PDW28 | C_PDW29
C_PDW28 | C_PDW31
C_PDW28 | C_PDW33
C_PDW29 | C_PDW24
C_PDW29 | C_PDW26
C_PDW29 | C_PDW31
C_PDW29 | C_PDW33
C_PDW30 | C_PDW16
C_PDW30 | C_PDW25
C_PDW30 | C_PDW34
C_PDW30 | C_PDW41
C_PDW31 | C_PDW24
C_PDW31 | C_PDW26
C_PDW33 | C_PDW24
C_PDW33 | C_PDW26
C_PDW33 | C_PDW31
C_PDW34 | C_PDW16
C_PDW34 | C_PDW18.1
C_PDW34 | C_PDW25
C_PDW34 | C_PDW26
C_PDW34 | C_PDW41
C_PDW36 | C_PDW18
C_PDW36 | C_PDW18.1
C_PDW36 | C_PDW24
C_PDW36 | C_PDW26
C_PDW36 | C_PDW28
C_PDW36 | C_PDW29
C_PDW36 | C_PDW31
C_PDW36 | C_PDW33
C_PDW36 | C_PDW38
C_PDW37 | C_PDW16
C_PDW37 | C_PDW18
C_PDW37 | C_PDW18.2
C_PDW37 | C_PDW24
C_PDW37 | C_PDW25
C_PDW37 | C_PDW26
C_PDW37 | C_PDW28
C_PDW37 | C_PDW29
C_PDW37 | C_PDW30
C_PDW37 | C_PDW31
C_PDW37 | C_PDW33
C_PDW37 | C_PDW34
C_PDW37 | C_PDW36
C_PDW37 | C_PDW38
C_PDW37 | C_PDW39
C_PDW37 | C_PDW40
C_PDW37 | C_PDW41
C_PDW38 | C_PDW18
C_PDW38 | C_PDW24
C_PDW38 | C_PDW26
C_PDW38 | C_PDW28
C_PDW38 | C_PDW29
C_PDW38 | C_PDW31
C_PDW38 | C_PDW33
C_PDW39 | C_PDW16
C_PDW39 | C_PDW25
C_PDW39 | C_PDW30
C_PDW39 | C_PDW34
C_PDW39 | C_PDW41
C_PDW40 | C_PDW16
C_PDW40 | C_PDW18.2
C_PDW40 | C_PDW25
C_PDW40 | C_PDW28
C_PDW40 | C_PDW29
C_PDW40 | C_PDW30
C_PDW40 | C_PDW34
C_PDW40 | C_PDW39
C_PDW40 | C_PDW41
C_PDW42 | C_PDW32
C_PDW42 | C_PDW45
C_PDW43 | C_PDW13
C_PDW43 | C_PDW12.1
C_PDW43 | C_PDW15
C_PDW43 | C_PDW17
C_PDW43 | C_PDW18.1
C_PDW43 | C_PDW19
C_PDW43 | C_PDW20
C_PDW43 | C_PDW32
C_PDW43 | C_PDW42
C_PDW43 | C_PDW45
C_PDW44 | C_PDW4
C_PDW44 | C_PDW13
C_PDW44 | C_PDW12
C_PDW44 | C_PDW12.1
C_PDW44 | C_PDW15
C_PDW44 | C_PDW17
C_PDW44 | C_PDW18.1
C_PDW44 | C_PDW19
C_PDW44 | C_PDW20
C_PDW44 | C_PDW32
C_PDW44 | C_PDW42
C_PDW44 | C_PDW43
C_PDW44 | C_PDW45
C_PDW45 | C_PDW32

## N
stage | number of station
1 | 1
2 | 3
3 | 2