## X
task | stage | resource option | resource type req
A_PDW-01A1A.1.0 | 1 | 0 | ['worker', 'gantry']
A_PDW-01A1A.11.0 | 2 | 0 | ['worker']
A_PDW-01A1A.13.0 | 3 | 0 | ['worker']
A_PDW-01A1A.14.0 | 2 | 0 | ['worker']
A_PDW-01A1A.17.0 | 2 | 0 | ['worker']
A_PDW-01A1A.21.0 | 1 | 0 | ['worker']
A_PDW-01A1A.27.0 | 1 | 0 | ['worker']
A_PDW-01A1A.30.0 | 1 | 0 | ['worker']
A_PDW2 | 2 | 0 | ['dryer']
A_PDW3 | 2 | 0 | ['dryer']
A_PDW4 | 5 | 0 | ['dryer']
A_PDW5 | 2 | 0 | ['dryer']
A_PDW-01A1AIF.1.0 | 2 | 0 | ['worker']
A_PDW8 | 2 | 0 | ['worker']
A_PDW9 | 2 | 0 | ['worker']
A_PDW13 | 2 | 0 | ['worker']
A_PDW12 | 2 | 0 | ['dryer']
A_PDW12.1 | 2 | 0 | ['dryer']
A_PDW10 | 2 | 0 | ['dryer']
A_PDW15 | 6 | 0 | ['worker']
A_PDW16 | 3 | 0 | ['worker']
A_PDW17 | 3 | 0 | ['worker']
A_PDW18 | 5 | 0 | ['dryer']
A_PDW19 | 3 | 0 | ['worker']
A_PDW20 | 7 | 0 | ['worker']
A_PDW21 | 3 | 0 | ['worker']
A_PDW22 | 5 | 0 | ['dryer']
A_PDW24 | 6 | 0 | ['worker']
A_PDW25 | 7 | 0 | ['worker']
A_PDW26 | 5 | 0 | ['dryer']
A_PDW28 | 7 | 0 | ['worker']
A_PDW29 | 6 | 0 | ['worker']
A_PDW30 | 6 | 0 | ['worker']
A_PDW31 | 6 | 0 | ['worker']
A_PDW32 | 6 | 0 | ['worker']
A_PDW33 | 6 | 0 | ['worker']
A_PDW34 | 6 | 0 | ['worker']
A_PDW36 | 7 | 0 | ['worker']
A_PDW37 | 6 | 0 | ['worker']
A_PDW38 | 6 | 0 | ['worker']
A_PDW39 | 6 | 0 | ['worker']
A_PDW40 | 6 | 0 | ['worker']
A_PDW41 | 7 | 0 | ['worker']
A_PDW42 | 6 | 0 | ['worker']
A_PDW43 | 2 | 0 | ['worker']
A_PDW44 | 7 | 0 | ['worker']
A_PDW45 | 3 | 0 | ['worker']
B_PDW-01A1A.1.0 | 1 | 0 | ['worker', 'gantry']
B_PDW-01A1A.13.0 | 2 | 0 | ['worker']
B_PDW-01A1A.17.0 | 2 | 0 | ['worker']
B_PDW-01A1A.21.0 | 2 | 0 | ['worker']
B_PDW-01A1A.27.0 | 1 | 0 | ['worker']
B_PDW-01A1A.30.0 | 2 | 0 | ['worker']
B_PDW5 | 2 | 0 | ['dryer']
B_PDW-01A1AIF.1.0 | 2 | 0 | ['worker']
B_PDW8 | 2 | 0 | ['worker']
B_PDW9 | 2 | 0 | ['worker']
B_PDW13 | 2 | 0 | ['worker']
B_PDW12 | 2 | 0 | ['dryer']
B_PDW12.1 | 2 | 0 | ['worker']
B_PDW10 | 2 | 0 | ['dryer']
B_PDW15 | 6 | 0 | ['worker']
B_PDW16 | 3 | 0 | ['worker']
B_PDW17 | 3 | 0 | ['worker']
B_PDW18 | 3 | 0 | ['worker']
B_PDW19 | 3 | 0 | ['worker']
B_PDW20 | 8 | 0 | ['worker']
B_PDW21 | 6 | 0 | ['worker']
B_PDW22 | 5 | 0 | ['dryer']
B_PDW24 | 8 | 0 | ['worker']
B_PDW25 | 6 | 0 | ['worker']
B_PDW26 | 5 | 0 | ['dryer']
B_PDW28 | 7 | 0 | ['worker']
B_PDW29 | 6 | 0 | ['worker']
B_PDW30 | 7 | 0 | ['worker']
B_PDW31 | 6 | 0 | ['worker']
B_PDW32 | 6 | 0 | ['worker']
B_PDW33 | 8 | 0 | ['worker']
B_PDW34 | 6 | 0 | ['worker']
B_PDW36 | 6 | 0 | ['worker']
B_PDW37 | 7 | 0 | ['worker']
B_PDW38 | 6 | 0 | ['worker']
B_PDW39 | 8 | 0 | ['worker']
B_PDW40 | 7 | 0 | ['worker']
B_PDW41 | 7 | 0 | ['worker']
B_PDW42 | 6 | 0 | ['worker']
B_PDW43 | 6 | 0 | ['worker']
B_PDW44 | 3 | 0 | ['worker']
B_PDW45 | 8 | 0 | ['worker']
C_PDW-01A1A.1.0 | 1 | 0 | ['worker', 'gantry']
C_PDW-01A1A.11.0 | 2 | 0 | ['worker']
C_PDW-01A1A.13.0 | 8 | 0 | ['worker']
C_PDW-01A1A.14.0 | 7 | 0 | ['worker']
C_PDW-01A1A.17.0 | 2 | 0 | ['worker']
C_PDW-01A1A.21.0 | 1 | 0 | ['worker']
C_PDW-01A1A.27.0 | 1 | 0 | ['worker']
C_PDW-01A1A.30.0 | 1 | 0 | ['worker']
C_PDW2 | 2 | 0 | ['worker']
C_PDW3 | 2 | 0 | ['worker']
C_PDW4 | 3 | 0 | ['worker']
C_PDW5 | 2 | 0 | ['dryer']
C_PDW-01A1AIF.1.0 | 2 | 0 | ['worker']
C_PDW8 | 2 | 0 | ['worker']
C_PDW9 | 2 | 0 | ['dryer']
C_PDW13 | 2 | 0 | ['worker']
C_PDW12 | 7 | 0 | ['worker']
C_PDW12.1 | 8 | 0 | ['worker']
C_PDW10 | 2 | 0 | ['dryer']
C_PDW15 | 6 | 0 | ['worker']
C_PDW16 | 3 | 0 | ['worker']
C_PDW17 | 3 | 0 | ['worker']
C_PDW18 | 3 | 0 | ['worker']
C_PDW18.1 | 6 | 0 | ['worker']
C_PDW18.2 | 6 | 0 | ['worker']
C_PDW19 | 3 | 0 | ['worker']
C_PDW20 | 6 | 0 | ['worker']
C_PDW21 | 7 | 0 | ['worker']
C_PDW22 | 5 | 0 | ['dryer']
C_PDW24 | 8 | 0 | ['worker']
C_PDW25 | 6 | 0 | ['worker']
C_PDW26 | 5 | 0 | ['dryer']
C_PDW28 | 8 | 0 | ['worker']
C_PDW29 | 6 | 0 | ['worker']
C_PDW30 | 7 | 0 | ['worker']
C_PDW31 | 6 | 0 | ['worker']
C_PDW32 | 6 | 0 | ['worker']
C_PDW33 | 8 | 0 | ['worker']
C_PDW34 | 7 | 0 | ['worker']
C_PDW36 | 6 | 0 | ['worker']
C_PDW37 | 6 | 0 | ['worker']
C_PDW38 | 6 | 0 | ['worker']
C_PDW39 | 6 | 0 | ['worker']
C_PDW40 | 6 | 0 | ['worker']
C_PDW41 | 7 | 0 | ['worker']
C_PDW42 | 6 | 0 | ['worker']
C_PDW43 | 6 | 0 | ['worker']
C_PDW44 | 6 | 0 | ['worker']
C_PDW45 | 8 | 0 | ['worker']

## Y
worker | stage | number of station | team cost | stage team cost
1 | 1 | 2 | 55 | 110
1 | 2 | 3 | 55 | 165
1 | 3 | 1 | 55 | 55
1 | 6 | 1 | 55 | 55
1 | 7 | 2 | 55 | 110
2 | 1 | 2 | 55 | 110
2 | 6 | 1 | 55 | 55
2 | 8 | 1 | 55 | 55
3 | 6 | 1 | 55 | 55
3 | 8 | 1 | 55 | 55
4 | 2 | 3 | 50 | 150
4 | 5 | 3 | 50 | 150
7 | 1 | 2 | 60 | 120

## T
task | task name | start time
A_PDW-01A1A.1.0 | 1. Frame | 0
A_PDW-01A1A.11.0 | 11. Install bath tub / shower pan | 0
A_PDW-01A1A.13.0 | 13. Install ceiling CLG-01A | 2
A_PDW-01A1A.14.0 | 14. Connect Fire Sprinkler Ceiling Assemblies | 6
A_PDW-01A1A.17.0 | 17. Install electrical panel | 56
A_PDW-01A1A.21.0 | 21. Conduct Plumbing & sprinkler Pressure Test | 180
A_PDW-01A1A.27.0 | 27. Install Lid LID-01A | 180
A_PDW-01A1A.30.0 | 30. Move Pod to Finish Station | 193
A_PDW2 | Bathroom insulation, drywall and tape/bed | 0
A_PDW3 | kitchen insulation, drywall and tape/bed | 12
A_PDW4 | exterior insulation, drywall and tape/bed | 10
A_PDW5 | dry bathroom | 31
A_PDW-01A1AIF.1.0 | 1. Set-up for finishing stage | 31
A_PDW8 | skim bathroom | 178
A_PDW9 | skim kitchen | 161
A_PDW13 | skim outside | 200
A_PDW12 | install doors and casing Bathroom | 181
A_PDW12.1 | install doors and casing Kitchen | 161
A_PDW10 | skim dry bathroom | 235
A_PDW15 | sand bathroom | 6
A_PDW16 | sand kitchen | 12
A_PDW17 | sand outside | 82
A_PDW18 | Install Tub/Shower Surround | 0
A_PDW19 | Prime paint bathroom | 29
A_PDW20 | Prime paint kitchen | 34
A_PDW21 | Apply wall covering | 0
A_PDW22 | Prime dry bathroom | 29
A_PDW24 | Paint bathroom | 56
A_PDW25 | Paint kitchen | 56
A_PDW26 | Paint dry | 184
A_PDW28 | cove base bathroom | 20
A_PDW29 | cove base kitchen | 0
A_PDW30 | bathroom plumbing | 26
A_PDW31 | bathroom trim | 28
A_PDW32 | Install Interior Cabinets & Countertops | 53
A_PDW33 | Kitchen plumbing and appliances | 51
A_PDW34 | Install Electrical Fixtures & trim | 10
A_PDW36 | 25. Connect POD to POD | 0
A_PDW37 | 26. Install interior pod to pod connection finishes | 0
A_PDW38 | 27. Connect pod to pod electrical | 0
A_PDW39 | 28. Install Batt Insulation in lids and Inspection | 14
A_PDW40 | 30. Install Sheathing on top of lids | 1
A_PDW41 | Perform test | 93
A_PDW42 | Batt Insulation in walls | 28
A_PDW43 | 40. Execute final interior punch - close NCRs | 36
A_PDW44 | 42. Final clean-up entire module | 10
A_PDW45 | Wrap, document and move to ship | 51
B_PDW-01A1A.1.0 | 1. Frame | 0
B_PDW-01A1A.13.0 | 13. Install ceiling CLG-01A | 5
B_PDW-01A1A.17.0 | 17. Install electrical panel | 55
B_PDW-01A1A.21.0 | 21. Conduct Plumbing & sprinkler Pressure Test | 0
B_PDW-01A1A.27.0 | 27. Install Lid LID-01A | 140
B_PDW-01A1A.30.0 | 30. Move Pod to Finish Station | 15
B_PDW5 | dry bathroom | 5
B_PDW-01A1AIF.1.0 | 1. Set-up for finishing stage | 115
B_PDW8 | skim bathroom | 157
B_PDW9 | skim kitchen | 120
B_PDW13 | skim outside | 179
B_PDW12 | install doors and casing Bathroom | 120
B_PDW12.1 | install doors and casing Kitchen | 137
B_PDW10 | skim dry bathroom | 214
B_PDW15 | sand bathroom | 10
B_PDW16 | sand kitchen | 20
B_PDW17 | sand outside | 59
B_PDW18 | Install Tub/Shower Surround | 0
B_PDW19 | Prime paint bathroom | 37
B_PDW20 | Prime paint kitchen | 0
B_PDW21 | Apply wall covering | 0
B_PDW22 | Prime dry bathroom | 0
B_PDW24 | Paint bathroom | 39
B_PDW25 | Paint kitchen | 44
B_PDW26 | Paint dry | 155
B_PDW28 | cove base bathroom | 6
B_PDW29 | cove base kitchen | 10
B_PDW30 | bathroom plumbing | 20
B_PDW31 | bathroom trim | 46
B_PDW32 | Install Interior Cabinets & Countertops | 32
B_PDW33 | Kitchen plumbing and appliances | 14
B_PDW34 | Install Electrical Fixtures & trim | 2
B_PDW36 | 25. Connect POD to POD | 0
B_PDW37 | 26. Install interior pod to pod connection finishes | 0
B_PDW38 | 27. Connect pod to pod electrical | 0
B_PDW39 | 28. Install Batt Insulation in lids and Inspection | 0
B_PDW40 | 30. Install Sheathing on top of lids | 1
B_PDW41 | Perform test | 45
B_PDW42 | Batt Insulation in walls | 18
B_PDW43 | 40. Execute final interior punch - close NCRs | 24
B_PDW44 | 42. Final clean-up entire module | 10
B_PDW45 | Wrap, document and move to ship | 22
C_PDW-01A1A.1.0 | 1. Frame | 0
C_PDW-01A1A.11.0 | 11. Install bath tub / shower pan | 31
C_PDW-01A1A.13.0 | 13. Install ceiling CLG-01A | 0
C_PDW-01A1A.14.0 | 14. Connect Fire Sprinkler Ceiling Assemblies | 2
C_PDW-01A1A.17.0 | 17. Install electrical panel | 42
C_PDW-01A1A.21.0 | 21. Conduct Plumbing & sprinkler Pressure Test | 180
C_PDW-01A1A.27.0 | 27. Install Lid LID-01A | 180
C_PDW-01A1A.30.0 | 30. Move Pod to Finish Station | 193
C_PDW2 | Bathroom insulation, drywall and tape/bed | 0
C_PDW3 | kitchen insulation, drywall and tape/bed | 12
C_PDW4 | exterior insulation, drywall and tape/bed | 27
C_PDW5 | dry bathroom | 31
C_PDW-01A1AIF.1.0 | 1. Set-up for finishing stage | 37
C_PDW8 | skim bathroom | 183
C_PDW9 | skim kitchen | 161
C_PDW13 | skim outside | 161
C_PDW12 | install doors and casing Bathroom | 40
C_PDW12.1 | install doors and casing Kitchen | 0
C_PDW10 | skim dry bathroom | 218
C_PDW15 | sand bathroom | 51
C_PDW16 | sand kitchen | 10
C_PDW17 | sand outside | 46
C_PDW18 | Install Tub/Shower Surround | 0
C_PDW18.1 | Install Tub/Shower Surround | 11
C_PDW18.2 | Install Tub/Shower Surround | 5
C_PDW19 | Prime paint bathroom | 66
C_PDW20 | Prime paint kitchen | 29
C_PDW21 | Apply wall covering | 0
C_PDW22 | Prime dry bathroom | 0
C_PDW24 | Paint bathroom | 24
C_PDW25 | Paint kitchen | 79
C_PDW26 | Paint dry | 155
C_PDW28 | cove base bathroom | 10
C_PDW29 | cove base kitchen | 20
C_PDW30 | bathroom plumbing | 57
C_PDW31 | bathroom trim | 54
C_PDW32 | Install Interior Cabinets & Countertops | 53
C_PDW33 | Kitchen plumbing and appliances | 20
C_PDW34 | Install Electrical Fixtures & trim | 24
C_PDW36 | 25. Connect POD to POD | 0
C_PDW37 | 26. Install interior pod to pod connection finishes | 0
C_PDW38 | 27. Connect pod to pod electrical | 10
C_PDW39 | 28. Install Batt Insulation in lids and Inspection | 15
C_PDW40 | 30. Install Sheathing on top of lids | 0
C_PDW41 | Perform test | 82
C_PDW42 | Batt Insulation in walls | 25
C_PDW43 | 40. Execute final interior punch - close NCRs | 34
C_PDW44 | 42. Final clean-up entire module | 1
C_PDW45 | Wrap, document and move to ship | 45

## A
worker | task | stage
1 | A_PDW-01A1A.1.0 | 1
1 | A_PDW-01A1A.11.0 | 2
1 | A_PDW-01A1A.13.0 | 3
1 | A_PDW-01A1A.14.0 | 2
1 | A_PDW-01A1A.17.0 | 2
1 | A_PDW-01A1A.27.0 | 1
1 | A_PDW-01A1A.30.0 | 1
1 | A_PDW-01A1AIF.1.0 | 2
1 | A_PDW8 | 2
1 | A_PDW9 | 2
1 | A_PDW13 | 2
1 | A_PDW15 | 6
1 | A_PDW16 | 3
1 | A_PDW17 | 3
1 | A_PDW19 | 3
1 | A_PDW20 | 7
1 | A_PDW21 | 3
1 | A_PDW24 | 6
1 | A_PDW25 | 7
1 | A_PDW28 | 7
1 | A_PDW36 | 7
1 | A_PDW37 | 6
1 | A_PDW40 | 6
1 | A_PDW41 | 7
1 | A_PDW42 | 6
1 | A_PDW43 | 2
1 | A_PDW44 | 7
1 | A_PDW45 | 3
1 | B_PDW-01A1A.1.0 | 1
1 | B_PDW-01A1A.13.0 | 2
1 | B_PDW-01A1A.17.0 | 2
1 | B_PDW-01A1A.21.0 | 2
1 | B_PDW-01A1A.30.0 | 2
1 | B_PDW-01A1AIF.1.0 | 2
1 | B_PDW8 | 2
1 | B_PDW9 | 2
1 | B_PDW13 | 2
1 | B_PDW12.1 | 2
1 | B_PDW16 | 3
1 | B_PDW17 | 3
1 | B_PDW18 | 3
1 | B_PDW19 | 3
1 | B_PDW21 | 6
1 | B_PDW28 | 7
1 | B_PDW30 | 7
1 | B_PDW31 | 6
1 | B_PDW34 | 6
1 | B_PDW37 | 7
1 | B_PDW40 | 7
1 | B_PDW41 | 7
1 | B_PDW42 | 6
1 | B_PDW44 | 3
1 | C_PDW-01A1A.1.0 | 1
1 | C_PDW-01A1A.11.0 | 2
1 | C_PDW-01A1A.14.0 | 7
1 | C_PDW-01A1A.17.0 | 2
1 | C_PDW-01A1A.27.0 | 1
1 | C_PDW2 | 2
1 | C_PDW3 | 2
1 | C_PDW4 | 3
1 | C_PDW-01A1AIF.1.0 | 2
1 | C_PDW8 | 2
1 | C_PDW13 | 2
1 | C_PDW12 | 7
1 | C_PDW16 | 3
1 | C_PDW17 | 3
1 | C_PDW18 | 3
1 | C_PDW19 | 3
1 | C_PDW21 | 7
1 | C_PDW25 | 6
1 | C_PDW29 | 6
1 | C_PDW30 | 7
1 | C_PDW31 | 6
1 | C_PDW34 | 7
1 | C_PDW36 | 6
1 | C_PDW38 | 6
1 | C_PDW41 | 7
1 | C_PDW43 | 6
2 | A_PDW-01A1A.1.0 | 1
2 | A_PDW-01A1A.21.0 | 1
2 | A_PDW-01A1A.30.0 | 1
2 | A_PDW29 | 6
2 | A_PDW31 | 6
2 | A_PDW32 | 6
2 | A_PDW39 | 6
2 | B_PDW-01A1A.1.0 | 1
2 | B_PDW-01A1A.27.0 | 1
2 | B_PDW15 | 6
2 | B_PDW24 | 8
2 | B_PDW32 | 6
2 | B_PDW33 | 8
2 | B_PDW36 | 6
2 | B_PDW39 | 8
2 | C_PDW-01A1A.1.0 | 1
2 | C_PDW-01A1A.21.0 | 1
2 | C_PDW-01A1A.30.0 | 1
2 | C_PDW12.1 | 8
2 | C_PDW18.1 | 6
2 | C_PDW32 | 6
2 | C_PDW33 | 8
2 | C_PDW37 | 6
2 | C_PDW42 | 6
2 | C_PDW44 | 6
2 | C_PDW45 | 8
3 | A_PDW30 | 6
3 | A_PDW33 | 6
3 | A_PDW34 | 6
3 | A_PDW38 | 6
3 | B_PDW20 | 8
3 | B_PDW25 | 6
3 | B_PDW29 | 6
3 | B_PDW38 | 6
3 | B_PDW43 | 6
3 | B_PDW45 | 8
3 | C_PDW-01A1A.13.0 | 8
3 | C_PDW15 | 6
3 | C_PDW18.2 | 6
3 | C_PDW20 | 6
3 | C_PDW24 | 8
3 | C_PDW28 | 8
3 | C_PDW39 | 6
3 | C_PDW40 | 6
4 | A_PDW2 | 2
4 | A_PDW3 | 2
4 | A_PDW4 | 5
4 | A_PDW5 | 2
4 | A_PDW12 | 2
4 | A_PDW12.1 | 2
4 | A_PDW10 | 2
4 | A_PDW18 | 5
4 | A_PDW22 | 5
4 | A_PDW26 | 5
4 | B_PDW5 | 2
4 | B_PDW12 | 2
4 | B_PDW10 | 2
4 | B_PDW22 | 5
4 | B_PDW26 | 5
4 | C_PDW5 | 2
4 | C_PDW9 | 2
4 | C_PDW10 | 2
4 | C_PDW22 | 5
4 | C_PDW26 | 5
7 | A_PDW-01A1A.1.0 | 1
7 | B_PDW-01A1A.1.0 | 1
7 | C_PDW-01A1A.1.0 | 1

## B
task | task | value
A_PDW-01A1A.1.0 | A_PDW-01A1A.21.0 | 1
A_PDW-01A1A.1.0 | A_PDW-01A1A.27.0 | 1
A_PDW-01A1A.1.0 | A_PDW-01A1A.30.0 | 1
A_PDW-01A1A.11.0 | A_PDW-01A1A.14.0 | 1
A_PDW-01A1A.11.0 | A_PDW-01A1A.17.0 | 1
A_PDW-01A1A.11.0 | A_PDW-01A1AIF.1.0 | 1
A_PDW-01A1A.11.0 | A_PDW8 | 1
A_PDW-01A1A.11.0 | A_PDW9 | 1
A_PDW-01A1A.11.0 | A_PDW13 | 1
A_PDW-01A1A.11.0 | A_PDW43 | 1
A_PDW-01A1A.13.0 | A_PDW16 | 1
A_PDW-01A1A.13.0 | A_PDW17 | 1
A_PDW-01A1A.13.0 | A_PDW19 | 1
A_PDW-01A1A.13.0 | A_PDW45 | 1
A_PDW-01A1A.14.0 | A_PDW-01A1A.17.0 | 1
A_PDW-01A1A.14.0 | A_PDW-01A1AIF.1.0 | 1
A_PDW-01A1A.14.0 | A_PDW8 | 1
A_PDW-01A1A.14.0 | A_PDW9 | 1
A_PDW-01A1A.14.0 | A_PDW13 | 1
A_PDW-01A1A.14.0 | A_PDW43 | 1
A_PDW-01A1A.17.0 | A_PDW8 | 1
A_PDW-01A1A.17.0 | A_PDW9 | 1
A_PDW-01A1A.17.0 | A_PDW13 | 1
A_PDW-01A1A.21.0 | A_PDW-01A1A.30.0 | 1
A_PDW-01A1A.27.0 | A_PDW-01A1A.30.0 | 1
A_PDW2 | A_PDW3 | 1
A_PDW2 | A_PDW5 | 1
A_PDW2 | A_PDW12 | 1
A_PDW2 | A_PDW12.1 | 1
A_PDW2 | A_PDW10 | 1
A_PDW3 | A_PDW5 | 1
A_PDW3 | A_PDW12 | 1
A_PDW3 | A_PDW12.1 | 1
A_PDW3 | A_PDW10 | 1
A_PDW4 | A_PDW22 | 1
A_PDW4 | A_PDW26 | 1
A_PDW5 | A_PDW12 | 1
A_PDW5 | A_PDW12.1 | 1
A_PDW5 | A_PDW10 | 1
A_PDW-01A1AIF.1.0 | A_PDW-01A1A.17.0 | 1
A_PDW-01A1AIF.1.0 | A_PDW8 | 1
A_PDW-01A1AIF.1.0 | A_PDW9 | 1
A_PDW-01A1AIF.1.0 | A_PDW13 | 1
A_PDW-01A1AIF.1.0 | A_PDW43 | 1
A_PDW8 | A_PDW13 | 1
A_PDW9 | A_PDW8 | 1
A_PDW9 | A_PDW13 | 1
A_PDW12 | A_PDW10 | 1
A_PDW12.1 | A_PDW12 | 1
A_PDW12.1 | A_PDW10 | 1
A_PDW15 | A_PDW24 | 1
A_PDW15 | A_PDW42 | 1
A_PDW16 | A_PDW17 | 1
A_PDW16 | A_PDW19 | 1
A_PDW16 | A_PDW45 | 1
A_PDW18 | A_PDW4 | 1
A_PDW18 | A_PDW22 | 1
A_PDW18 | A_PDW26 | 1
A_PDW19 | A_PDW17 | 1
A_PDW19 | A_PDW45 | 1
A_PDW20 | A_PDW25 | 1
A_PDW20 | A_PDW41 | 1
A_PDW21 | A_PDW-01A1A.13.0 | 1
A_PDW21 | A_PDW16 | 1
A_PDW21 | A_PDW17 | 1
A_PDW21 | A_PDW19 | 1
A_PDW21 | A_PDW45 | 1
A_PDW22 | A_PDW26 | 1
A_PDW25 | A_PDW41 | 1
A_PDW28 | A_PDW20 | 1
A_PDW28 | A_PDW25 | 1
A_PDW28 | A_PDW41 | 1
A_PDW29 | A_PDW31 | 1
A_PDW29 | A_PDW32 | 1
A_PDW29 | A_PDW39 | 1
A_PDW30 | A_PDW33 | 1
A_PDW31 | A_PDW32 | 1
A_PDW34 | A_PDW30 | 1
A_PDW34 | A_PDW32 | 1
A_PDW34 | A_PDW33 | 1
A_PDW36 | A_PDW20 | 1
A_PDW36 | A_PDW25 | 1
A_PDW36 | A_PDW28 | 1
A_PDW36 | A_PDW41 | 1
A_PDW36 | A_PDW44 | 1
A_PDW37 | A_PDW15 | 1
A_PDW37 | A_PDW24 | 1
A_PDW37 | A_PDW32 | 1
A_PDW37 | A_PDW33 | 1
A_PDW37 | A_PDW40 | 1
A_PDW37 | A_PDW42 | 1
A_PDW38 | A_PDW24 | 1
A_PDW38 | A_PDW30 | 1
A_PDW38 | A_PDW31 | 1
A_PDW38 | A_PDW33 | 1
A_PDW38 | A_PDW34 | 1
A_PDW39 | A_PDW31 | 1
A_PDW39 | A_PDW32 | 1
A_PDW40 | A_PDW15 | 1
A_PDW40 | A_PDW24 | 1
A_PDW40 | A_PDW33 | 1
A_PDW40 | A_PDW39 | 1
A_PDW40 | A_PDW42 | 1
A_PDW42 | A_PDW24 | 1
A_PDW43 | A_PDW-01A1A.17.0 | 1
A_PDW43 | A_PDW8 | 1
A_PDW43 | A_PDW9 | 1
A_PDW43 | A_PDW13 | 1
A_PDW44 | A_PDW20 | 1
A_PDW44 | A_PDW25 | 1
A_PDW44 | A_PDW28 | 1
A_PDW44 | A_PDW41 | 1
A_PDW45 | A_PDW17 | 1
B_PDW-01A1A.1.0 | B_PDW-01A1A.27.0 | 1
B_PDW-01A1A.13.0 | B_PDW-01A1A.17.0 | 1
B_PDW-01A1A.13.0 | B_PDW-01A1A.30.0 | 1
B_PDW-01A1A.13.0 | B_PDW-01A1AIF.1.0 | 1
B_PDW-01A1A.13.0 | B_PDW8 | 1
B_PDW-01A1A.13.0 | B_PDW9 | 1
B_PDW-01A1A.13.0 | B_PDW13 | 1
B_PDW-01A1A.13.0 | B_PDW12.1 | 1
B_PDW-01A1A.17.0 | B_PDW-01A1AIF.1.0 | 1
B_PDW-01A1A.17.0 | B_PDW8 | 1
B_PDW-01A1A.17.0 | B_PDW9 | 1
B_PDW-01A1A.17.0 | B_PDW13 | 1
B_PDW-01A1A.17.0 | B_PDW12.1 | 1
B_PDW-01A1A.21.0 | B_PDW-01A1A.13.0 | 1
B_PDW-01A1A.21.0 | B_PDW-01A1A.17.0 | 1
B_PDW-01A1A.21.0 | B_PDW-01A1A.27.0 | 1
B_PDW-01A1A.21.0 | B_PDW-01A1A.30.0 | 1
B_PDW-01A1A.21.0 | B_PDW-01A1AIF.1.0 | 1
B_PDW-01A1A.21.0 | B_PDW8 | 1
B_PDW-01A1A.21.0 | B_PDW9 | 1
B_PDW-01A1A.21.0 | B_PDW13 | 1
B_PDW-01A1A.21.0 | B_PDW12.1 | 1
B_PDW-01A1A.30.0 | B_PDW-01A1A.17.0 | 1
B_PDW-01A1A.30.0 | B_PDW-01A1AIF.1.0 | 1
B_PDW-01A1A.30.0 | B_PDW8 | 1
B_PDW-01A1A.30.0 | B_PDW9 | 1
B_PDW-01A1A.30.0 | B_PDW13 | 1
B_PDW-01A1A.30.0 | B_PDW12.1 | 1
B_PDW5 | B_PDW12 | 1
B_PDW5 | B_PDW10 | 1
B_PDW-01A1AIF.1.0 | B_PDW8 | 1
B_PDW-01A1AIF.1.0 | B_PDW9 | 1
B_PDW-01A1AIF.1.0 | B_PDW13 | 1
B_PDW-01A1AIF.1.0 | B_PDW12.1 | 1
B_PDW8 | B_PDW13 | 1
B_PDW9 | B_PDW8 | 1
B_PDW9 | B_PDW13 | 1
B_PDW9 | B_PDW12.1 | 1
B_PDW12 | B_PDW10 | 1
B_PDW12.1 | B_PDW8 | 1
B_PDW12.1 | B_PDW13 | 1
B_PDW15 | B_PDW32 | 1
B_PDW16 | B_PDW17 | 1
B_PDW16 | B_PDW19 | 1
B_PDW18 | B_PDW16 | 1
B_PDW18 | B_PDW17 | 1
B_PDW18 | B_PDW19 | 1
B_PDW18 | B_PDW44 | 1
B_PDW19 | B_PDW17 | 1
B_PDW20 | B_PDW45 | 1
B_PDW21 | B_PDW13 | 1
B_PDW21 | B_PDW12.1 | 1
B_PDW21 | B_PDW31 | 1
B_PDW21 | B_PDW34 | 1
B_PDW21 | B_PDW41 | 1
B_PDW21 | B_PDW42 | 1
B_PDW22 | B_PDW26 | 1
B_PDW28 | B_PDW30 | 1
B_PDW28 | B_PDW41 | 1
B_PDW29 | B_PDW25 | 1
B_PDW29 | B_PDW43 | 1
B_PDW30 | B_PDW41 | 1
B_PDW33 | B_PDW24 | 1
B_PDW34 | B_PDW31 | 1
B_PDW34 | B_PDW42 | 1
B_PDW36 | B_PDW15 | 1
B_PDW36 | B_PDW32 | 1
B_PDW37 | B_PDW-01A1A.30.0 | 1
B_PDW37 | B_PDW-01A1AIF.1.0 | 1
B_PDW37 | B_PDW8 | 1
B_PDW37 | B_PDW9 | 1
B_PDW37 | B_PDW13 | 1
B_PDW37 | B_PDW12.1 | 1
B_PDW37 | B_PDW16 | 1
B_PDW37 | B_PDW19 | 1
B_PDW37 | B_PDW25 | 1
B_PDW37 | B_PDW28 | 1
B_PDW37 | B_PDW30 | 1
B_PDW37 | B_PDW31 | 1
B_PDW37 | B_PDW32 | 1
B_PDW37 | B_PDW34 | 1
B_PDW37 | B_PDW40 | 1
B_PDW37 | B_PDW41 | 1
B_PDW37 | B_PDW42 | 1
B_PDW38 | B_PDW25 | 1
B_PDW38 | B_PDW29 | 1
B_PDW38 | B_PDW43 | 1
B_PDW39 | B_PDW24 | 1
B_PDW39 | B_PDW33 | 1
B_PDW40 | B_PDW-01A1AIF.1.0 | 1
B_PDW40 | B_PDW8 | 1
B_PDW40 | B_PDW9 | 1
B_PDW40 | B_PDW13 | 1
B_PDW40 | B_PDW12.1 | 1
B_PDW40 | B_PDW15 | 1
B_PDW40 | B_PDW28 | 1
B_PDW40 | B_PDW29 | 1
B_PDW40 | B_PDW30 | 1
B_PDW40 | B_PDW41 | 1
B_PDW40 | B_PDW42 | 1
B_PDW42 | B_PDW31 | 1
B_PDW43 | B_PDW25 | 1
B_PDW44 | B_PDW-01A1AIF.1.0 | 1
B_PDW44 | B_PDW16 | 1
B_PDW44 | B_PDW17 | 1
B_PDW44 | B_PDW19 | 1
C_PDW-01A1A.1.0 | C_PDW-01A1A.21.0 | 1
C_PDW-01A1A.1.0 | C_PDW-01A1A.27.0 | 1
C_PDW-01A1A.1.0 | C_PDW-01A1A.30.0 | 1
C_PDW-01A1A.11.0 | C_PDW-01A1A.17.0 | 1
C_PDW-01A1A.11.0 | C_PDW-01A1AIF.1.0 | 1
C_PDW-01A1A.11.0 | C_PDW8 | 1
C_PDW-01A1A.11.0 | C_PDW13 | 1
C_PDW-01A1A.13.0 | C_PDW24 | 1
C_PDW-01A1A.13.0 | C_PDW28 | 1
C_PDW-01A1A.14.0 | C_PDW8 | 1
C_PDW-01A1A.14.0 | C_PDW13 | 1
C_PDW-01A1A.14.0 | C_PDW12 | 1
C_PDW-01A1A.14.0 | C_PDW30 | 1
C_PDW-01A1A.14.0 | C_PDW34 | 1
C_PDW-01A1A.14.0 | C_PDW41 | 1
C_PDW-01A1A.17.0 | C_PDW8 | 1
C_PDW-01A1A.17.0 | C_PDW13 | 1
C_PDW-01A1A.21.0 | C_PDW-01A1A.30.0 | 1
C_PDW2 | C_PDW-01A1A.11.0 | 1
C_PDW2 | C_PDW-01A1A.17.0 | 1
C_PDW2 | C_PDW3 | 1
C_PDW2 | C_PDW-01A1AIF.1.0 | 1
C_PDW2 | C_PDW8 | 1
C_PDW2 | C_PDW13 | 1
C_PDW3 | C_PDW-01A1A.11.0 | 1
C_PDW3 | C_PDW-01A1A.17.0 | 1
C_PDW3 | C_PDW-01A1AIF.1.0 | 1
C_PDW3 | C_PDW8 | 1
C_PDW3 | C_PDW13 | 1
C_PDW4 | C_PDW-01A1A.21.0 | 1
C_PDW4 | C_PDW-01A1A.27.0 | 1
C_PDW4 | C_PDW8 | 1
C_PDW4 | C_PDW13 | 1
C_PDW4 | C_PDW17 | 1
C_PDW4 | C_PDW19 | 1
C_PDW5 | C_PDW9 | 1
C_PDW5 | C_PDW10 | 1
C_PDW-01A1AIF.1.0 | C_PDW-01A1A.17.0 | 1
C_PDW-01A1AIF.1.0 | C_PDW8 | 1
C_PDW-01A1AIF.1.0 | C_PDW13 | 1
C_PDW9 | C_PDW10 | 1
C_PDW13 | C_PDW8 | 1
C_PDW12 | C_PDW30 | 1
C_PDW12 | C_PDW41 | 1
C_PDW12.1 | C_PDW33 | 1
C_PDW12.1 | C_PDW45 | 1
C_PDW16 | C_PDW4 | 1
C_PDW16 | C_PDW17 | 1
C_PDW16 | C_PDW19 | 1
C_PDW17 | C_PDW19 | 1
C_PDW18 | C_PDW4 | 1
C_PDW18 | C_PDW16 | 1
C_PDW18 | C_PDW17 | 1
C_PDW18 | C_PDW19 | 1
C_PDW18.1 | C_PDW32 | 1
C_PDW18.1 | C_PDW42 | 1
C_PDW18.2 | C_PDW15 | 1
C_PDW18.2 | C_PDW20 | 1
C_PDW18.2 | C_PDW39 | 1
C_PDW20 | C_PDW15 | 1
C_PDW21 | C_PDW-01A1A.14.0 | 1
C_PDW21 | C_PDW8 | 1
C_PDW21 | C_PDW12 | 1
C_PDW21 | C_PDW30 | 1
C_PDW21 | C_PDW34 | 1
C_PDW21 | C_PDW41 | 1
C_PDW22 | C_PDW26 | 1
C_PDW28 | C_PDW24 | 1
C_PDW29 | C_PDW25 | 1
C_PDW29 | C_PDW31 | 1
C_PDW29 | C_PDW43 | 1
C_PDW30 | C_PDW41 | 1
C_PDW31 | C_PDW25 | 1
C_PDW33 | C_PDW45 | 1
C_PDW34 | C_PDW-01A1A.21.0 | 1
C_PDW34 | C_PDW-01A1A.30.0 | 1
C_PDW34 | C_PDW13 | 1
C_PDW34 | C_PDW12 | 1
C_PDW34 | C_PDW30 | 1
C_PDW34 | C_PDW41 | 1
C_PDW36 | C_PDW25 | 1
C_PDW36 | C_PDW29 | 1
C_PDW36 | C_PDW31 | 1
C_PDW36 | C_PDW38 | 1
C_PDW36 | C_PDW43 | 1
C_PDW37 | C_PDW-01A1A.30.0 | 1
C_PDW37 | C_PDW-01A1AIF.1.0 | 1
C_PDW37 | C_PDW8 | 1
C_PDW37 | C_PDW13 | 1
C_PDW37 | C_PDW18.1 | 1
C_PDW37 | C_PDW19 | 1
C_PDW37 | C_PDW28 | 1
C_PDW37 | C_PDW32 | 1
C_PDW37 | C_PDW34 | 1
C_PDW37 | C_PDW41 | 1
C_PDW37 | C_PDW42 | 1
C_PDW37 | C_PDW44 | 1
C_PDW38 | C_PDW25 | 1
C_PDW38 | C_PDW29 | 1
C_PDW38 | C_PDW31 | 1
C_PDW38 | C_PDW43 | 1
C_PDW39 | C_PDW15 | 1
C_PDW39 | C_PDW20 | 1
C_PDW40 | C_PDW15 | 1
C_PDW40 | C_PDW18.2 | 1
C_PDW40 | C_PDW20 | 1
C_PDW40 | C_PDW39 | 1
C_PDW42 | C_PDW32 | 1
C_PDW43 | C_PDW25 | 1
C_PDW43 | C_PDW31 | 1
C_PDW44 | C_PDW18.1 | 1
C_PDW44 | C_PDW32 | 1
C_PDW44 | C_PDW42 | 1

## N
stage | number of station | value
1 | 2 | 1
2 | 3 | 1
3 | 1 | 1
5 | 3 | 1
6 | 1 | 1
7 | 2 | 1
8 | 1 | 1