## X
task | stage | resource option | resource type req
A_PDW-01A1A.1.0 | 2 | 2 | ['worker', 'robot arm']
A_PDW-01A1A.11.0 | 2 | 0 | ['worker']
A_PDW-01A1A.13.0 | 2 | 0 | ['worker']
A_PDW-01A1A.14.0 | 2 | 0 | ['worker']
A_PDW-01A1A.17.0 | 2 | 1 | ['worker', 'robot arm']
B_PDW-01A1A.1.0 | 2 | 2 | ['worker', 'robot arm']
B_PDW-01A1A.13.0 | 2 | 0 | ['worker']
B_PDW-01A1A.17.0 | 2 | 0 | ['worker']
C_PDW-01A1A.1.0 | 2 | 2 | ['worker', 'robot arm']
C_PDW-01A1A.11.0 | 2 | 0 | ['worker']
C_PDW-01A1A.13.0 | 2 | 0 | ['worker']
C_PDW-01A1A.14.0 | 2 | 0 | ['worker']
C_PDW-01A1A.17.0 | 2 | 1 | ['worker', 'robot arm']
A_PDW-01A1A.21.0 | 3 | 0 | ['worker']
A_PDW-01A1A.27.0 | 3 | 0 | ['worker']
A_PDW-01A1A.30.0 | 3 | 0 | ['worker']
A_PDW2 | 3 | 0 | ['dryer']
A_PDW3 | 3 | 0 | ['dryer']
A_PDW5 | 3 | 0 | ['dryer']
B_PDW-01A1A.21.0 | 3 | 0 | ['worker']
B_PDW-01A1A.27.0 | 3 | 0 | ['worker']
B_PDW-01A1A.30.0 | 3 | 0 | ['worker']
B_PDW5 | 3 | 0 | ['dryer']
C_PDW-01A1A.21.0 | 3 | 0 | ['worker']
C_PDW-01A1A.27.0 | 3 | 0 | ['worker']
C_PDW-01A1A.30.0 | 3 | 0 | ['worker']
C_PDW2 | 3 | 0 | ['worker']
C_PDW3 | 3 | 0 | ['worker']
C_PDW5 | 3 | 0 | ['dryer']
A_PDW4 | 4 | 0 | ['dryer']
A_PDW-01A1AIF.1.0 | 4 | 0 | ['worker']
A_PDW8 | 4 | 0 | ['worker']
A_PDW9 | 4 | 1 | ['worker']
A_PDW13 | 4 | 0 | ['worker']
A_PDW12 | 4 | 0 | ['dryer']
A_PDW10 | 4 | 0 | ['dryer']
A_PDW15 | 4 | 1 | ['worker']
A_PDW18 | 4 | 0 | ['dryer']
A_PDW19 | 4 | 0 | ['worker']
B_PDW-01A1AIF.1.0 | 4 | 0 | ['worker']
B_PDW8 | 4 | 0 | ['worker']
B_PDW9 | 4 | 0 | ['worker']
B_PDW13 | 4 | 0 | ['worker']
B_PDW12 | 4 | 0 | ['worker']
B_PDW10 | 4 | 0 | ['dryer']
B_PDW15 | 4 | 1 | ['worker']
B_PDW18 | 4 | 1 | ['worker']
B_PDW19 | 4 | 0 | ['worker']
C_PDW4 | 4 | 0 | ['worker']
C_PDW-01A1AIF.1.0 | 4 | 0 | ['worker']
C_PDW8 | 4 | 1 | ['worker']
C_PDW9 | 4 | 1 | ['worker']
C_PDW13 | 4 | 0 | ['worker']
C_PDW12 | 4 | 0 | ['worker']
C_PDW10 | 4 | 0 | ['dryer']
C_PDW15 | 4 | 1 | ['worker']
C_PDW18 | 4 | 1 | ['worker']
C_PDW18.1 | 4 | 1 | ['worker']
C_PDW18.2 | 4 | 1 | ['worker']
C_PDW19 | 4 | 0 | ['worker']
A_PDW12.1 | 6 | 0 | ['dryer']
A_PDW16 | 6 | 0 | ['worker']
A_PDW17 | 6 | 0 | ['worker']
A_PDW20 | 6 | 0 | ['worker']
A_PDW21 | 6 | 0 | ['worker']
A_PDW24 | 6 | 0 | ['worker']
A_PDW25 | 6 | 0 | ['worker']
A_PDW26 | 6 | 1 | ['dryer', 'worker']
A_PDW29 | 6 | 0 | ['worker']
A_PDW34 | 6 | 0 | ['worker']
A_PDW42 | 6 | 0 | ['worker']
B_PDW12.1 | 6 | 0 | ['worker']
B_PDW16 | 6 | 1 | ['worker']
B_PDW17 | 6 | 0 | ['worker']
B_PDW20 | 6 | 0 | ['worker']
B_PDW21 | 6 | 0 | ['worker']
B_PDW24 | 6 | 0 | ['worker']
B_PDW25 | 6 | 0 | ['worker']
B_PDW26 | 6 | 1 | ['dryer', 'worker']
B_PDW29 | 6 | 0 | ['worker']
B_PDW34 | 6 | 0 | ['worker']
B_PDW42 | 6 | 0 | ['worker']
C_PDW12.1 | 6 | 0 | ['worker']
C_PDW16 | 6 | 1 | ['worker']
C_PDW17 | 6 | 0 | ['worker']
C_PDW20 | 6 | 0 | ['worker']
C_PDW21 | 6 | 0 | ['worker']
C_PDW24 | 6 | 0 | ['worker']
C_PDW25 | 6 | 0 | ['worker']
C_PDW26 | 6 | 1 | ['dryer', 'worker']
C_PDW29 | 6 | 0 | ['worker']
C_PDW34 | 6 | 0 | ['worker']
C_PDW42 | 6 | 0 | ['worker']
A_PDW22 | 5 | 0 | ['dryer']
B_PDW22 | 5 | 0 | ['dryer']
C_PDW22 | 5 | 0 | ['dryer']
A_PDW28 | 8 | 0 | ['worker']
A_PDW30 | 8 | 0 | ['worker']
A_PDW31 | 8 | 0 | ['worker']
A_PDW32 | 8 | 0 | ['worker']
A_PDW33 | 8 | 0 | ['worker']
A_PDW36 | 8 | 0 | ['worker']
A_PDW37 | 8 | 0 | ['worker']
A_PDW38 | 8 | 0 | ['worker']
A_PDW39 | 8 | 0 | ['worker']
A_PDW40 | 8 | 0 | ['worker']
A_PDW41 | 8 | 0 | ['worker']
A_PDW43 | 8 | 0 | ['worker']
A_PDW44 | 8 | 0 | ['worker']
A_PDW45 | 8 | 0 | ['worker']
B_PDW28 | 8 | 0 | ['worker']
B_PDW30 | 8 | 1 | ['worker']
B_PDW31 | 8 | 0 | ['worker']
B_PDW32 | 8 | 0 | ['worker']
B_PDW33 | 8 | 0 | ['worker']
B_PDW36 | 8 | 0 | ['worker']
B_PDW37 | 8 | 0 | ['worker']
B_PDW38 | 8 | 0 | ['worker']
B_PDW39 | 8 | 0 | ['worker']
B_PDW40 | 8 | 0 | ['worker']
B_PDW41 | 8 | 0 | ['worker']
B_PDW43 | 8 | 0 | ['worker']
B_PDW44 | 8 | 0 | ['worker']
B_PDW45 | 8 | 0 | ['worker']
C_PDW28 | 8 | 0 | ['worker']
C_PDW30 | 8 | 1 | ['worker']
C_PDW31 | 8 | 0 | ['worker']
C_PDW32 | 8 | 0 | ['worker']
C_PDW33 | 8 | 0 | ['worker']
C_PDW36 | 8 | 0 | ['worker']
C_PDW37 | 8 | 0 | ['worker']
C_PDW38 | 8 | 0 | ['worker']
C_PDW39 | 8 | 0 | ['worker']
C_PDW40 | 8 | 0 | ['worker']
C_PDW41 | 8 | 0 | ['worker']
C_PDW43 | 8 | 0 | ['worker']
C_PDW44 | 8 | 0 | ['worker']
C_PDW45 | 8 | 0 | ['worker']

## Y
worker | stage | number of station | team cost | stage team cost
1 | 2 | 1 | 55 | 55
8 | 2 | 1 | 90 | 90
3 | 3 | 2 | 55 | 110
9 | 3 | 2 | 50 | 100
1 | 4 | 2 | 55 | 110
3 | 4 | 2 | 55 | 110
5 | 4 | 2 | 50 | 100
1 | 6 | 2 | 55 | 110
3 | 6 | 2 | 55 | 110
4 | 6 | 2 | 50 | 100
9 | 5 | 2 | 50 | 100
1 | 8 | 3 | 55 | 165

## T
task | task name | start time
A_PDW-01A1A.1.0 | 1. Frame | 0
A_PDW-01A1A.11.0 | 11. Install bath tub / shower pan | 45
A_PDW-01A1A.13.0 | 13. Install ceiling CLG-01A | 51
A_PDW-01A1A.14.0 | 14. Connect Fire Sprinkler Ceiling Assemblies | 82
A_PDW-01A1A.17.0 | 17. Install electrical panel | 61
B_PDW-01A1A.1.0 | 1. Frame | 0
B_PDW-01A1A.13.0 | 13. Install ceiling CLG-01A | 40
B_PDW-01A1A.17.0 | 17. Install electrical panel | 50
C_PDW-01A1A.1.0 | 1. Frame | 0
C_PDW-01A1A.11.0 | 11. Install bath tub / shower pan | 45
C_PDW-01A1A.13.0 | 13. Install ceiling CLG-01A | 51
C_PDW-01A1A.14.0 | 14. Connect Fire Sprinkler Ceiling Assemblies | 82
C_PDW-01A1A.17.0 | 17. Install electrical panel | 61
A_PDW-01A1A.21.0 | 21. Conduct Plumbing & sprinkler Pressure Test | 0
A_PDW-01A1A.27.0 | 27. Install Lid LID-01A | 5
A_PDW-01A1A.30.0 | 30. Move Pod to Finish Station | 18
A_PDW2 | Bathroom insulation, drywall and tape/bed | 58
A_PDW3 | kitchen insulation, drywall and tape/bed | 70
A_PDW5 | dry bathroom | 89
B_PDW-01A1A.21.0 | 21. Conduct Plumbing & sprinkler Pressure Test | 0
B_PDW-01A1A.27.0 | 27. Install Lid LID-01A | 5
B_PDW-01A1A.30.0 | 30. Move Pod to Finish Station | 18
B_PDW5 | dry bathroom | 58
C_PDW-01A1A.21.0 | 21. Conduct Plumbing & sprinkler Pressure Test | 0
C_PDW-01A1A.27.0 | 27. Install Lid LID-01A | 5
C_PDW-01A1A.30.0 | 30. Move Pod to Finish Station | 18
C_PDW2 | Bathroom insulation, drywall and tape/bed | 58
C_PDW3 | kitchen insulation, drywall and tape/bed | 70
C_PDW5 | dry bathroom | 89
A_PDW4 | exterior insulation, drywall and tape/bed | 0
A_PDW-01A1AIF.1.0 | 1. Set-up for finishing stage | 0
A_PDW8 | skim bathroom | 13
A_PDW9 | skim kitchen | 5
A_PDW13 | skim outside | 13
A_PDW12 | install doors and casing Bathroom | 19
A_PDW10 | skim dry bathroom | 39
A_PDW15 | sand bathroom | 164
A_PDW18 | Install Tub/Shower Surround | 177
A_PDW19 | Prime paint bathroom | 187
B_PDW-01A1AIF.1.0 | 1. Set-up for finishing stage | 0
B_PDW8 | skim bathroom | 0
B_PDW9 | skim kitchen | 5
B_PDW13 | skim outside | 22
B_PDW12 | install doors and casing Bathroom | 22
B_PDW10 | skim dry bathroom | 22
B_PDW15 | sand bathroom | 132
B_PDW18 | Install Tub/Shower Surround | 145
B_PDW19 | Prime paint bathroom | 152
C_PDW4 | exterior insulation, drywall and tape/bed | 39.0993
C_PDW-01A1AIF.1.0 | 1. Set-up for finishing stage | 0
C_PDW8 | skim bathroom | 13
C_PDW9 | skim kitchen | 5
C_PDW13 | skim outside | 32
C_PDW12 | install doors and casing Bathroom | 32
C_PDW10 | skim dry bathroom | 32
C_PDW15 | sand bathroom | 157
C_PDW18 | Install Tub/Shower Surround | 170
C_PDW18.1 | Install Tub/Shower Surround | 180
C_PDW18.2 | Install Tub/Shower Surround | 194
C_PDW19 | Prime paint bathroom | 177
A_PDW12.1 | install doors and casing Kitchen | 0
A_PDW16 | sand kitchen | 0
A_PDW17 | sand outside | 0
A_PDW20 | Prime paint kitchen | 60
A_PDW21 | Apply wall covering | 35
A_PDW24 | Paint bathroom | 17
A_PDW25 | Paint kitchen | 37
A_PDW26 | Paint dry | 74
A_PDW29 | cove base kitchen | 154
A_PDW34 | Install Electrical Fixtures & trim | 168
A_PDW42 | Batt Insulation in walls | 82
B_PDW12.1 | install doors and casing Kitchen | 8
B_PDW16 | sand kitchen | 0
B_PDW17 | sand outside | 8
B_PDW20 | Prime paint kitchen | 28
B_PDW21 | Apply wall covering | 43
B_PDW24 | Paint bathroom | 45
B_PDW25 | Paint kitchen | 50
B_PDW26 | Paint dry | 88
B_PDW29 | cove base kitchen | 168
B_PDW34 | Install Electrical Fixtures & trim | 182
B_PDW42 | Batt Insulation in walls | 87
C_PDW12.1 | install doors and casing Kitchen | 8
C_PDW16 | sand kitchen | 0
C_PDW17 | sand outside | 8
C_PDW20 | Prime paint kitchen | 67
C_PDW21 | Apply wall covering | 28
C_PDW24 | Paint bathroom | 28
C_PDW25 | Paint kitchen | 30
C_PDW26 | Paint dry | 71
C_PDW29 | cove base kitchen | 151
C_PDW34 | Install Electrical Fixtures & trim | 165
C_PDW42 | Batt Insulation in walls | 89
A_PDW22 | Prime dry bathroom | 0
B_PDW22 | Prime dry bathroom | 0
C_PDW22 | Prime dry bathroom | 0
A_PDW28 | cove base bathroom | 0
A_PDW30 | bathroom plumbing | 14
A_PDW31 | bathroom trim | 39
A_PDW32 | Install Interior Cabinets & Countertops | 129
A_PDW33 | Kitchen plumbing and appliances | 104
A_PDW36 | 25. Connect POD to POD | 64
A_PDW37 | 26. Install interior pod to pod connection finishes | 74
A_PDW38 | 27. Connect pod to pod electrical | 94
A_PDW39 | 28. Install Batt Insulation in lids and Inspection | 75
A_PDW40 | 30. Install Sheathing on top of lids | 89
A_PDW41 | Perform test | 174
A_PDW43 | 40. Execute final interior punch - close NCRs | 299
A_PDW44 | 42. Final clean-up entire module | 319
A_PDW45 | Wrap, document and move to ship | 329
B_PDW28 | cove base bathroom | 0
B_PDW30 | bathroom plumbing | 14
B_PDW31 | bathroom trim | 29
B_PDW32 | Install Interior Cabinets & Countertops | 119
B_PDW33 | Kitchen plumbing and appliances | 94
B_PDW36 | 25. Connect POD to POD | 54
B_PDW37 | 26. Install interior pod to pod connection finishes | 64
B_PDW38 | 27. Connect pod to pod electrical | 84
B_PDW39 | 28. Install Batt Insulation in lids and Inspection | 65
B_PDW40 | 30. Install Sheathing on top of lids | 79
B_PDW41 | Perform test | 164
B_PDW43 | 40. Execute final interior punch - close NCRs | 289
B_PDW44 | 42. Final clean-up entire module | 309
B_PDW45 | Wrap, document and move to ship | 319
C_PDW28 | cove base bathroom | 0
C_PDW30 | bathroom plumbing | 14
C_PDW31 | bathroom trim | 29
C_PDW32 | Install Interior Cabinets & Countertops | 119
C_PDW33 | Kitchen plumbing and appliances | 94
C_PDW36 | 25. Connect POD to POD | 54
C_PDW37 | 26. Install interior pod to pod connection finishes | 64
C_PDW38 | 27. Connect pod to pod electrical | 84
C_PDW39 | 28. Install Batt Insulation in lids and Inspection | 65
C_PDW40 | 30. Install Sheathing on top of lids | 79
C_PDW41 | Perform test | 164
C_PDW43 | 40. Execute final interior punch - close NCRs | 289
C_PDW44 | 42. Final clean-up entire module | 309
C_PDW45 | Wrap, document and move to ship | 319

## A
worker | task | stage
1 | A_PDW-01A1A.1.0 | 2
1 | A_PDW-01A1A.11.0 | 2
1 | A_PDW-01A1A.13.0 | 2
1 | A_PDW-01A1A.14.0 | 2
1 | A_PDW-01A1A.17.0 | 2
1 | B_PDW-01A1A.1.0 | 2
1 | B_PDW-01A1A.13.0 | 2
1 | B_PDW-01A1A.17.0 | 2
1 | C_PDW-01A1A.1.0 | 2
1 | C_PDW-01A1A.11.0 | 2
1 | C_PDW-01A1A.13.0 | 2
1 | C_PDW-01A1A.14.0 | 2
1 | C_PDW-01A1A.17.0 | 2
8 | A_PDW-01A1A.1.0 | 2
8 | A_PDW-01A1A.17.0 | 2
8 | B_PDW-01A1A.1.0 | 2
8 | C_PDW-01A1A.1.0 | 2
8 | C_PDW-01A1A.17.0 | 2
3 | A_PDW-01A1A.21.0 | 3
3 | A_PDW-01A1A.27.0 | 3
3 | A_PDW-01A1A.30.0 | 3
3 | B_PDW-01A1A.21.0 | 3
3 | B_PDW-01A1A.27.0 | 3
3 | B_PDW-01A1A.30.0 | 3
3 | C_PDW-01A1A.21.0 | 3
3 | C_PDW-01A1A.27.0 | 3
3 | C_PDW-01A1A.30.0 | 3
3 | C_PDW2 | 3
3 | C_PDW3 | 3
9 | A_PDW2 | 3
9 | A_PDW3 | 3
9 | A_PDW5 | 3
9 | B_PDW5 | 3
9 | C_PDW5 | 3
1 | A_PDW-01A1AIF.1.0 | 4
1 | A_PDW9 | 4
1 | A_PDW13 | 4
1 | A_PDW15 | 4
1 | A_PDW19 | 4
1 | B_PDW8 | 4
1 | B_PDW12 | 4
1 | B_PDW15 | 4
1 | B_PDW18 | 4
1 | B_PDW19 | 4
1 | C_PDW4 | 4
1 | C_PDW8 | 4
1 | C_PDW9 | 4
1 | C_PDW12 | 4
1 | C_PDW15 | 4
1 | C_PDW18 | 4
1 | C_PDW18.1 | 4
1 | C_PDW18.2 | 4
1 | C_PDW19 | 4
3 | A_PDW8 | 4
3 | A_PDW9 | 4
3 | A_PDW15 | 4
3 | B_PDW-01A1AIF.1.0 | 4
3 | B_PDW9 | 4
3 | B_PDW13 | 4
3 | B_PDW15 | 4
3 | B_PDW18 | 4
3 | C_PDW-01A1AIF.1.0 | 4
3 | C_PDW8 | 4
3 | C_PDW9 | 4
3 | C_PDW13 | 4
3 | C_PDW15 | 4
3 | C_PDW18 | 4
5 | A_PDW4 | 4
5 | A_PDW12 | 4
5 | A_PDW10 | 4
5 | A_PDW18 | 4
5 | B_PDW10 | 4
5 | C_PDW10 | 4
1 | A_PDW16 | 6
1 | A_PDW20 | 6
1 | A_PDW24 | 6
1 | A_PDW29 | 6
1 | A_PDW42 | 6
1 | B_PDW16 | 6
1 | B_PDW17 | 6
1 | B_PDW21 | 6
1 | B_PDW24 | 6
1 | B_PDW26 | 6
1 | B_PDW29 | 6
1 | B_PDW34 | 6
1 | C_PDW12.1 | 6
1 | C_PDW16 | 6
1 | C_PDW20 | 6
1 | C_PDW21 | 6
1 | C_PDW25 | 6
1 | C_PDW29 | 6
1 | C_PDW42 | 6
3 | A_PDW17 | 6
3 | A_PDW21 | 6
3 | A_PDW25 | 6
3 | A_PDW26 | 6
3 | A_PDW34 | 6
3 | B_PDW12.1 | 6
3 | B_PDW16 | 6
3 | B_PDW20 | 6
3 | B_PDW25 | 6
3 | B_PDW42 | 6
3 | C_PDW16 | 6
3 | C_PDW17 | 6
3 | C_PDW24 | 6
3 | C_PDW26 | 6
3 | C_PDW34 | 6
4 | A_PDW12.1 | 6
4 | A_PDW26 | 6
4 | B_PDW26 | 6
4 | C_PDW26 | 6
9 | A_PDW22 | 5
9 | B_PDW22 | 5
9 | C_PDW22 | 5
1 | A_PDW28 | 8
1 | A_PDW30 | 8
1 | A_PDW31 | 8
1 | A_PDW32 | 8
1 | A_PDW33 | 8
1 | A_PDW36 | 8
1 | A_PDW37 | 8
1 | A_PDW38 | 8
1 | A_PDW39 | 8
1 | A_PDW40 | 8
1 | A_PDW41 | 8
1 | A_PDW43 | 8
1 | A_PDW44 | 8
1 | A_PDW45 | 8
1 | B_PDW28 | 8
1 | B_PDW30 | 8
1 | B_PDW31 | 8
1 | B_PDW32 | 8
1 | B_PDW33 | 8
1 | B_PDW36 | 8
1 | B_PDW37 | 8
1 | B_PDW38 | 8
1 | B_PDW39 | 8
1 | B_PDW40 | 8
1 | B_PDW41 | 8
1 | B_PDW43 | 8
1 | B_PDW44 | 8
1 | B_PDW45 | 8
1 | C_PDW28 | 8
1 | C_PDW30 | 8
1 | C_PDW31 | 8
1 | C_PDW32 | 8
1 | C_PDW33 | 8
1 | C_PDW36 | 8
1 | C_PDW37 | 8
1 | C_PDW38 | 8
1 | C_PDW39 | 8
1 | C_PDW40 | 8
1 | C_PDW41 | 8
1 | C_PDW43 | 8
1 | C_PDW44 | 8
1 | C_PDW45 | 8

## B
task | task | value
A_PDW-01A1A.1.0 | A_PDW-01A1A.11.0 | 1
A_PDW-01A1A.1.0 | A_PDW-01A1A.13.0 | 1
A_PDW-01A1A.1.0 | A_PDW-01A1A.14.0 | 1
A_PDW-01A1A.1.0 | A_PDW-01A1A.17.0 | 1
A_PDW-01A1A.11.0 | A_PDW-01A1A.13.0 | 1
A_PDW-01A1A.11.0 | A_PDW-01A1A.14.0 | 1
A_PDW-01A1A.11.0 | A_PDW-01A1A.17.0 | 1
A_PDW-01A1A.13.0 | A_PDW-01A1A.14.0 | 1
A_PDW-01A1A.13.0 | A_PDW-01A1A.17.0 | 1
A_PDW-01A1A.17.0 | A_PDW-01A1A.14.0 | 1
B_PDW-01A1A.1.0 | B_PDW-01A1A.13.0 | 1
B_PDW-01A1A.1.0 | B_PDW-01A1A.17.0 | 1
B_PDW-01A1A.13.0 | B_PDW-01A1A.17.0 | 1
C_PDW-01A1A.1.0 | C_PDW-01A1A.11.0 | 1
C_PDW-01A1A.1.0 | C_PDW-01A1A.13.0 | 1
C_PDW-01A1A.1.0 | C_PDW-01A1A.14.0 | 1
C_PDW-01A1A.1.0 | C_PDW-01A1A.17.0 | 1
C_PDW-01A1A.11.0 | C_PDW-01A1A.13.0 | 1
C_PDW-01A1A.11.0 | C_PDW-01A1A.14.0 | 1
C_PDW-01A1A.11.0 | C_PDW-01A1A.17.0 | 1
C_PDW-01A1A.13.0 | C_PDW-01A1A.14.0 | 1
C_PDW-01A1A.13.0 | C_PDW-01A1A.17.0 | 1
C_PDW-01A1A.17.0 | C_PDW-01A1A.14.0 | 1
A_PDW-01A1A.21.0 | A_PDW-01A1A.27.0 | 1
A_PDW-01A1A.21.0 | A_PDW-01A1A.30.0 | 1
A_PDW-01A1A.27.0 | A_PDW-01A1A.30.0 | 1
A_PDW2 | A_PDW3 | 1
A_PDW2 | A_PDW5 | 1
A_PDW3 | A_PDW5 | 1
B_PDW-01A1A.21.0 | B_PDW-01A1A.27.0 | 1
B_PDW-01A1A.21.0 | B_PDW-01A1A.30.0 | 1
B_PDW-01A1A.27.0 | B_PDW-01A1A.30.0 | 1
C_PDW-01A1A.21.0 | C_PDW-01A1A.27.0 | 1
C_PDW-01A1A.21.0 | C_PDW-01A1A.30.0 | 1
C_PDW-01A1A.21.0 | C_PDW2 | 1
C_PDW-01A1A.21.0 | C_PDW3 | 1
C_PDW-01A1A.27.0 | C_PDW-01A1A.30.0 | 1
C_PDW-01A1A.27.0 | C_PDW2 | 1
C_PDW-01A1A.27.0 | C_PDW3 | 1
C_PDW-01A1A.30.0 | C_PDW2 | 1
C_PDW-01A1A.30.0 | C_PDW3 | 1
C_PDW2 | C_PDW3 | 1
A_PDW4 | A_PDW12 | 1
A_PDW4 | A_PDW10 | 1
A_PDW4 | A_PDW18 | 1
A_PDW-01A1AIF.1.0 | A_PDW8 | 1
A_PDW-01A1AIF.1.0 | A_PDW9 | 1
A_PDW-01A1AIF.1.0 | A_PDW13 | 1
A_PDW-01A1AIF.1.0 | A_PDW15 | 1
A_PDW-01A1AIF.1.0 | A_PDW19 | 1
A_PDW8 | A_PDW15 | 1
A_PDW8 | A_PDW19 | 1
A_PDW9 | A_PDW8 | 1
A_PDW9 | A_PDW13 | 1
A_PDW9 | A_PDW15 | 1
A_PDW9 | A_PDW19 | 1
A_PDW13 | A_PDW15 | 1
A_PDW13 | A_PDW19 | 1
A_PDW12 | A_PDW10 | 1
A_PDW12 | A_PDW18 | 1
A_PDW10 | A_PDW18 | 1
A_PDW15 | A_PDW19 | 1
B_PDW-01A1AIF.1.0 | B_PDW9 | 1
B_PDW-01A1AIF.1.0 | B_PDW13 | 1
B_PDW-01A1AIF.1.0 | B_PDW12 | 1
B_PDW-01A1AIF.1.0 | B_PDW15 | 1
B_PDW-01A1AIF.1.0 | B_PDW18 | 1
B_PDW-01A1AIF.1.0 | B_PDW19 | 1
B_PDW8 | B_PDW12 | 1
B_PDW8 | B_PDW15 | 1
B_PDW8 | B_PDW18 | 1
B_PDW8 | B_PDW19 | 1
B_PDW9 | B_PDW13 | 1
B_PDW9 | B_PDW12 | 1
B_PDW9 | B_PDW15 | 1
B_PDW9 | B_PDW18 | 1
B_PDW9 | B_PDW19 | 1
B_PDW13 | B_PDW15 | 1
B_PDW13 | B_PDW18 | 1
B_PDW13 | B_PDW19 | 1
B_PDW12 | B_PDW15 | 1
B_PDW12 | B_PDW18 | 1
B_PDW12 | B_PDW19 | 1
B_PDW15 | B_PDW18 | 1
B_PDW15 | B_PDW19 | 1
B_PDW18 | B_PDW19 | 1
C_PDW4 | C_PDW15 | 1
C_PDW4 | C_PDW18 | 1
C_PDW4 | C_PDW19 | 1
C_PDW-01A1AIF.1.0 | C_PDW4 | 1
C_PDW-01A1AIF.1.0 | C_PDW8 | 1
C_PDW-01A1AIF.1.0 | C_PDW9 | 1
C_PDW-01A1AIF.1.0 | C_PDW13 | 1
C_PDW-01A1AIF.1.0 | C_PDW12 | 1
C_PDW-01A1AIF.1.0 | C_PDW15 | 1
C_PDW-01A1AIF.1.0 | C_PDW18 | 1
C_PDW-01A1AIF.1.0 | C_PDW19 | 1
C_PDW8 | C_PDW4 | 1
C_PDW8 | C_PDW13 | 1
C_PDW8 | C_PDW12 | 1
C_PDW8 | C_PDW15 | 1
C_PDW8 | C_PDW18 | 1
C_PDW8 | C_PDW19 | 1
C_PDW9 | C_PDW4 | 1
C_PDW9 | C_PDW8 | 1
C_PDW9 | C_PDW13 | 1
C_PDW9 | C_PDW12 | 1
C_PDW9 | C_PDW15 | 1
C_PDW9 | C_PDW18 | 1
C_PDW9 | C_PDW19 | 1
C_PDW13 | C_PDW15 | 1
C_PDW13 | C_PDW18 | 1
C_PDW13 | C_PDW19 | 1
C_PDW12 | C_PDW4 | 0.99999
C_PDW12 | C_PDW15 | 1
C_PDW12 | C_PDW18 | 1
C_PDW12 | C_PDW19 | 1
C_PDW15 | C_PDW18 | 1
C_PDW15 | C_PDW19 | 1
C_PDW18 | C_PDW19 | 1
A_PDW12.1 | A_PDW26 | 1
A_PDW16 | A_PDW20 | 1
A_PDW16 | A_PDW21 | 1
A_PDW16 | A_PDW24 | 1
A_PDW16 | A_PDW26 | 1
A_PDW16 | A_PDW29 | 1
A_PDW16 | A_PDW34 | 1
A_PDW16 | A_PDW42 | 1
A_PDW17 | A_PDW20 | 1
A_PDW17 | A_PDW21 | 1
A_PDW17 | A_PDW25 | 1
A_PDW17 | A_PDW26 | 1
A_PDW17 | A_PDW29 | 1
A_PDW17 | A_PDW34 | 1
A_PDW17 | A_PDW42 | 1
A_PDW20 | A_PDW29 | 1
A_PDW20 | A_PDW42 | 1
A_PDW21 | A_PDW20 | 1
A_PDW21 | A_PDW25 | 1
A_PDW21 | A_PDW26 | 1
A_PDW21 | A_PDW29 | 1
A_PDW21 | A_PDW34 | 1
A_PDW21 | A_PDW42 | 1
A_PDW24 | A_PDW20 | 1
A_PDW24 | A_PDW26 | 1
A_PDW24 | A_PDW29 | 1
A_PDW24 | A_PDW42 | 1
A_PDW25 | A_PDW26 | 1
A_PDW25 | A_PDW29 | 1
A_PDW25 | A_PDW34 | 1
A_PDW25 | A_PDW42 | 1
A_PDW26 | A_PDW29 | 1
A_PDW26 | A_PDW34 | 1
A_PDW29 | A_PDW34 | 1
A_PDW42 | A_PDW29 | 1
A_PDW42 | A_PDW34 | 1
B_PDW12.1 | B_PDW20 | 1
B_PDW12.1 | B_PDW21 | 1
B_PDW12.1 | B_PDW24 | 1
B_PDW12.1 | B_PDW25 | 1
B_PDW12.1 | B_PDW26 | 1
B_PDW12.1 | B_PDW29 | 1
B_PDW12.1 | B_PDW34 | 1
B_PDW12.1 | B_PDW42 | 1
B_PDW16 | B_PDW12.1 | 1
B_PDW16 | B_PDW17 | 1
B_PDW16 | B_PDW20 | 1
B_PDW16 | B_PDW21 | 1
B_PDW16 | B_PDW24 | 1
B_PDW16 | B_PDW25 | 1
B_PDW16 | B_PDW26 | 1
B_PDW16 | B_PDW29 | 1
B_PDW16 | B_PDW34 | 1
B_PDW16 | B_PDW42 | 1
B_PDW17 | B_PDW21 | 1
B_PDW17 | B_PDW24 | 1
B_PDW17 | B_PDW26 | 1
B_PDW17 | B_PDW29 | 1
B_PDW17 | B_PDW34 | 1
B_PDW20 | B_PDW25 | 1
B_PDW20 | B_PDW42 | 1
B_PDW21 | B_PDW24 | 1
B_PDW21 | B_PDW25 | 1
B_PDW21 | B_PDW26 | 1
B_PDW21 | B_PDW29 | 1
B_PDW21 | B_PDW34 | 1
B_PDW24 | B_PDW26 | 1
B_PDW24 | B_PDW29 | 1
B_PDW24 | B_PDW34 | 1
B_PDW25 | B_PDW26 | 1
B_PDW25 | B_PDW29 | 1
B_PDW25 | B_PDW34 | 1
B_PDW25 | B_PDW42 | 1
B_PDW26 | B_PDW29 | 1
B_PDW26 | B_PDW34 | 1
B_PDW29 | B_PDW34 | 1
B_PDW42 | B_PDW34 | 1
C_PDW12.1 | C_PDW20 | 1
C_PDW12.1 | C_PDW21 | 1
C_PDW12.1 | C_PDW25 | 1
C_PDW12.1 | C_PDW26 | 1
C_PDW12.1 | C_PDW29 | 1
C_PDW12.1 | C_PDW34 | 1
C_PDW12.1 | C_PDW42 | 1
C_PDW16 | C_PDW12.1 | 1
C_PDW16 | C_PDW17 | 1
C_PDW16 | C_PDW20 | 1
C_PDW16 | C_PDW21 | 1
C_PDW16 | C_PDW24 | 1
C_PDW16 | C_PDW25 | 1
C_PDW16 | C_PDW26 | 1
C_PDW16 | C_PDW29 | 1
C_PDW16 | C_PDW34 | 1
C_PDW16 | C_PDW42 | 1
C_PDW17 | C_PDW21 | 1
C_PDW17 | C_PDW24 | 1
C_PDW17 | C_PDW26 | 1
C_PDW17 | C_PDW34 | 1
C_PDW20 | C_PDW29 | 1
C_PDW20 | C_PDW42 | 1
C_PDW21 | C_PDW20 | 1
C_PDW21 | C_PDW25 | 1
C_PDW21 | C_PDW29 | 1
C_PDW21 | C_PDW34 | 1
C_PDW21 | C_PDW42 | 1
C_PDW24 | C_PDW26 | 1
C_PDW24 | C_PDW34 | 1
C_PDW25 | C_PDW20 | 1
C_PDW25 | C_PDW26 | 1
C_PDW25 | C_PDW29 | 1
C_PDW25 | C_PDW34 | 1
C_PDW25 | C_PDW42 | 1
C_PDW26 | C_PDW29 | 1
C_PDW26 | C_PDW34 | 1
C_PDW29 | C_PDW34 | 1
C_PDW42 | C_PDW29 | 1
C_PDW42 | C_PDW34 | 1
A_PDW28 | A_PDW30 | 1
A_PDW28 | A_PDW31 | 1
A_PDW28 | A_PDW32 | 1
A_PDW28 | A_PDW33 | 1
A_PDW28 | A_PDW36 | 1
A_PDW28 | A_PDW37 | 1
A_PDW28 | A_PDW38 | 1
A_PDW28 | A_PDW39 | 1
A_PDW28 | A_PDW40 | 1
A_PDW28 | A_PDW41 | 1
A_PDW28 | A_PDW43 | 1
A_PDW28 | A_PDW44 | 1
A_PDW28 | A_PDW45 | 1
A_PDW30 | A_PDW31 | 1
A_PDW30 | A_PDW32 | 1
A_PDW30 | A_PDW33 | 1
A_PDW30 | A_PDW36 | 1
A_PDW30 | A_PDW37 | 1
A_PDW30 | A_PDW38 | 1
A_PDW30 | A_PDW39 | 1
A_PDW30 | A_PDW40 | 1
A_PDW30 | A_PDW41 | 1
A_PDW30 | A_PDW43 | 1
A_PDW30 | A_PDW44 | 1
A_PDW30 | A_PDW45 | 1
A_PDW31 | A_PDW32 | 1
A_PDW31 | A_PDW33 | 1
A_PDW31 | A_PDW36 | 1
A_PDW31 | A_PDW37 | 1
A_PDW31 | A_PDW38 | 1
A_PDW31 | A_PDW39 | 1
A_PDW31 | A_PDW40 | 1
A_PDW31 | A_PDW41 | 1
A_PDW31 | A_PDW43 | 1
A_PDW31 | A_PDW44 | 1
A_PDW31 | A_PDW45 | 1
A_PDW32 | A_PDW41 | 1
A_PDW32 | A_PDW43 | 1
A_PDW32 | A_PDW44 | 1
A_PDW32 | A_PDW45 | 1
A_PDW33 | A_PDW32 | 1
A_PDW33 | A_PDW41 | 1
A_PDW33 | A_PDW43 | 1
A_PDW33 | A_PDW44 | 1
A_PDW33 | A_PDW45 | 1
A_PDW36 | A_PDW32 | 1
A_PDW36 | A_PDW33 | 1
A_PDW36 | A_PDW37 | 1
A_PDW36 | A_PDW38 | 1
A_PDW36 | A_PDW39 | 1
A_PDW36 | A_PDW40 | 1
A_PDW36 | A_PDW41 | 1
A_PDW36 | A_PDW43 | 1
A_PDW36 | A_PDW44 | 1
A_PDW36 | A_PDW45 | 1
A_PDW37 | A_PDW32 | 1
A_PDW37 | A_PDW33 | 1
A_PDW37 | A_PDW38 | 1
A_PDW37 | A_PDW39 | 1
A_PDW37 | A_PDW40 | 1
A_PDW37 | A_PDW41 | 1
A_PDW37 | A_PDW43 | 1
A_PDW37 | A_PDW44 | 1
A_PDW37 | A_PDW45 | 1
A_PDW38 | A_PDW32 | 1
A_PDW38 | A_PDW33 | 1
A_PDW38 | A_PDW41 | 1
A_PDW38 | A_PDW43 | 1
A_PDW38 | A_PDW44 | 1
A_PDW38 | A_PDW45 | 1
A_PDW39 | A_PDW32 | 1
A_PDW39 | A_PDW33 | 1
A_PDW39 | A_PDW38 | 1
A_PDW39 | A_PDW40 | 1
A_PDW39 | A_PDW41 | 1
A_PDW39 | A_PDW43 | 1
A_PDW39 | A_PDW44 | 1
A_PDW39 | A_PDW45 | 1
A_PDW40 | A_PDW32 | 1
A_PDW40 | A_PDW33 | 1
A_PDW40 | A_PDW38 | 1
A_PDW40 | A_PDW41 | 1
A_PDW40 | A_PDW43 | 1
A_PDW40 | A_PDW44 | 1
A_PDW40 | A_PDW45 | 1
A_PDW41 | A_PDW43 | 1
A_PDW41 | A_PDW44 | 1
A_PDW41 | A_PDW45 | 1
A_PDW43 | A_PDW44 | 1
A_PDW43 | A_PDW45 | 1
A_PDW44 | A_PDW45 | 1
B_PDW28 | B_PDW30 | 1
B_PDW28 | B_PDW31 | 1
B_PDW28 | B_PDW32 | 1
B_PDW28 | B_PDW33 | 1
B_PDW28 | B_PDW36 | 1
B_PDW28 | B_PDW37 | 1
B_PDW28 | B_PDW38 | 1
B_PDW28 | B_PDW39 | 1
B_PDW28 | B_PDW40 | 1
B_PDW28 | B_PDW41 | 1
B_PDW28 | B_PDW43 | 1
B_PDW28 | B_PDW44 | 1
B_PDW28 | B_PDW45 | 1
B_PDW30 | B_PDW31 | 1
B_PDW30 | B_PDW32 | 1
B_PDW30 | B_PDW33 | 1
B_PDW30 | B_PDW36 | 1
B_PDW30 | B_PDW37 | 1
B_PDW30 | B_PDW38 | 1
B_PDW30 | B_PDW39 | 1
B_PDW30 | B_PDW40 | 1
B_PDW30 | B_PDW41 | 1
B_PDW30 | B_PDW43 | 1
B_PDW30 | B_PDW44 | 1
B_PDW30 | B_PDW45 | 1
B_PDW31 | B_PDW32 | 1
B_PDW31 | B_PDW33 | 1
B_PDW31 | B_PDW36 | 1
B_PDW31 | B_PDW37 | 1
B_PDW31 | B_PDW38 | 1
B_PDW31 | B_PDW39 | 1
B_PDW31 | B_PDW40 | 1
B_PDW31 | B_PDW41 | 1
B_PDW31 | B_PDW43 | 1
B_PDW31 | B_PDW44 | 1
B_PDW31 | B_PDW45 | 1
B_PDW32 | B_PDW41 | 1
B_PDW32 | B_PDW43 | 1
B_PDW32 | B_PDW44 | 1
B_PDW32 | B_PDW45 | 1
B_PDW33 | B_PDW32 | 1
B_PDW33 | B_PDW41 | 1
B_PDW33 | B_PDW43 | 1
B_PDW33 | B_PDW44 | 1
B_PDW33 | B_PDW45 | 1
B_PDW36 | B_PDW32 | 1
B_PDW36 | B_PDW33 | 1
B_PDW36 | B_PDW37 | 1
B_PDW36 | B_PDW38 | 1
B_PDW36 | B_PDW39 | 1
B_PDW36 | B_PDW40 | 1
B_PDW36 | B_PDW41 | 1
B_PDW36 | B_PDW43 | 1
B_PDW36 | B_PDW44 | 1
B_PDW36 | B_PDW45 | 1
B_PDW37 | B_PDW32 | 1
B_PDW37 | B_PDW33 | 1
B_PDW37 | B_PDW38 | 1
B_PDW37 | B_PDW39 | 1
B_PDW37 | B_PDW40 | 1
B_PDW37 | B_PDW41 | 1
B_PDW37 | B_PDW43 | 1
B_PDW37 | B_PDW44 | 1
B_PDW37 | B_PDW45 | 1
B_PDW38 | B_PDW32 | 1
B_PDW38 | B_PDW33 | 1
B_PDW38 | B_PDW41 | 1
B_PDW38 | B_PDW43 | 1
B_PDW38 | B_PDW44 | 1
B_PDW38 | B_PDW45 | 1
B_PDW39 | B_PDW32 | 1
B_PDW39 | B_PDW33 | 1
B_PDW39 | B_PDW38 | 1
B_PDW39 | B_PDW40 | 1
B_PDW39 | B_PDW41 | 1
B_PDW39 | B_PDW43 | 1
B_PDW39 | B_PDW44 | 1
B_PDW39 | B_PDW45 | 1
B_PDW40 | B_PDW32 | 1
B_PDW40 | B_PDW33 | 1
B_PDW40 | B_PDW38 | 1
B_PDW40 | B_PDW41 | 1
B_PDW40 | B_PDW43 | 1
B_PDW40 | B_PDW44 | 1
B_PDW40 | B_PDW45 | 1
B_PDW41 | B_PDW43 | 1
B_PDW41 | B_PDW44 | 1
B_PDW41 | B_PDW45 | 1
B_PDW43 | B_PDW44 | 1
B_PDW43 | B_PDW45 | 1
B_PDW44 | B_PDW45 | 1
C_PDW28 | C_PDW30 | 1
C_PDW28 | C_PDW31 | 1
C_PDW28 | C_PDW32 | 1
C_PDW28 | C_PDW33 | 1
C_PDW28 | C_PDW36 | 1
C_PDW28 | C_PDW37 | 1
C_PDW28 | C_PDW38 | 1
C_PDW28 | C_PDW39 | 1
C_PDW28 | C_PDW40 | 1
C_PDW28 | C_PDW41 | 1
C_PDW28 | C_PDW43 | 1
C_PDW28 | C_PDW44 | 1
C_PDW28 | C_PDW45 | 1
C_PDW30 | C_PDW31 | 1
C_PDW30 | C_PDW32 | 1
C_PDW30 | C_PDW33 | 1
C_PDW30 | C_PDW36 | 1
C_PDW30 | C_PDW37 | 1
C_PDW30 | C_PDW38 | 1
C_PDW30 | C_PDW39 | 1
C_PDW30 | C_PDW40 | 1
C_PDW30 | C_PDW41 | 1
C_PDW30 | C_PDW43 | 1
C_PDW30 | C_PDW44 | 1
C_PDW30 | C_PDW45 | 1
C_PDW31 | C_PDW32 | 1
C_PDW31 | C_PDW33 | 1
C_PDW31 | C_PDW36 | 1
C_PDW31 | C_PDW37 | 1
C_PDW31 | C_PDW38 | 1
C_PDW31 | C_PDW39 | 1
C_PDW31 | C_PDW40 | 1
C_PDW31 | C_PDW41 | 1
C_PDW31 | C_PDW43 | 1
C_PDW31 | C_PDW44 | 1
C_PDW31 | C_PDW45 | 1
C_PDW32 | C_PDW41 | 1
C_PDW32 | C_PDW43 | 1
C_PDW32 | C_PDW44 | 1
C_PDW32 | C_PDW45 | 1
C_PDW33 | C_PDW32 | 1
C_PDW33 | C_PDW41 | 1
C_PDW33 | C_PDW43 | 1
C_PDW33 | C_PDW44 | 1
C_PDW33 | C_PDW45 | 1
C_PDW36 | C_PDW32 | 1
C_PDW36 | C_PDW33 | 1
C_PDW36 | C_PDW37 | 1
C_PDW36 | C_PDW38 | 1
C_PDW36 | C_PDW39 | 1
C_PDW36 | C_PDW40 | 1
C_PDW36 | C_PDW41 | 1
C_PDW36 | C_PDW43 | 1
C_PDW36 | C_PDW44 | 1
C_PDW36 | C_PDW45 | 1
C_PDW37 | C_PDW32 | 1
C_PDW37 | C_PDW33 | 1
C_PDW37 | C_PDW38 | 1
C_PDW37 | C_PDW39 | 1
C_PDW37 | C_PDW40 | 1
C_PDW37 | C_PDW41 | 1
C_PDW37 | C_PDW43 | 1
C_PDW37 | C_PDW44 | 1
C_PDW37 | C_PDW45 | 1
C_PDW38 | C_PDW32 | 1
C_PDW38 | C_PDW33 | 1
C_PDW38 | C_PDW41 | 1
C_PDW38 | C_PDW43 | 1
C_PDW38 | C_PDW44 | 1
C_PDW38 | C_PDW45 | 1
C_PDW39 | C_PDW32 | 1
C_PDW39 | C_PDW33 | 1
C_PDW39 | C_PDW38 | 1
C_PDW39 | C_PDW40 | 1
C_PDW39 | C_PDW41 | 1
C_PDW39 | C_PDW43 | 1
C_PDW39 | C_PDW44 | 1
C_PDW39 | C_PDW45 | 1
C_PDW40 | C_PDW32 | 1
C_PDW40 | C_PDW33 | 1
C_PDW40 | C_PDW38 | 1
C_PDW40 | C_PDW41 | 1
C_PDW40 | C_PDW43 | 1
C_PDW40 | C_PDW44 | 1
C_PDW40 | C_PDW45 | 1
C_PDW41 | C_PDW43 | 1
C_PDW41 | C_PDW44 | 1
C_PDW41 | C_PDW45 | 1
C_PDW43 | C_PDW44 | 1
C_PDW43 | C_PDW45 | 1
C_PDW44 | C_PDW45 | 1

## N
stage | number of station | value
2 | 1 | 1
3 | 2 | 1
4 | 2 | 1
6 | 2 | 1
5 | 2 | 1
8 | 3 | 1