## X
task | stage | resource option | resource type req
A_PDW-01A1A.1.0 | 1 | 1 | ['worker', 'gantry']
A_PDW-01A1A.11.0 | 15 | 0 | ['worker']
A_PDW-01A1A.13.0 | 21 | 0 | ['worker']
A_PDW-01A1A.14.0 | 21 | 0 | ['worker']
A_PDW-01A1A.17.0 | 43 | 0 | ['worker']
A_PDW-01A1A.21.0 | 5 | 0 | ['worker']
A_PDW-01A1A.27.0 | 5 | 0 | ['worker']
A_PDW-01A1A.30.0 | 5 | 0 | ['worker']
A_PDW2 | 7 | 0 | ['dryer']
A_PDW3 | 7 | 0 | ['dryer']
A_PDW4 | 15 | 0 | ['dryer']
A_PDW5 | 21 | 2 | ['dryer']
A_PDW-01A1AIF.1.0 | 15 | 0 | ['worker']
A_PDW8 | 15 | 0 | ['worker']
A_PDW9 | 15 | 0 | ['worker']
A_PDW13 | 15 | 0 | ['worker']
A_PDW12 | 29 | 0 | ['dryer']
A_PDW12.1 | 27 | 0 | ['dryer']
A_PDW10 | 19 | 2 | ['dryer']
A_PDW15 | 31 | 0 | ['worker']
A_PDW16 | 31 | 0 | ['worker']
A_PDW17 | 21 | 0 | ['worker']
A_PDW18 | 27 | 0 | ['dryer']
A_PDW19 | 27 | 0 | ['worker']
A_PDW20 | 48 | 0 | ['worker']
A_PDW21 | 21 | 0 | ['worker']
A_PDW22 | 27 | 1 | ['dryer', 'worker']
A_PDW24 | 48 | 0 | ['worker']
A_PDW25 | 29 | 0 | ['worker']
A_PDW26 | 29 | 1 | ['dryer', 'worker']
A_PDW28 | 31 | 0 | ['worker']
A_PDW29 | 48 | 0 | ['worker']
A_PDW30 | 43 | 0 | ['worker']
A_PDW31 | 43 | 0 | ['worker']
A_PDW32 | 31 | 0 | ['worker']
A_PDW33 | 31 | 0 | ['worker']
A_PDW34 | 29 | 0 | ['worker']
A_PDW36 | 31 | 0 | ['worker']
A_PDW37 | 29 | 0 | ['worker']
A_PDW38 | 43 | 0 | ['worker']
A_PDW39 | 29 | 0 | ['worker']
A_PDW40 | 48 | 0 | ['worker']
A_PDW41 | 43 | 1 | ['worker']
A_PDW42 | 29 | 0 | ['worker']
A_PDW43 | 15 | 0 | ['worker']
A_PDW44 | 27 | 0 | ['worker']
A_PDW45 | 27 | 0 | ['worker']
B_PDW-01A1A.1.0 | 1 | 1 | ['worker', 'gantry']
B_PDW-01A1A.13.0 | 29 | 0 | ['worker']
B_PDW-01A1A.17.0 | 48 | 0 | ['worker']
B_PDW-01A1A.21.0 | 15 | 0 | ['worker']
B_PDW-01A1A.27.0 | 15 | 0 | ['worker']
B_PDW-01A1A.30.0 | 5 | 0 | ['worker']
B_PDW5 | 19 | 0 | ['dryer']
B_PDW-01A1AIF.1.0 | 21 | 0 | ['worker']
B_PDW8 | 5 | 0 | ['worker']
B_PDW9 | 5 | 0 | ['worker']
B_PDW13 | 27 | 0 | ['worker']
B_PDW12 | 27 | 0 | ['dryer']
B_PDW12.1 | 29 | 0 | ['worker']
B_PDW10 | 7 | 0 | ['dryer']
B_PDW15 | 31 | 0 | ['worker']
B_PDW16 | 43 | 0 | ['worker']
B_PDW17 | 29 | 0 | ['worker']
B_PDW18 | 15 | 0 | ['worker']
B_PDW19 | 15 | 0 | ['worker']
B_PDW20 | 27 | 0 | ['worker']
B_PDW21 | 43 | 0 | ['worker']
B_PDW22 | 15 | 1 | ['dryer', 'worker']
B_PDW24 | 31 | 0 | ['worker']
B_PDW25 | 21 | 0 | ['worker']
B_PDW26 | 29 | 1 | ['dryer', 'worker']
B_PDW28 | 29 | 0 | ['worker']
B_PDW29 | 48 | 0 | ['worker']
B_PDW30 | 21 | 0 | ['worker']
B_PDW31 | 27 | 0 | ['worker']
B_PDW32 | 31 | 0 | ['worker']
B_PDW33 | 29 | 0 | ['worker']
B_PDW34 | 43 | 0 | ['worker']
B_PDW36 | 27 | 0 | ['worker']
B_PDW37 | 31 | 0 | ['worker']
B_PDW38 | 43 | 0 | ['worker']
B_PDW39 | 48 | 0 | ['worker']
B_PDW40 | 31 | 0 | ['worker']
B_PDW41 | 43 | 1 | ['worker']
B_PDW42 | 27 | 0 | ['worker']
B_PDW43 | 31 | 0 | ['worker']
B_PDW44 | 43 | 0 | ['worker']
B_PDW45 | 43 | 0 | ['worker']
C_PDW-01A1A.1.0 | 1 | 1 | ['worker', 'gantry']
C_PDW-01A1A.11.0 | 15 | 0 | ['worker']
C_PDW-01A1A.13.0 | 15 | 0 | ['worker']
C_PDW-01A1A.14.0 | 29 | 0 | ['worker']
C_PDW-01A1A.17.0 | 21 | 0 | ['worker']
C_PDW-01A1A.21.0 | 5 | 0 | ['worker']
C_PDW-01A1A.27.0 | 5 | 0 | ['worker']
C_PDW-01A1A.30.0 | 5 | 0 | ['worker']
C_PDW2 | 15 | 0 | ['worker']
C_PDW3 | 5 | 0 | ['worker']
C_PDW4 | 27 | 0 | ['worker']
C_PDW5 | 19 | 2 | ['dryer']
C_PDW-01A1AIF.1.0 | 15 | 0 | ['worker']
C_PDW8 | 15 | 0 | ['worker']
C_PDW9 | 15 | 0 | ['dryer']
C_PDW13 | 21 | 0 | ['worker']
C_PDW12 | 31 | 0 | ['worker']
C_PDW12.1 | 48 | 0 | ['worker']
C_PDW10 | 21 | 2 | ['dryer']
C_PDW15 | 29 | 0 | ['worker']
C_PDW16 | 29 | 0 | ['worker']
C_PDW17 | 43 | 0 | ['worker']
C_PDW18 | 31 | 0 | ['worker']
C_PDW18.1 | 43 | 0 | ['worker']
C_PDW18.2 | 27 | 0 | ['worker']
C_PDW19 | 27 | 0 | ['worker']
C_PDW20 | 43 | 0 | ['worker']
C_PDW21 | 48 | 0 | ['worker']
C_PDW22 | 27 | 1 | ['dryer', 'worker']
C_PDW24 | 31 | 0 | ['worker']
C_PDW25 | 31 | 0 | ['worker']
C_PDW26 | 29 | 1 | ['dryer', 'worker']
C_PDW28 | 31 | 0 | ['worker']
C_PDW29 | 31 | 0 | ['worker']
C_PDW30 | 29 | 0 | ['worker']
C_PDW31 | 43 | 0 | ['worker']
C_PDW32 | 48 | 0 | ['worker']
C_PDW33 | 31 | 0 | ['worker']
C_PDW34 | 31 | 0 | ['worker']
C_PDW36 | 29 | 0 | ['worker']
C_PDW37 | 29 | 0 | ['worker']
C_PDW38 | 29 | 0 | ['worker']
C_PDW39 | 48 | 0 | ['worker']
C_PDW40 | 43 | 0 | ['worker']
C_PDW41 | 43 | 1 | ['worker']
C_PDW42 | 15 | 0 | ['worker']
C_PDW43 | 21 | 0 | ['worker']
C_PDW44 | 29 | 0 | ['worker']
C_PDW45 | 15 | 0 | ['worker']

## Y
worker | stage | number of station | team cost | stage team cost
1 | 1 | 1 | 55 | 55
1 | 15 | 1 | 55 | 55
1 | 43 | 1 | 55 | 55
1 | 48 | 1 | 55 | 55
2 | 27 | 1 | 55 | 55
3 | 1 | 1 | 55 | 55
3 | 5 | 1 | 55 | 55
3 | 29 | 1 | 55 | 55
4 | 7 | 1 | 50 | 50
4 | 19 | 1 | 50 | 50
4 | 21 | 1 | 50 | 50
5 | 15 | 1 | 50 | 50
5 | 19 | 1 | 50 | 50
5 | 21 | 1 | 50 | 50
5 | 27 | 1 | 50 | 50
5 | 29 | 1 | 50 | 50
6 | 19 | 1 | 50 | 50
6 | 21 | 1 | 50 | 50
7 | 1 | 1 | 60 | 60
9 | 19 | 1 | 50 | 50
9 | 21 | 1 | 50 | 50
10 | 1 | 1 | 55 | 55
10 | 29 | 1 | 55 | 55
10 | 31 | 1 | 55 | 55
10 | 43 | 1 | 55 | 55
11 | 1 | 1 | 55 | 55
11 | 15 | 1 | 55 | 55
11 | 21 | 1 | 55 | 55
11 | 27 | 1 | 55 | 55
11 | 31 | 1 | 55 | 55

## T
task | task name | start time
A_PDW-01A1A.1.0 | 1. Frame | 0
A_PDW-01A1A.11.0 | 11. Install bath tub / shower pan | 0
A_PDW-01A1A.13.0 | 13. Install ceiling CLG-01A | 2
A_PDW-01A1A.14.0 | 14. Connect Fire Sprinkler Ceiling Assemblies | 12
A_PDW-01A1A.17.0 | 17. Install electrical panel | 10
A_PDW-01A1A.21.0 | 21. Conduct Plumbing & sprinkler Pressure Test | 0
A_PDW-01A1A.27.0 | 27. Install Lid LID-01A | 5
A_PDW-01A1A.30.0 | 30. Move Pod to Finish Station | 18
A_PDW2 | Bathroom insulation, drywall and tape/bed | 0
A_PDW3 | kitchen insulation, drywall and tape/bed | 12
A_PDW4 | exterior insulation, drywall and tape/bed | 0
A_PDW5 | dry bathroom | 0
A_PDW-01A1AIF.1.0 | 1. Set-up for finishing stage | 0
A_PDW8 | skim bathroom | 25
A_PDW9 | skim kitchen | 6
A_PDW13 | skim outside | 23
A_PDW12 | install doors and casing Bathroom | 0
A_PDW12.1 | install doors and casing Kitchen | 10
A_PDW10 | skim dry bathroom | 0
A_PDW15 | sand bathroom | 14
A_PDW16 | sand kitchen | 10
A_PDW17 | sand outside | 34
A_PDW18 | Install Tub/Shower Surround | 0
A_PDW19 | Prime paint bathroom | 10
A_PDW20 | Prime paint kitchen | 19
A_PDW21 | Apply wall covering | 0
A_PDW22 | Prime dry bathroom | 32
A_PDW24 | Paint bathroom | 41
A_PDW25 | Paint kitchen | 29
A_PDW26 | Paint dry | 30
A_PDW28 | cove base bathroom | 0
A_PDW29 | cove base kitchen | 5
A_PDW30 | bathroom plumbing | 25
A_PDW31 | bathroom trim | 0
A_PDW32 | Install Interior Cabinets & Countertops | 36
A_PDW33 | Kitchen plumbing and appliances | 27
A_PDW34 | Install Electrical Fixtures & trim | 14
A_PDW36 | 25. Connect POD to POD | 0
A_PDW37 | 26. Install interior pod to pod connection finishes | 0
A_PDW38 | 27. Connect pod to pod electrical | 0
A_PDW39 | 28. Install Batt Insulation in lids and Inspection | 0
A_PDW40 | 30. Install Sheathing on top of lids | 0
A_PDW41 | Perform test | 50
A_PDW42 | Batt Insulation in walls | 1
A_PDW43 | 40. Execute final interior punch - close NCRs | 5
A_PDW44 | 42. Final clean-up entire module | 0
A_PDW45 | Wrap, document and move to ship | 0
B_PDW-01A1A.1.0 | 1. Frame | 0
B_PDW-01A1A.13.0 | 13. Install ceiling CLG-01A | 0
B_PDW-01A1A.17.0 | 17. Install electrical panel | 27.0784
B_PDW-01A1A.21.0 | 21. Conduct Plumbing & sprinkler Pressure Test | 0
B_PDW-01A1A.27.0 | 27. Install Lid LID-01A | 8.146
B_PDW-01A1A.30.0 | 30. Move Pod to Finish Station | 0
B_PDW5 | dry bathroom | 0
B_PDW-01A1AIF.1.0 | 1. Set-up for finishing stage | 0
B_PDW8 | skim bathroom | 57
B_PDW9 | skim kitchen | 40
B_PDW13 | skim outside | 22
B_PDW12 | install doors and casing Bathroom | 0
B_PDW12.1 | install doors and casing Kitchen | 14
B_PDW10 | skim dry bathroom | 0
B_PDW15 | sand bathroom | 1
B_PDW16 | sand kitchen | 26
B_PDW17 | sand outside | 34
B_PDW18 | Install Tub/Shower Surround | 0
B_PDW19 | Prime paint bathroom | 4.0801
B_PDW20 | Prime paint kitchen | 0
B_PDW21 | Apply wall covering | 0
B_PDW22 | Prime dry bathroom | 26.0801
B_PDW24 | Paint bathroom | 25
B_PDW25 | Paint kitchen | 30
B_PDW26 | Paint dry | 35
B_PDW28 | cove base bathroom | 0
B_PDW29 | cove base kitchen | 13.0784
B_PDW30 | bathroom plumbing | 5
B_PDW31 | bathroom trim | 10
B_PDW32 | Install Interior Cabinets & Countertops | 23
B_PDW33 | Kitchen plumbing and appliances | 10
B_PDW34 | Install Electrical Fixtures & trim | 10
B_PDW36 | 25. Connect POD to POD | 0
B_PDW37 | 26. Install interior pod to pod connection finishes | 0
B_PDW38 | 27. Connect pod to pod electrical | 0
B_PDW39 | 28. Install Batt Insulation in lids and Inspection | 0
B_PDW40 | 30. Install Sheathing on top of lids | 0
B_PDW41 | Perform test | 43
B_PDW42 | Batt Insulation in walls | 35
B_PDW43 | 40. Execute final interior punch - close NCRs | 5
B_PDW44 | 42. Final clean-up entire module | 2
B_PDW45 | Wrap, document and move to ship | 12
C_PDW-01A1A.1.0 | 1. Frame | 0
C_PDW-01A1A.11.0 | 11. Install bath tub / shower pan | 0
C_PDW-01A1A.13.0 | 13. Install ceiling CLG-01A | 6
C_PDW-01A1A.14.0 | 14. Connect Fire Sprinkler Ceiling Assemblies | 11
C_PDW-01A1A.17.0 | 17. Install electrical panel | 42
C_PDW-01A1A.21.0 | 21. Conduct Plumbing & sprinkler Pressure Test | 0
C_PDW-01A1A.27.0 | 27. Install Lid LID-01A | 5
C_PDW-01A1A.30.0 | 30. Move Pod to Finish Station | 18
C_PDW2 | Bathroom insulation, drywall and tape/bed | 0
C_PDW3 | kitchen insulation, drywall and tape/bed | 58
C_PDW4 | exterior insulation, drywall and tape/bed | 10
C_PDW5 | dry bathroom | 0
C_PDW-01A1AIF.1.0 | 1. Set-up for finishing stage | 12
C_PDW8 | skim bathroom | 17
C_PDW9 | skim kitchen | 17
C_PDW13 | skim outside | 20
C_PDW12 | install doors and casing Bathroom | 14
C_PDW12.1 | install doors and casing Kitchen | 16
C_PDW10 | skim dry bathroom | 0
C_PDW15 | sand bathroom | 33
C_PDW16 | sand kitchen | 20
C_PDW17 | sand outside | 0
C_PDW18 | Install Tub/Shower Surround | 0
C_PDW18.1 | Install Tub/Shower Surround | 5
C_PDW18.2 | Install Tub/Shower Surround | 0
C_PDW19 | Prime paint bathroom | 0
C_PDW20 | Prime paint kitchen | 20
C_PDW21 | Apply wall covering | 0
C_PDW22 | Prime dry bathroom | 29
C_PDW24 | Paint bathroom | 40
C_PDW25 | Paint kitchen | 56
C_PDW26 | Paint dry | 37
C_PDW28 | cove base bathroom | 0
C_PDW29 | cove base kitchen | 10
C_PDW30 | bathroom plumbing | 55
C_PDW31 | bathroom trim | 19
C_PDW32 | Install Interior Cabinets & Countertops | 36
C_PDW33 | Kitchen plumbing and appliances | 31
C_PDW34 | Install Electrical Fixtures & trim | 24
C_PDW36 | 25. Connect POD to POD | 1
C_PDW37 | 26. Install interior pod to pod connection finishes | 0
C_PDW38 | 27. Connect pod to pod electrical | 0
C_PDW39 | 28. Install Batt Insulation in lids and Inspection | 2
C_PDW40 | 30. Install Sheathing on top of lids | 0
C_PDW41 | Perform test | 44
C_PDW42 | Batt Insulation in walls | 17
C_PDW43 | 40. Execute final interior punch - close NCRs | 0
C_PDW44 | 42. Final clean-up entire module | 10
C_PDW45 | Wrap, document and move to ship | 45

## A
worker | task | stage
1 | A_PDW-01A1A.1.0 | 1
1 | A_PDW-01A1A.17.0 | 43
1 | A_PDW-01A1AIF.1.0 | 15
1 | A_PDW8 | 15
1 | A_PDW20 | 48
1 | A_PDW24 | 48
1 | A_PDW29 | 48
1 | A_PDW38 | 43
1 | A_PDW40 | 48
1 | A_PDW41 | 43
1 | A_PDW43 | 15
1 | B_PDW-01A1A.1.0 | 1
1 | B_PDW-01A1A.17.0 | 48
1 | B_PDW-01A1A.27.0 | 15
1 | B_PDW16 | 43
1 | B_PDW18 | 15
1 | B_PDW22 | 15
1 | B_PDW29 | 48
1 | B_PDW34 | 43
1 | B_PDW38 | 43
1 | B_PDW39 | 48
1 | B_PDW41 | 43
1 | C_PDW-01A1A.1.0 | 1
1 | C_PDW-01A1A.11.0 | 15
1 | C_PDW-01A1A.13.0 | 15
1 | C_PDW12.1 | 48
1 | C_PDW18.1 | 43
1 | C_PDW21 | 48
1 | C_PDW31 | 43
1 | C_PDW32 | 48
1 | C_PDW39 | 48
1 | C_PDW40 | 43
1 | C_PDW41 | 43
1 | C_PDW42 | 15
1 | C_PDW45 | 15
2 | A_PDW19 | 27
2 | A_PDW22 | 27
2 | A_PDW44 | 27
2 | B_PDW31 | 27
2 | B_PDW36 | 27
2 | B_PDW42 | 27
2 | C_PDW19 | 27
2 | C_PDW22 | 27
3 | A_PDW-01A1A.1.0 | 1
3 | A_PDW-01A1A.21.0 | 5
3 | A_PDW-01A1A.27.0 | 5
3 | A_PDW-01A1A.30.0 | 5
3 | A_PDW26 | 29
3 | A_PDW34 | 29
3 | A_PDW39 | 29
3 | B_PDW-01A1A.1.0 | 1
3 | B_PDW-01A1A.30.0 | 5
3 | B_PDW8 | 5
3 | B_PDW9 | 5
3 | B_PDW12.1 | 29
3 | B_PDW17 | 29
3 | B_PDW28 | 29
3 | C_PDW-01A1A.1.0 | 1
3 | C_PDW-01A1A.14.0 | 29
3 | C_PDW-01A1A.21.0 | 5
3 | C_PDW-01A1A.27.0 | 5
3 | C_PDW-01A1A.30.0 | 5
3 | C_PDW3 | 5
3 | C_PDW15 | 29
3 | C_PDW30 | 29
3 | C_PDW36 | 29
3 | C_PDW37 | 29
4 | A_PDW2 | 7
4 | A_PDW3 | 7
4 | A_PDW5 | 21
4 | A_PDW10 | 19
4 | B_PDW5 | 19
4 | B_PDW10 | 7
4 | C_PDW5 | 19
4 | C_PDW10 | 21
5 | A_PDW4 | 15
5 | A_PDW5 | 21
5 | A_PDW12 | 29
5 | A_PDW12.1 | 27
5 | A_PDW10 | 19
5 | A_PDW18 | 27
5 | A_PDW22 | 27
5 | A_PDW26 | 29
5 | B_PDW5 | 19
5 | B_PDW12 | 27
5 | B_PDW22 | 15
5 | B_PDW26 | 29
5 | C_PDW5 | 19
5 | C_PDW9 | 15
5 | C_PDW10 | 21
5 | C_PDW22 | 27
5 | C_PDW26 | 29
6 | A_PDW5 | 21
6 | A_PDW10 | 19
6 | B_PDW5 | 19
6 | C_PDW5 | 19
6 | C_PDW10 | 21
7 | A_PDW-01A1A.1.0 | 1
7 | B_PDW-01A1A.1.0 | 1
7 | C_PDW-01A1A.1.0 | 1
9 | A_PDW5 | 21
9 | A_PDW10 | 19
9 | B_PDW5 | 19
9 | C_PDW5 | 19
9 | C_PDW10 | 21
10 | A_PDW-01A1A.1.0 | 1
10 | A_PDW15 | 31
10 | A_PDW25 | 29
10 | A_PDW28 | 31
10 | A_PDW30 | 43
10 | A_PDW31 | 43
10 | A_PDW32 | 31
10 | A_PDW37 | 29
10 | A_PDW41 | 43
10 | A_PDW42 | 29
10 | B_PDW-01A1A.1.0 | 1
10 | B_PDW-01A1A.13.0 | 29
10 | B_PDW21 | 43
10 | B_PDW24 | 31
10 | B_PDW26 | 29
10 | B_PDW33 | 29
10 | B_PDW40 | 31
10 | B_PDW41 | 43
10 | B_PDW43 | 31
10 | B_PDW44 | 43
10 | B_PDW45 | 43
10 | C_PDW-01A1A.1.0 | 1
10 | C_PDW12 | 31
10 | C_PDW16 | 29
10 | C_PDW17 | 43
10 | C_PDW20 | 43
10 | C_PDW25 | 31
10 | C_PDW26 | 29
10 | C_PDW28 | 31
10 | C_PDW33 | 31
10 | C_PDW38 | 29
10 | C_PDW41 | 43
10 | C_PDW44 | 29
11 | A_PDW-01A1A.1.0 | 1
11 | A_PDW-01A1A.11.0 | 15
11 | A_PDW-01A1A.13.0 | 21
11 | A_PDW-01A1A.14.0 | 21
11 | A_PDW9 | 15
11 | A_PDW13 | 15
11 | A_PDW16 | 31
11 | A_PDW17 | 21
11 | A_PDW21 | 21
11 | A_PDW22 | 27
11 | A_PDW33 | 31
11 | A_PDW36 | 31
11 | A_PDW45 | 27
11 | B_PDW-01A1A.1.0 | 1
11 | B_PDW-01A1A.21.0 | 15
11 | B_PDW-01A1AIF.1.0 | 21
11 | B_PDW13 | 27
11 | B_PDW15 | 31
11 | B_PDW19 | 15
11 | B_PDW20 | 27
11 | B_PDW22 | 15
11 | B_PDW25 | 21
11 | B_PDW30 | 21
11 | B_PDW32 | 31
11 | B_PDW37 | 31
11 | C_PDW-01A1A.1.0 | 1
11 | C_PDW-01A1A.17.0 | 21
11 | C_PDW2 | 15
11 | C_PDW4 | 27
11 | C_PDW-01A1AIF.1.0 | 15
11 | C_PDW8 | 15
11 | C_PDW13 | 21
11 | C_PDW18 | 31
11 | C_PDW18.2 | 27
11 | C_PDW22 | 27
11 | C_PDW24 | 31
11 | C_PDW29 | 31
11 | C_PDW34 | 31
11 | C_PDW43 | 21

## B
task | task | value
A_PDW-01A1A.11.0 | A_PDW9 | 1
A_PDW-01A1A.11.0 | A_PDW13 | 1
A_PDW-01A1A.13.0 | A_PDW-01A1A.14.0 | 1
A_PDW-01A1A.13.0 | A_PDW17 | 1
A_PDW-01A1A.14.0 | A_PDW17 | 1
A_PDW-01A1A.17.0 | A_PDW41 | 1
A_PDW-01A1A.21.0 | A_PDW-01A1A.27.0 | 1
A_PDW-01A1A.21.0 | A_PDW-01A1A.30.0 | 1
A_PDW-01A1A.27.0 | A_PDW-01A1A.30.0 | 1
A_PDW2 | A_PDW3 | 1
A_PDW-01A1AIF.1.0 | A_PDW8 | 1
A_PDW-01A1AIF.1.0 | A_PDW43 | 1
A_PDW9 | A_PDW13 | 1
A_PDW12 | A_PDW26 | 1
A_PDW12.1 | A_PDW22 | 1
A_PDW15 | A_PDW32 | 1
A_PDW16 | A_PDW33 | 1
A_PDW18 | A_PDW12.1 | 1
A_PDW18 | A_PDW22 | 1
A_PDW19 | A_PDW22 | 1
A_PDW20 | A_PDW24 | 1
A_PDW21 | A_PDW-01A1A.13.0 | 1
A_PDW21 | A_PDW-01A1A.14.0 | 1
A_PDW21 | A_PDW17 | 1
A_PDW28 | A_PDW15 | 1
A_PDW28 | A_PDW32 | 1
A_PDW29 | A_PDW20 | 1
A_PDW29 | A_PDW24 | 1
A_PDW30 | A_PDW41 | 1
A_PDW31 | A_PDW30 | 1
A_PDW31 | A_PDW41 | 1
A_PDW34 | A_PDW26 | 1
A_PDW36 | A_PDW16 | 1
A_PDW36 | A_PDW33 | 1
A_PDW37 | A_PDW25 | 1
A_PDW37 | A_PDW26 | 1
A_PDW37 | A_PDW42 | 1
A_PDW38 | A_PDW-01A1A.17.0 | 1
A_PDW38 | A_PDW41 | 1
A_PDW39 | A_PDW26 | 1
A_PDW39 | A_PDW34 | 1
A_PDW40 | A_PDW20 | 1
A_PDW40 | A_PDW24 | 1
A_PDW40 | A_PDW29 | 1
A_PDW42 | A_PDW25 | 1
A_PDW43 | A_PDW8 | 1
A_PDW44 | A_PDW19 | 1
A_PDW44 | A_PDW22 | 1
A_PDW45 | A_PDW22 | 1
B_PDW-01A1A.13.0 | B_PDW26 | 1
B_PDW-01A1A.13.0 | B_PDW33 | 1
B_PDW-01A1A.21.0 | B_PDW19 | 1
B_PDW-01A1A.21.0 | B_PDW22 | 1
B_PDW-01A1A.27.0 | B_PDW22 | 1
B_PDW-01A1A.30.0 | B_PDW8 | 1
B_PDW-01A1A.30.0 | B_PDW9 | 1
B_PDW-01A1AIF.1.0 | B_PDW25 | 1
B_PDW-01A1AIF.1.0 | B_PDW30 | 1
B_PDW9 | B_PDW8 | 1
B_PDW12.1 | B_PDW17 | 1
B_PDW15 | B_PDW32 | 1
B_PDW16 | B_PDW41 | 1
B_PDW18 | B_PDW-01A1A.27.0 | 1
B_PDW18 | B_PDW22 | 1
B_PDW19 | B_PDW22 | 1
B_PDW20 | B_PDW13 | 1
B_PDW21 | B_PDW41 | 1
B_PDW21 | B_PDW44 | 1
B_PDW21 | B_PDW45 | 1
B_PDW28 | B_PDW12.1 | 1
B_PDW28 | B_PDW17 | 1
B_PDW29 | B_PDW-01A1A.17.0 | 1
B_PDW30 | B_PDW25 | 1
B_PDW31 | B_PDW42 | 1
B_PDW33 | B_PDW26 | 1
B_PDW34 | B_PDW16 | 1
B_PDW34 | B_PDW41 | 1
B_PDW36 | B_PDW31 | 1
B_PDW36 | B_PDW42 | 1
B_PDW37 | B_PDW15 | 1
B_PDW37 | B_PDW32 | 1
B_PDW38 | B_PDW16 | 1
B_PDW38 | B_PDW34 | 1
B_PDW38 | B_PDW41 | 1
B_PDW39 | B_PDW-01A1A.17.0 | 1
B_PDW39 | B_PDW29 | 1
B_PDW40 | B_PDW24 | 1
B_PDW40 | B_PDW43 | 1
B_PDW43 | B_PDW24 | 1
B_PDW44 | B_PDW41 | 1
B_PDW44 | B_PDW45 | 1
B_PDW45 | B_PDW41 | 1
C_PDW-01A1A.11.0 | C_PDW-01A1A.13.0 | 1
C_PDW-01A1A.11.0 | C_PDW-01A1AIF.1.0 | 1
C_PDW-01A1A.11.0 | C_PDW42 | 1
C_PDW-01A1A.11.0 | C_PDW45 | 1
C_PDW-01A1A.13.0 | C_PDW42 | 1
C_PDW-01A1A.13.0 | C_PDW45 | 1
C_PDW-01A1A.14.0 | C_PDW15 | 1
C_PDW-01A1A.14.0 | C_PDW30 | 1
C_PDW-01A1A.21.0 | C_PDW-01A1A.27.0 | 1
C_PDW-01A1A.21.0 | C_PDW-01A1A.30.0 | 1
C_PDW-01A1A.21.0 | C_PDW3 | 1
C_PDW-01A1A.27.0 | C_PDW-01A1A.30.0 | 1
C_PDW-01A1A.27.0 | C_PDW3 | 1
C_PDW-01A1A.30.0 | C_PDW3 | 1
C_PDW2 | C_PDW-01A1AIF.1.0 | 1
C_PDW2 | C_PDW8 | 1
C_PDW4 | C_PDW22 | 1
C_PDW-01A1AIF.1.0 | C_PDW8 | 1
C_PDW13 | C_PDW-01A1A.17.0 | 1
C_PDW12 | C_PDW25 | 1
C_PDW12 | C_PDW33 | 1
C_PDW12.1 | C_PDW32 | 1
C_PDW15 | C_PDW30 | 1
C_PDW16 | C_PDW26 | 1
C_PDW17 | C_PDW20 | 1
C_PDW17 | C_PDW41 | 1
C_PDW18 | C_PDW24 | 1
C_PDW18 | C_PDW29 | 1
C_PDW18 | C_PDW34 | 1
C_PDW18.1 | C_PDW31 | 1
C_PDW18.1 | C_PDW41 | 1
C_PDW18.2 | C_PDW4 | 1
C_PDW18.2 | C_PDW22 | 1
C_PDW19 | C_PDW22 | 1
C_PDW20 | C_PDW41 | 1
C_PDW21 | C_PDW12.1 | 1
C_PDW21 | C_PDW32 | 1
C_PDW21 | C_PDW39 | 1
C_PDW28 | C_PDW12 | 1
C_PDW28 | C_PDW25 | 1
C_PDW28 | C_PDW33 | 1
C_PDW29 | C_PDW24 | 1
C_PDW29 | C_PDW34 | 1
C_PDW31 | C_PDW41 | 1
C_PDW33 | C_PDW25 | 1
C_PDW34 | C_PDW24 | 1
C_PDW36 | C_PDW-01A1A.14.0 | 1
C_PDW36 | C_PDW15 | 1
C_PDW36 | C_PDW30 | 1
C_PDW37 | C_PDW-01A1A.14.0 | 1
C_PDW37 | C_PDW15 | 1
C_PDW37 | C_PDW30 | 1
C_PDW37 | C_PDW36 | 1
C_PDW38 | C_PDW16 | 1
C_PDW38 | C_PDW26 | 1
C_PDW38 | C_PDW44 | 1
C_PDW39 | C_PDW12.1 | 1
C_PDW39 | C_PDW32 | 1
C_PDW40 | C_PDW18.1 | 1
C_PDW40 | C_PDW31 | 1
C_PDW40 | C_PDW41 | 1
C_PDW42 | C_PDW45 | 1
C_PDW43 | C_PDW-01A1A.17.0 | 1
C_PDW43 | C_PDW13 | 1
C_PDW44 | C_PDW16 | 1
C_PDW44 | C_PDW26 | 1

## N
stage | number of station | value
1 | 1 | 1
5 | 1 | 1
7 | 1 | 1
15 | 1 | 1
19 | 1 | 1
21 | 1 | 1
27 | 1 | 1
29 | 1 | 1
31 | 1 | 1
43 | 1 | 1
48 | 1 | 1