## X
task | task name | stage | resource type req | selected option | selected duration
A_PDW-01A1A.1.0 | 1. Frame | 1 | ['worker', 'robot arm'] | 2 | 45
A_PDW-01A1A.11.0 | 11. Install bath tub / shower pan | 1 | ['worker'] | 0 | 6
A_PDW-01A1A.13.0 | 13. Install ceiling CLG-01A | 1 | ['worker'] | 1 | 7
A_PDW-01A1A.14.0 | 14. Connect Fire Sprinkler Ceiling Assemblies | 1 | ['worker'] | 0 | 22
A_PDW-01A1A.17.0 | 17. Install electrical panel | 1 | ['worker', 'robot arm'] | 1 | 21
A_PDW-01A1A.21.0 | 21. Conduct Plumbing & sprinkler Pressure Test | 1 | ['worker'] | 0 | 5
A_PDW-01A1A.27.0 | 27. Install Lid LID-01A | 1 | ['worker'] | 1 | 11
A_PDW-01A1A.30.0 | 30. Move Pod to Finish Station | 1 | ['worker', 'robot arm'] | 1 | 6
A_PDW2 | Bathroom insulation, drywall and tape/bed | 1 | ['dryer'] | 0 | 12
A_PDW3 | kitchen insulation, drywall and tape/bed | 2 | ['dryer'] | 0 | 19
A_PDW4 | exterior insulation, drywall and tape/bed | 2 | ['dryer'] | 0 | 19
A_PDW5 | dry bathroom | 2 | ['dryer'] | 1 | 125
A_PDW-01A1AIF.1.0 | 1. Set-up for finishing stage | 2 | ['worker'] | 0 | 5
A_PDW8 | skim bathroom | 2 | ['worker'] | 0 | 22
A_PDW9 | skim kitchen | 2 | ['worker'] | 0 | 17
A_PDW13 | skim outside | 2 | ['worker'] | 0 | 35
A_PDW12 | install doors and casing Bathroom | 2 | ['dryer'] | 1 | 14
A_PDW12.1 | install doors and casing Kitchen | 2 | ['dryer'] | 0 | 20
A_PDW10 | skim dry bathroom | 3 | ['dryer'] | 2 | 118
A_PDW15 | sand bathroom | 4 | ['worker'] | 1 | 13
A_PDW16 | sand kitchen | 4 | ['worker'] | 0 | 17
A_PDW17 | sand outside | 4 | ['worker'] | 0 | 35
A_PDW18 | Install Tub/Shower Surround | 4 | ['dryer'] | 0 | 10
A_PDW19 | Prime paint bathroom | 4 | ['worker'] | 1 | 5
A_PDW20 | Prime paint kitchen | 4 | ['worker'] | 1 | 5
A_PDW21 | Apply wall covering | 5 | ['worker'] | 0 | 2
A_PDW22 | Prime dry bathroom | 4 | ['dryer', 'worker'] | 1 | 80
A_PDW24 | Paint bathroom | 5 | ['worker'] | 0 | 43
A_PDW25 | Paint kitchen | 5 | ['worker'] | 0 | 37
A_PDW26 | Paint dry | 6 | ['dryer', 'worker'] | 1 | 80
A_PDW28 | cove base bathroom | 6 | ['worker'] | 0 | 14
A_PDW29 | cove base kitchen | 7 | ['worker'] | 0 | 14
A_PDW30 | bathroom plumbing | 7 | ['worker'] | 1 | 15
A_PDW31 | bathroom trim | 7 | ['worker'] | 1 | 15
A_PDW32 | Install Interior Cabinets & Countertops | 7 | ['worker'] | 0 | 45
A_PDW33 | Kitchen plumbing and appliances | 7 | ['worker'] | 0 | 25
A_PDW34 | Install Electrical Fixtures & trim | 7 | ['worker'] | 0 | 16
A_PDW36 | 25. Connect POD to POD | 7 | ['worker'] | 1 | 7
A_PDW37 | 26. Install interior pod to pod connection finishes | 7 | ['worker'] | 0 | 1
A_PDW38 | 27. Connect pod to pod electrical | 7 | ['worker'] | 0 | 10
A_PDW39 | 28. Install Batt Insulation in lids and Inspection | 8 | ['worker'] | 0 | 14
A_PDW40 | 30. Install Sheathing on top of lids | 8 | ['worker'] | 0 | 5
A_PDW41 | Perform test | 7 | ['worker'] | 1 | 65
A_PDW42 | Batt Insulation in walls | 7 | ['worker'] | 0 | 28
A_PDW43 | 40. Execute final interior punch - close NCRs | 8 | ['worker'] | 0 | 20
A_PDW44 | 42. Final clean-up entire module | 8 | ['worker'] | 0 | 10
A_PDW45 | Wrap, document and move to ship | 8 | ['worker'] | 0 | 31
B_PDW-01A1A.1.0 | 1. Frame | 1 | ['worker', 'robot arm'] | 2 | 40
B_PDW-01A1A.13.0 | 13. Install ceiling CLG-01A | 1 | ['worker'] | 1 | 7
B_PDW-01A1A.17.0 | 17. Install electrical panel | 1 | ['worker', 'robot arm'] | 1 | 21
B_PDW-01A1A.21.0 | 21. Conduct Plumbing & sprinkler Pressure Test | 1 | ['worker'] | 0 | 5
B_PDW-01A1A.27.0 | 27. Install Lid LID-01A | 1 | ['worker'] | 1 | 11
B_PDW-01A1A.30.0 | 30. Move Pod to Finish Station | 1 | ['worker', 'robot arm'] | 1 | 6
B_PDW5 | dry bathroom | 2 | ['dryer'] | 1 | 105
B_PDW-01A1AIF.1.0 | 1. Set-up for finishing stage | 7 | ['worker'] | 0 | 5
B_PDW8 | skim bathroom | 2 | ['worker'] | 0 | 22
B_PDW9 | skim kitchen | 2 | ['worker'] | 0 | 17
B_PDW13 | skim outside | 2 | ['worker'] | 0 | 35
B_PDW12 | install doors and casing Bathroom | 3 | ['dryer'] | 1 | 14
B_PDW12.1 | install doors and casing Kitchen | 2 | ['worker'] | 0 | 20
B_PDW10 | skim dry bathroom | 3 | ['dryer'] | 2 | 98
B_PDW15 | sand bathroom | 4 | ['worker'] | 1 | 13
B_PDW16 | sand kitchen | 4 | ['worker'] | 0 | 17
B_PDW17 | sand outside | 4 | ['worker'] | 0 | 35
B_PDW18 | Install Tub/Shower Surround | 4 | ['worker'] | 1 | 7
B_PDW19 | Prime paint bathroom | 4 | ['worker'] | 1 | 5
B_PDW20 | Prime paint kitchen | 4 | ['worker'] | 1 | 5
B_PDW21 | Apply wall covering | 5 | ['worker'] | 0 | 2
B_PDW22 | Prime dry bathroom | 4 | ['dryer', 'worker'] | 1 | 80
B_PDW24 | Paint bathroom | 5 | ['worker'] | 0 | 43
B_PDW25 | Paint kitchen | 5 | ['worker'] | 0 | 37
B_PDW26 | Paint dry | 6 | ['dryer', 'worker'] | 1 | 80
B_PDW28 | cove base bathroom | 6 | ['worker'] | 0 | 14
B_PDW29 | cove base kitchen | 7 | ['worker'] | 0 | 14
B_PDW30 | bathroom plumbing | 7 | ['worker'] | 1 | 15
B_PDW31 | bathroom trim | 7 | ['worker'] | 1 | 15
B_PDW32 | Install Interior Cabinets & Countertops | 7 | ['worker'] | 0 | 45
B_PDW33 | Kitchen plumbing and appliances | 7 | ['worker'] | 0 | 25
B_PDW34 | Install Electrical Fixtures & trim | 7 | ['worker'] | 0 | 16
B_PDW36 | 25. Connect POD to POD | 7 | ['worker'] | 1 | 7
B_PDW37 | 26. Install interior pod to pod connection finishes | 7 | ['worker'] | 0 | 1
B_PDW38 | 27. Connect pod to pod electrical | 7 | ['worker'] | 0 | 10
B_PDW39 | 28. Install Batt Insulation in lids and Inspection | 7 | ['worker'] | 0 | 14
B_PDW40 | 30. Install Sheathing on top of lids | 8 | ['worker'] | 0 | 5
B_PDW41 | Perform test | 7 | ['worker'] | 1 | 65
B_PDW42 | Batt Insulation in walls | 8 | ['worker'] | 0 | 28
B_PDW43 | 40. Execute final interior punch - close NCRs | 8 | ['worker'] | 0 | 20
B_PDW44 | 42. Final clean-up entire module | 8 | ['worker'] | 0 | 10
B_PDW45 | Wrap, document and move to ship | 8 | ['worker'] | 0 | 31
C_PDW-01A1A.1.0 | 1. Frame | 1 | ['worker', 'robot arm'] | 2 | 45
C_PDW-01A1A.11.0 | 11. Install bath tub / shower pan | 1 | ['worker'] | 0 | 6
C_PDW-01A1A.13.0 | 13. Install ceiling CLG-01A | 1 | ['worker'] | 1 | 7
C_PDW-01A1A.14.0 | 14. Connect Fire Sprinkler Ceiling Assemblies | 1 | ['worker'] | 0 | 22
C_PDW-01A1A.17.0 | 17. Install electrical panel | 1 | ['worker', 'robot arm'] | 1 | 21
C_PDW-01A1A.21.0 | 21. Conduct Plumbing & sprinkler Pressure Test | 1 | ['worker'] | 0 | 5
C_PDW-01A1A.27.0 | 27. Install Lid LID-01A | 1 | ['worker'] | 1 | 11
C_PDW-01A1A.30.0 | 30. Move Pod to Finish Station | 1 | ['worker', 'robot arm'] | 1 | 6
C_PDW2 | Bathroom insulation, drywall and tape/bed | 2 | ['worker'] | 0 | 12
C_PDW3 | kitchen insulation, drywall and tape/bed | 2 | ['worker'] | 0 | 19
C_PDW4 | exterior insulation, drywall and tape/bed | 2 | ['worker'] | 0 | 19
C_PDW5 | dry bathroom | 2 | ['dryer'] | 1 | 125
C_PDW-01A1AIF.1.0 | 1. Set-up for finishing stage | 2 | ['worker'] | 0 | 5
C_PDW8 | skim bathroom | 2 | ['worker'] | 0 | 35
C_PDW9 | skim kitchen | 2 | ['dryer'] | 1 | 8
C_PDW13 | skim outside | 4 | ['worker'] | 0 | 22
C_PDW12 | install doors and casing Bathroom | 2 | ['worker'] | 0 | 17
C_PDW12.1 | install doors and casing Kitchen | 6 | ['worker'] | 0 | 20
C_PDW10 | skim dry bathroom | 3 | ['dryer'] | 2 | 118
C_PDW15 | sand bathroom | 4 | ['worker'] | 0 | 22
C_PDW16 | sand kitchen | 4 | ['worker'] | 0 | 17
C_PDW17 | sand outside | 4 | ['worker'] | 0 | 20
C_PDW18 | Install Tub/Shower Surround | 4 | ['worker'] | 0 | 10
C_PDW18.1 | Install Tub/Shower Surround | 4 | ['worker'] | 0 | 14
C_PDW18.2 | Install Tub/Shower Surround | 4 | ['worker'] | 0 | 10
C_PDW19 | Prime paint bathroom | 4 | ['worker'] | 1 | 5
C_PDW20 | Prime paint kitchen | 7 | ['worker'] | 0 | 22
C_PDW21 | Apply wall covering | 5 | ['worker'] | 0 | 2
C_PDW22 | Prime dry bathroom | 4 | ['dryer', 'worker'] | 1 | 80
C_PDW24 | Paint bathroom | 5 | ['worker'] | 0 | 43
C_PDW25 | Paint kitchen | 5 | ['worker'] | 0 | 37
C_PDW26 | Paint dry | 6 | ['dryer', 'worker'] | 1 | 80
C_PDW28 | cove base bathroom | 7 | ['worker'] | 0 | 14
C_PDW29 | cove base kitchen | 6 | ['worker'] | 0 | 14
C_PDW30 | bathroom plumbing | 7 | ['worker'] | 1 | 15
C_PDW31 | bathroom trim | 7 | ['worker'] | 1 | 15
C_PDW32 | Install Interior Cabinets & Countertops | 7 | ['worker'] | 0 | 45
C_PDW33 | Kitchen plumbing and appliances | 7 | ['worker'] | 0 | 25
C_PDW34 | Install Electrical Fixtures & trim | 7 | ['worker'] | 0 | 16
C_PDW36 | 25. Connect POD to POD | 7 | ['worker'] | 0 | 10
C_PDW37 | 26. Install interior pod to pod connection finishes | 7 | ['worker'] | 0 | 1
C_PDW38 | 27. Connect pod to pod electrical | 7 | ['worker'] | 0 | 10
C_PDW39 | 28. Install Batt Insulation in lids and Inspection | 7 | ['worker'] | 0 | 14
C_PDW40 | 30. Install Sheathing on top of lids | 8 | ['worker'] | 0 | 5
C_PDW41 | Perform test | 7 | ['worker'] | 1 | 65
C_PDW42 | Batt Insulation in walls | 8 | ['worker'] | 0 | 28
C_PDW43 | 40. Execute final interior punch - close NCRs | 8 | ['worker'] | 0 | 20
C_PDW44 | 42. Final clean-up entire module | 8 | ['worker'] | 0 | 10
C_PDW45 | Wrap, document and move to ship | 8 | ['worker'] | 0 | 31

## Y
worker | stage | number of station | team cost | stage team cost
1 | 1 | 1 | 55 | 55
1 | 2 | 2 | 55 | 110
1 | 4 | 1 | 55 | 55
1 | 5 | 1 | 55 | 55
1 | 7 | 1 | 55 | 55
1 | 8 | 1 | 55 | 55
2 | 1 | 1 | 55 | 55
2 | 7 | 1 | 55 | 55
3 | 4 | 1 | 55 | 55
3 | 7 | 1 | 55 | 55
4 | 1 | 1 | 50 | 50
4 | 2 | 2 | 50 | 100
4 | 3 | 1 | 50 | 50
4 | 4 | 1 | 50 | 50
4 | 6 | 1 | 50 | 50
5 | 1 | 1 | 50 | 50
5 | 2 | 2 | 50 | 100
5 | 3 | 1 | 50 | 50
6 | 3 | 1 | 50 | 50
8 | 1 | 1 | 90 | 90
9 | 3 | 1 | 50 | 50
10 | 4 | 1 | 55 | 55
10 | 6 | 1 | 55 | 55

## T
task | task name | start time
A_PDW-01A1A.1.0 | 1. Frame | 0
A_PDW-01A1A.11.0 | 11. Install bath tub / shower pan | 45
A_PDW-01A1A.13.0 | 13. Install ceiling CLG-01A | 51
A_PDW-01A1A.14.0 | 14. Connect Fire Sprinkler Ceiling Assemblies | 58
A_PDW-01A1A.17.0 | 17. Install electrical panel | 58
A_PDW-01A1A.21.0 | 21. Conduct Plumbing & sprinkler Pressure Test | 80
A_PDW-01A1A.27.0 | 27. Install Lid LID-01A | 85
A_PDW-01A1A.30.0 | 30. Move Pod to Finish Station | 96
A_PDW2 | Bathroom insulation, drywall and tape/bed | 102
A_PDW3 | kitchen insulation, drywall and tape/bed | 0
A_PDW4 | exterior insulation, drywall and tape/bed | 0
A_PDW5 | dry bathroom | 19
A_PDW-01A1AIF.1.0 | 1. Set-up for finishing stage | 144
A_PDW8 | skim bathroom | 149
A_PDW9 | skim kitchen | 206
A_PDW13 | skim outside | 171
A_PDW12 | install doors and casing Bathroom | 226
A_PDW12.1 | install doors and casing Kitchen | 206
A_PDW10 | skim dry bathroom | 0
A_PDW15 | sand bathroom | 0
A_PDW16 | sand kitchen | 0
A_PDW17 | sand outside | 28
A_PDW18 | Install Tub/Shower Surround | 13
A_PDW19 | Prime paint bathroom | 23
A_PDW20 | Prime paint kitchen | 17
A_PDW21 | Apply wall covering | 0
A_PDW22 | Prime dry bathroom | 28
A_PDW24 | Paint bathroom | 39
A_PDW25 | Paint kitchen | 2
A_PDW26 | Paint dry | 0
A_PDW28 | cove base bathroom | 80
A_PDW29 | cove base kitchen | 0
A_PDW30 | bathroom plumbing | 0
A_PDW31 | bathroom trim | 15
A_PDW32 | Install Interior Cabinets & Countertops | 65
A_PDW33 | Kitchen plumbing and appliances | 30
A_PDW34 | Install Electrical Fixtures & trim | 14
A_PDW36 | 25. Connect POD to POD | 30
A_PDW37 | 26. Install interior pod to pod connection finishes | 37
A_PDW38 | 27. Connect pod to pod electrical | 38
A_PDW39 | 28. Install Batt Insulation in lids and Inspection | 0
A_PDW40 | 30. Install Sheathing on top of lids | 14
A_PDW41 | Perform test | 55
A_PDW42 | Batt Insulation in walls | 37
A_PDW43 | 40. Execute final interior punch - close NCRs | 19
A_PDW44 | 42. Final clean-up entire module | 39
A_PDW45 | Wrap, document and move to ship | 49
B_PDW-01A1A.1.0 | 1. Frame | 0
B_PDW-01A1A.13.0 | 13. Install ceiling CLG-01A | 40
B_PDW-01A1A.17.0 | 17. Install electrical panel | 47
B_PDW-01A1A.21.0 | 21. Conduct Plumbing & sprinkler Pressure Test | 68
B_PDW-01A1A.27.0 | 27. Install Lid LID-01A | 73
B_PDW-01A1A.30.0 | 30. Move Pod to Finish Station | 84
B_PDW5 | dry bathroom | 0
B_PDW-01A1AIF.1.0 | 1. Set-up for finishing stage | 0
B_PDW8 | skim bathroom | 17
B_PDW9 | skim kitchen | 0
B_PDW13 | skim outside | 39
B_PDW12 | install doors and casing Bathroom | 0
B_PDW12.1 | install doors and casing Kitchen | 74
B_PDW10 | skim dry bathroom | 14
B_PDW15 | sand bathroom | 0
B_PDW16 | sand kitchen | 0
B_PDW17 | sand outside | 30
B_PDW18 | Install Tub/Shower Surround | 13
B_PDW19 | Prime paint bathroom | 20
B_PDW20 | Prime paint kitchen | 25
B_PDW21 | Apply wall covering | 0
B_PDW22 | Prime dry bathroom | 30
B_PDW24 | Paint bathroom | 39
B_PDW25 | Paint kitchen | 2
B_PDW26 | Paint dry | 0
B_PDW28 | cove base bathroom | 80
B_PDW29 | cove base kitchen | 0
B_PDW30 | bathroom plumbing | 0
B_PDW31 | bathroom trim | 15
B_PDW32 | Install Interior Cabinets & Countertops | 55
B_PDW33 | Kitchen plumbing and appliances | 30
B_PDW34 | Install Electrical Fixtures & trim | 14
B_PDW36 | 25. Connect POD to POD | 30
B_PDW37 | 26. Install interior pod to pod connection finishes | 37
B_PDW38 | 27. Connect pod to pod electrical | 38
B_PDW39 | 28. Install Batt Insulation in lids and Inspection | 37
B_PDW40 | 30. Install Sheathing on top of lids | 0
B_PDW41 | Perform test | 51
B_PDW42 | Batt Insulation in walls | 25
B_PDW43 | 40. Execute final interior punch - close NCRs | 5
B_PDW44 | 42. Final clean-up entire module | 53
B_PDW45 | Wrap, document and move to ship | 63
C_PDW-01A1A.1.0 | 1. Frame | 0
C_PDW-01A1A.11.0 | 11. Install bath tub / shower pan | 45
C_PDW-01A1A.13.0 | 13. Install ceiling CLG-01A | 51
C_PDW-01A1A.14.0 | 14. Connect Fire Sprinkler Ceiling Assemblies | 58
C_PDW-01A1A.17.0 | 17. Install electrical panel | 58
C_PDW-01A1A.21.0 | 21. Conduct Plumbing & sprinkler Pressure Test | 80
C_PDW-01A1A.27.0 | 27. Install Lid LID-01A | 85
C_PDW-01A1A.30.0 | 30. Move Pod to Finish Station | 96
C_PDW2 | Bathroom insulation, drywall and tape/bed | 0
C_PDW3 | kitchen insulation, drywall and tape/bed | 12
C_PDW4 | exterior insulation, drywall and tape/bed | 31
C_PDW5 | dry bathroom | 50
C_PDW-01A1AIF.1.0 | 1. Set-up for finishing stage | 175
C_PDW8 | skim bathroom | 205
C_PDW9 | skim kitchen | 180
C_PDW13 | skim outside | 37
C_PDW12 | install doors and casing Bathroom | 188
C_PDW12.1 | install doors and casing Kitchen | 0
C_PDW10 | skim dry bathroom | 0
C_PDW15 | sand bathroom | 0
C_PDW16 | sand kitchen | 0
C_PDW17 | sand outside | 0
C_PDW18 | Install Tub/Shower Surround | 22
C_PDW18.1 | Install Tub/Shower Surround | 17
C_PDW18.2 | Install Tub/Shower Surround | 20
C_PDW19 | Prime paint bathroom | 32
C_PDW20 | Prime paint kitchen | 15
C_PDW21 | Apply wall covering | 0
C_PDW22 | Prime dry bathroom | 37
C_PDW24 | Paint bathroom | 39
C_PDW25 | Paint kitchen | 2
C_PDW26 | Paint dry | 20
C_PDW28 | cove base bathroom | 0
C_PDW29 | cove base kitchen | 100
C_PDW30 | bathroom plumbing | 15
C_PDW31 | bathroom trim | 0
C_PDW32 | Install Interior Cabinets & Countertops | 55
C_PDW33 | Kitchen plumbing and appliances | 30
C_PDW34 | Install Electrical Fixtures & trim | 14
C_PDW36 | 25. Connect POD to POD | 30
C_PDW37 | 26. Install interior pod to pod connection finishes | 40
C_PDW38 | 27. Connect pod to pod electrical | 41
C_PDW39 | 28. Install Batt Insulation in lids and Inspection | 40
C_PDW40 | 30. Install Sheathing on top of lids | 0
C_PDW41 | Perform test | 54
C_PDW42 | Batt Insulation in walls | 5
C_PDW43 | 40. Execute final interior punch - close NCRs | 33
C_PDW44 | 42. Final clean-up entire module | 53
C_PDW45 | Wrap, document and move to ship | 63

## A
worker | task | stage
1 | A_PDW-01A1A.1.0 | 1
1 | A_PDW-01A1A.11.0 | 1
1 | A_PDW-01A1A.13.0 | 1
1 | A_PDW-01A1A.14.0 | 1
1 | A_PDW-01A1A.27.0 | 1
1 | A_PDW-01A1A.30.0 | 1
1 | A_PDW-01A1AIF.1.0 | 2
1 | A_PDW8 | 2
1 | A_PDW9 | 2
1 | A_PDW13 | 2
1 | A_PDW15 | 4
1 | A_PDW17 | 4
1 | A_PDW19 | 4
1 | A_PDW20 | 4
1 | A_PDW21 | 5
1 | A_PDW24 | 5
1 | A_PDW25 | 5
1 | A_PDW30 | 7
1 | A_PDW31 | 7
1 | A_PDW33 | 7
1 | A_PDW39 | 8
1 | A_PDW40 | 8
1 | A_PDW41 | 7
1 | A_PDW43 | 8
1 | A_PDW44 | 8
1 | A_PDW45 | 8
1 | B_PDW-01A1A.1.0 | 1
1 | B_PDW-01A1A.13.0 | 1
1 | B_PDW-01A1A.17.0 | 1
1 | B_PDW-01A1A.21.0 | 1
1 | B_PDW-01A1A.27.0 | 1
1 | B_PDW8 | 2
1 | B_PDW9 | 2
1 | B_PDW13 | 2
1 | B_PDW12.1 | 2
1 | B_PDW16 | 4
1 | B_PDW17 | 4
1 | B_PDW19 | 4
1 | B_PDW20 | 4
1 | B_PDW21 | 5
1 | B_PDW24 | 5
1 | B_PDW25 | 5
1 | B_PDW30 | 7
1 | B_PDW31 | 7
1 | B_PDW32 | 7
1 | B_PDW33 | 7
1 | B_PDW40 | 8
1 | B_PDW42 | 8
1 | B_PDW43 | 8
1 | B_PDW44 | 8
1 | B_PDW45 | 8
1 | C_PDW-01A1A.1.0 | 1
1 | C_PDW-01A1A.13.0 | 1
1 | C_PDW-01A1A.17.0 | 1
1 | C_PDW-01A1A.27.0 | 1
1 | C_PDW-01A1A.30.0 | 1
1 | C_PDW2 | 2
1 | C_PDW3 | 2
1 | C_PDW4 | 2
1 | C_PDW-01A1AIF.1.0 | 2
1 | C_PDW8 | 2
1 | C_PDW12 | 2
1 | C_PDW16 | 4
1 | C_PDW18.1 | 4
1 | C_PDW19 | 4
1 | C_PDW21 | 5
1 | C_PDW22 | 4
1 | C_PDW24 | 5
1 | C_PDW25 | 5
1 | C_PDW28 | 7
1 | C_PDW32 | 7
1 | C_PDW33 | 7
1 | C_PDW34 | 7
1 | C_PDW40 | 8
1 | C_PDW42 | 8
1 | C_PDW43 | 8
1 | C_PDW44 | 8
1 | C_PDW45 | 8
2 | A_PDW-01A1A.1.0 | 1
2 | A_PDW-01A1A.13.0 | 1
2 | A_PDW-01A1A.17.0 | 1
2 | A_PDW-01A1A.21.0 | 1
2 | A_PDW-01A1A.27.0 | 1
2 | A_PDW-01A1A.30.0 | 1
2 | A_PDW29 | 7
2 | A_PDW34 | 7
2 | A_PDW36 | 7
2 | A_PDW37 | 7
2 | A_PDW38 | 7
2 | A_PDW41 | 7
2 | B_PDW-01A1A.1.0 | 1
2 | B_PDW-01A1A.13.0 | 1
2 | B_PDW-01A1A.27.0 | 1
2 | B_PDW-01A1A.30.0 | 1
2 | B_PDW29 | 7
2 | B_PDW31 | 7
2 | B_PDW36 | 7
2 | B_PDW39 | 7
2 | B_PDW41 | 7
2 | C_PDW-01A1A.1.0 | 1
2 | C_PDW-01A1A.11.0 | 1
2 | C_PDW-01A1A.13.0 | 1
2 | C_PDW-01A1A.14.0 | 1
2 | C_PDW-01A1A.21.0 | 1
2 | C_PDW-01A1A.27.0 | 1
2 | C_PDW20 | 7
2 | C_PDW31 | 7
2 | C_PDW37 | 7
2 | C_PDW38 | 7
2 | C_PDW41 | 7
3 | A_PDW16 | 4
3 | A_PDW19 | 4
3 | A_PDW20 | 4
3 | A_PDW22 | 4
3 | A_PDW30 | 7
3 | A_PDW31 | 7
3 | A_PDW32 | 7
3 | A_PDW36 | 7
3 | A_PDW42 | 7
3 | B_PDW-01A1AIF.1.0 | 7
3 | B_PDW15 | 4
3 | B_PDW18 | 4
3 | B_PDW19 | 4
3 | B_PDW20 | 4
3 | B_PDW22 | 4
3 | B_PDW34 | 7
3 | B_PDW36 | 7
3 | B_PDW37 | 7
3 | B_PDW38 | 7
3 | B_PDW41 | 7
3 | C_PDW13 | 4
3 | C_PDW15 | 4
3 | C_PDW18 | 4
3 | C_PDW19 | 4
3 | C_PDW30 | 7
3 | C_PDW31 | 7
3 | C_PDW36 | 7
3 | C_PDW39 | 7
3 | C_PDW41 | 7
4 | A_PDW2 | 1
4 | A_PDW4 | 2
4 | A_PDW5 | 2
4 | A_PDW12 | 2
4 | A_PDW12.1 | 2
4 | A_PDW10 | 3
4 | A_PDW18 | 4
4 | A_PDW22 | 4
4 | A_PDW26 | 6
4 | B_PDW5 | 2
4 | B_PDW12 | 3
4 | B_PDW10 | 3
4 | B_PDW22 | 4
4 | B_PDW26 | 6
4 | C_PDW5 | 2
4 | C_PDW9 | 2
4 | C_PDW10 | 3
4 | C_PDW22 | 4
4 | C_PDW26 | 6
5 | A_PDW2 | 1
5 | A_PDW3 | 2
5 | A_PDW5 | 2
5 | A_PDW12 | 2
5 | A_PDW10 | 3
5 | B_PDW5 | 2
5 | B_PDW12 | 3
5 | B_PDW10 | 3
5 | C_PDW5 | 2
5 | C_PDW9 | 2
5 | C_PDW10 | 3
6 | A_PDW10 | 3
6 | B_PDW12 | 3
6 | B_PDW10 | 3
6 | C_PDW10 | 3
8 | A_PDW-01A1A.1.0 | 1
8 | A_PDW-01A1A.17.0 | 1
8 | A_PDW-01A1A.30.0 | 1
8 | B_PDW-01A1A.1.0 | 1
8 | B_PDW-01A1A.17.0 | 1
8 | B_PDW-01A1A.30.0 | 1
8 | C_PDW-01A1A.1.0 | 1
8 | C_PDW-01A1A.17.0 | 1
8 | C_PDW-01A1A.30.0 | 1
9 | A_PDW10 | 3
9 | B_PDW12 | 3
9 | B_PDW10 | 3
9 | C_PDW10 | 3
10 | A_PDW15 | 4
10 | A_PDW19 | 4
10 | A_PDW20 | 4
10 | A_PDW22 | 4
10 | A_PDW26 | 6
10 | A_PDW28 | 6
10 | B_PDW15 | 4
10 | B_PDW18 | 4
10 | B_PDW19 | 4
10 | B_PDW20 | 4
10 | B_PDW22 | 4
10 | B_PDW26 | 6
10 | B_PDW28 | 6
10 | C_PDW12.1 | 6
10 | C_PDW17 | 4
10 | C_PDW18.2 | 4
10 | C_PDW19 | 4
10 | C_PDW22 | 4
10 | C_PDW26 | 6
10 | C_PDW29 | 6

## B
task | task
A_PDW-01A1A.1.0 | A_PDW-01A1A.11.0
A_PDW-01A1A.1.0 | A_PDW-01A1A.13.0
A_PDW-01A1A.1.0 | A_PDW-01A1A.14.0
A_PDW-01A1A.1.0 | A_PDW-01A1A.17.0
A_PDW-01A1A.1.0 | A_PDW-01A1A.21.0
A_PDW-01A1A.1.0 | A_PDW-01A1A.27.0
A_PDW-01A1A.1.0 | A_PDW-01A1A.30.0
A_PDW-01A1A.1.0 | A_PDW28
A_PDW-01A1A.11.0 | A_PDW-01A1A.13.0
A_PDW-01A1A.11.0 | A_PDW-01A1A.14.0
A_PDW-01A1A.11.0 | A_PDW-01A1A.17.0
A_PDW-01A1A.11.0 | A_PDW-01A1A.21.0
A_PDW-01A1A.11.0 | A_PDW-01A1A.27.0
A_PDW-01A1A.11.0 | A_PDW-01A1A.30.0
A_PDW-01A1A.13.0 | A_PDW-01A1A.14.0
A_PDW-01A1A.13.0 | A_PDW-01A1A.17.0
A_PDW-01A1A.13.0 | A_PDW-01A1A.21.0
A_PDW-01A1A.13.0 | A_PDW-01A1A.27.0
A_PDW-01A1A.13.0 | A_PDW-01A1A.30.0
A_PDW-01A1A.14.0 | A_PDW-01A1A.21.0
A_PDW-01A1A.14.0 | A_PDW-01A1A.27.0
A_PDW-01A1A.14.0 | A_PDW-01A1A.30.0
A_PDW-01A1A.17.0 | A_PDW-01A1A.21.0
A_PDW-01A1A.17.0 | A_PDW-01A1A.27.0
A_PDW-01A1A.17.0 | A_PDW-01A1A.30.0
A_PDW-01A1A.21.0 | A_PDW-01A1A.27.0
A_PDW-01A1A.21.0 | A_PDW-01A1A.30.0
A_PDW-01A1A.27.0 | A_PDW-01A1A.30.0
A_PDW3 | A_PDW2
A_PDW3 | A_PDW5
A_PDW3 | A_PDW12
A_PDW4 | A_PDW5
A_PDW4 | A_PDW12
A_PDW4 | A_PDW12.1
A_PDW5 | A_PDW12
A_PDW5 | A_PDW12.1
A_PDW-01A1AIF.1.0 | A_PDW8
A_PDW-01A1AIF.1.0 | A_PDW9
A_PDW-01A1AIF.1.0 | A_PDW13
A_PDW8 | A_PDW9
A_PDW8 | A_PDW13
A_PDW13 | A_PDW9
A_PDW12.1 | A_PDW12
A_PDW15 | A_PDW-01A1A.14.0
A_PDW15 | A_PDW-01A1A.27.0
A_PDW15 | A_PDW17
A_PDW15 | A_PDW19
A_PDW15 | A_PDW20
A_PDW15 | A_PDW22
A_PDW16 | A_PDW9
A_PDW16 | A_PDW19
A_PDW16 | A_PDW20
A_PDW16 | A_PDW22
A_PDW16 | A_PDW24
A_PDW16 | A_PDW36
A_PDW18 | A_PDW12.1
A_PDW18 | A_PDW22
A_PDW19 | A_PDW-01A1A.13.0
A_PDW19 | A_PDW-01A1A.14.0
A_PDW19 | A_PDW-01A1A.17.0
A_PDW19 | A_PDW-01A1A.27.0
A_PDW19 | A_PDW17
A_PDW19 | A_PDW22
A_PDW19 | A_PDW41
A_PDW20 | A_PDW17
A_PDW20 | A_PDW19
A_PDW20 | A_PDW22
A_PDW21 | A_PDW24
A_PDW21 | A_PDW25
A_PDW21 | A_PDW31
A_PDW21 | A_PDW38
A_PDW22 | A_PDW9
A_PDW22 | A_PDW12.1
A_PDW25 | A_PDW24
A_PDW26 | A_PDW28
A_PDW29 | A_PDW31
A_PDW29 | A_PDW32
A_PDW29 | A_PDW34
A_PDW29 | A_PDW36
A_PDW29 | A_PDW37
A_PDW29 | A_PDW38
A_PDW29 | A_PDW41
A_PDW29 | A_PDW42
A_PDW30 | A_PDW20
A_PDW30 | A_PDW31
A_PDW30 | A_PDW32
A_PDW30 | A_PDW33
A_PDW30 | A_PDW36
A_PDW30 | A_PDW37
A_PDW30 | A_PDW38
A_PDW30 | A_PDW41
A_PDW30 | A_PDW42
A_PDW31 | A_PDW32
A_PDW31 | A_PDW33
A_PDW31 | A_PDW36
A_PDW31 | A_PDW37
A_PDW31 | A_PDW38
A_PDW31 | A_PDW41
A_PDW31 | A_PDW42
A_PDW33 | A_PDW32
A_PDW33 | A_PDW41
A_PDW34 | A_PDW32
A_PDW34 | A_PDW33
A_PDW34 | A_PDW36
A_PDW34 | A_PDW37
A_PDW34 | A_PDW38
A_PDW34 | A_PDW41
A_PDW34 | A_PDW42
A_PDW36 | A_PDW32
A_PDW36 | A_PDW37
A_PDW36 | A_PDW38
A_PDW36 | A_PDW41
A_PDW36 | A_PDW42
A_PDW37 | A_PDW38
A_PDW37 | A_PDW41
A_PDW38 | A_PDW41
A_PDW39 | A_PDW40
A_PDW39 | A_PDW43
A_PDW39 | A_PDW44
A_PDW39 | A_PDW45
A_PDW40 | A_PDW43
A_PDW40 | A_PDW44
A_PDW40 | A_PDW45
A_PDW42 | A_PDW32
A_PDW43 | A_PDW44
A_PDW43 | A_PDW45
A_PDW44 | A_PDW45
B_PDW-01A1A.1.0 | B_PDW-01A1A.13.0
B_PDW-01A1A.1.0 | B_PDW-01A1A.17.0
B_PDW-01A1A.1.0 | B_PDW-01A1A.21.0
B_PDW-01A1A.1.0 | B_PDW-01A1A.27.0
B_PDW-01A1A.1.0 | B_PDW-01A1A.30.0
B_PDW-01A1A.13.0 | B_PDW-01A1A.17.0
B_PDW-01A1A.13.0 | B_PDW-01A1A.21.0
B_PDW-01A1A.13.0 | B_PDW-01A1A.27.0
B_PDW-01A1A.13.0 | B_PDW-01A1A.30.0
B_PDW-01A1A.17.0 | B_PDW-01A1A.21.0
B_PDW-01A1A.17.0 | B_PDW-01A1A.27.0
B_PDW-01A1A.17.0 | B_PDW-01A1A.30.0
B_PDW-01A1A.21.0 | B_PDW-01A1A.27.0
B_PDW-01A1A.21.0 | B_PDW-01A1A.30.0
B_PDW-01A1A.27.0 | B_PDW-01A1A.30.0
B_PDW-01A1AIF.1.0 | B_PDW32
B_PDW-01A1AIF.1.0 | B_PDW34
B_PDW-01A1AIF.1.0 | B_PDW36
B_PDW-01A1AIF.1.0 | B_PDW37
B_PDW-01A1AIF.1.0 | B_PDW38
B_PDW-01A1AIF.1.0 | B_PDW39
B_PDW-01A1AIF.1.0 | B_PDW41
B_PDW8 | B_PDW13
B_PDW8 | B_PDW12.1
B_PDW9 | B_PDW8
B_PDW9 | B_PDW13
B_PDW9 | B_PDW12.1
B_PDW13 | B_PDW12.1
B_PDW12 | B_PDW10
B_PDW15 | B_PDW18
B_PDW15 | B_PDW19
B_PDW15 | B_PDW20
B_PDW15 | B_PDW22
B_PDW16 | B_PDW12.1
B_PDW16 | B_PDW17
B_PDW16 | B_PDW19
B_PDW16 | B_PDW20
B_PDW16 | B_PDW22
B_PDW16 | B_PDW44
B_PDW18 | B_PDW12.1
B_PDW18 | B_PDW17
B_PDW18 | B_PDW19
B_PDW18 | B_PDW20
B_PDW18 | B_PDW22
B_PDW18 | B_PDW45
B_PDW19 | B_PDW-01A1A.27.0
B_PDW19 | B_PDW17
B_PDW19 | B_PDW20
B_PDW19 | B_PDW22
B_PDW19 | B_PDW28
B_PDW19 | B_PDW41
B_PDW20 | B_PDW17
B_PDW20 | B_PDW22
B_PDW21 | B_PDW17
B_PDW21 | B_PDW24
B_PDW21 | B_PDW25
B_PDW25 | B_PDW24
B_PDW26 | B_PDW28
B_PDW29 | B_PDW19
B_PDW29 | B_PDW28
B_PDW29 | B_PDW31
B_PDW29 | B_PDW32
B_PDW29 | B_PDW33
B_PDW29 | B_PDW34
B_PDW29 | B_PDW36
B_PDW29 | B_PDW37
B_PDW29 | B_PDW38
B_PDW29 | B_PDW39
B_PDW29 | B_PDW41
B_PDW30 | B_PDW31
B_PDW30 | B_PDW32
B_PDW30 | B_PDW33
B_PDW30 | B_PDW36
B_PDW30 | B_PDW37
B_PDW30 | B_PDW38
B_PDW30 | B_PDW39
B_PDW30 | B_PDW41
B_PDW31 | B_PDW32
B_PDW31 | B_PDW33
B_PDW31 | B_PDW36
B_PDW31 | B_PDW37
B_PDW31 | B_PDW38
B_PDW31 | B_PDW39
B_PDW31 | B_PDW41
B_PDW33 | B_PDW32
B_PDW34 | B_PDW28
B_PDW34 | B_PDW32
B_PDW34 | B_PDW33
B_PDW34 | B_PDW36
B_PDW34 | B_PDW37
B_PDW34 | B_PDW38
B_PDW34 | B_PDW39
B_PDW34 | B_PDW41
B_PDW36 | B_PDW28
B_PDW36 | B_PDW32
B_PDW36 | B_PDW37
B_PDW36 | B_PDW38
B_PDW36 | B_PDW39
B_PDW36 | B_PDW41
B_PDW37 | B_PDW28
B_PDW37 | B_PDW38
B_PDW37 | B_PDW41
B_PDW38 | B_PDW28
B_PDW38 | B_PDW41
B_PDW39 | B_PDW32
B_PDW39 | B_PDW41
B_PDW40 | B_PDW42
B_PDW40 | B_PDW43
B_PDW40 | B_PDW44
B_PDW40 | B_PDW45
B_PDW42 | B_PDW44
B_PDW42 | B_PDW45
B_PDW43 | B_PDW33
B_PDW43 | B_PDW42
B_PDW43 | B_PDW44
B_PDW43 | B_PDW45
B_PDW44 | B_PDW45
C_PDW-01A1A.1.0 | C_PDW-01A1A.11.0
C_PDW-01A1A.1.0 | C_PDW-01A1A.13.0
C_PDW-01A1A.1.0 | C_PDW-01A1A.14.0
C_PDW-01A1A.1.0 | C_PDW-01A1A.17.0
C_PDW-01A1A.1.0 | C_PDW-01A1A.21.0
C_PDW-01A1A.1.0 | C_PDW-01A1A.27.0
C_PDW-01A1A.1.0 | C_PDW-01A1A.30.0
C_PDW-01A1A.11.0 | C_PDW-01A1A.13.0
C_PDW-01A1A.11.0 | C_PDW-01A1A.14.0
C_PDW-01A1A.11.0 | C_PDW-01A1A.21.0
C_PDW-01A1A.11.0 | C_PDW-01A1A.27.0
C_PDW-01A1A.11.0 | C_PDW-01A1A.30.0
C_PDW-01A1A.13.0 | C_PDW-01A1A.14.0
C_PDW-01A1A.13.0 | C_PDW-01A1A.17.0
C_PDW-01A1A.13.0 | C_PDW-01A1A.21.0
C_PDW-01A1A.13.0 | C_PDW-01A1A.27.0
C_PDW-01A1A.13.0 | C_PDW-01A1A.30.0
C_PDW-01A1A.14.0 | C_PDW-01A1A.21.0
C_PDW-01A1A.14.0 | C_PDW-01A1A.27.0
C_PDW-01A1A.17.0 | C_PDW-01A1A.21.0
C_PDW-01A1A.17.0 | C_PDW-01A1A.27.0
C_PDW-01A1A.17.0 | C_PDW-01A1A.30.0
C_PDW-01A1A.21.0 | C_PDW-01A1A.27.0
C_PDW-01A1A.21.0 | C_PDW-01A1A.30.0
C_PDW-01A1A.27.0 | C_PDW-01A1A.30.0
C_PDW2 | C_PDW3
C_PDW2 | C_PDW4
C_PDW2 | C_PDW-01A1AIF.1.0
C_PDW2 | C_PDW8
C_PDW2 | C_PDW12
C_PDW3 | C_PDW-01A1A.11.0
C_PDW3 | C_PDW4
C_PDW3 | C_PDW-01A1AIF.1.0
C_PDW3 | C_PDW8
C_PDW3 | C_PDW12
C_PDW4 | C_PDW-01A1AIF.1.0
C_PDW4 | C_PDW8
C_PDW4 | C_PDW12
C_PDW5 | C_PDW9
C_PDW-01A1AIF.1.0 | C_PDW8
C_PDW-01A1AIF.1.0 | C_PDW12
C_PDW12 | C_PDW8
C_PDW12.1 | C_PDW26
C_PDW12.1 | C_PDW29
C_PDW10 | C_PDW9
C_PDW15 | C_PDW13
C_PDW15 | C_PDW18
C_PDW15 | C_PDW19
C_PDW15 | C_PDW22
C_PDW16 | C_PDW13
C_PDW16 | C_PDW18
C_PDW16 | C_PDW18.1
C_PDW16 | C_PDW18.2
C_PDW16 | C_PDW19
C_PDW16 | C_PDW22
C_PDW16 | C_PDW36
C_PDW16 | C_PDW39
C_PDW16 | C_PDW41
C_PDW17 | C_PDW18.2
C_PDW17 | C_PDW19
C_PDW17 | C_PDW22
C_PDW17 | C_PDW36
C_PDW17 | C_PDW38
C_PDW18 | C_PDW13
C_PDW18 | C_PDW19
C_PDW18 | C_PDW22
C_PDW18 | C_PDW41
C_PDW18.1 | C_PDW13
C_PDW18.1 | C_PDW19
C_PDW18.1 | C_PDW22
C_PDW18.2 | C_PDW-01A1A.13.0
C_PDW18.2 | C_PDW-01A1A.17.0
C_PDW18.2 | C_PDW19
C_PDW18.2 | C_PDW22
C_PDW18.2 | C_PDW41
C_PDW19 | C_PDW-01A1A.13.0
C_PDW19 | C_PDW-01A1A.14.0
C_PDW19 | C_PDW-01A1A.17.0
C_PDW19 | C_PDW-01A1A.21.0
C_PDW19 | C_PDW-01A1A.27.0
C_PDW19 | C_PDW-01A1A.30.0
C_PDW19 | C_PDW13
C_PDW19 | C_PDW22
C_PDW19 | C_PDW29
C_PDW19 | C_PDW41
C_PDW20 | C_PDW37
C_PDW20 | C_PDW38
C_PDW20 | C_PDW39
C_PDW20 | C_PDW41
C_PDW21 | C_PDW24
C_PDW21 | C_PDW25
C_PDW21 | C_PDW29
C_PDW25 | C_PDW24
C_PDW26 | C_PDW29
C_PDW28 | C_PDW20
C_PDW28 | C_PDW30
C_PDW28 | C_PDW32
C_PDW28 | C_PDW33
C_PDW28 | C_PDW34
C_PDW28 | C_PDW36
C_PDW28 | C_PDW37
C_PDW28 | C_PDW38
C_PDW28 | C_PDW39
C_PDW28 | C_PDW41
C_PDW30 | C_PDW36
C_PDW30 | C_PDW37
C_PDW30 | C_PDW38
C_PDW30 | C_PDW39
C_PDW30 | C_PDW41
C_PDW31 | C_PDW-01A1A.14.0
C_PDW31 | C_PDW20
C_PDW31 | C_PDW30
C_PDW31 | C_PDW32
C_PDW31 | C_PDW36
C_PDW31 | C_PDW37
C_PDW31 | C_PDW38
C_PDW31 | C_PDW39
C_PDW31 | C_PDW41
C_PDW33 | C_PDW32
C_PDW34 | C_PDW32
C_PDW34 | C_PDW33
C_PDW34 | C_PDW36
C_PDW34 | C_PDW37
C_PDW34 | C_PDW38
C_PDW34 | C_PDW39
C_PDW34 | C_PDW41
C_PDW36 | C_PDW37
C_PDW36 | C_PDW38
C_PDW36 | C_PDW39
C_PDW36 | C_PDW41
C_PDW37 | C_PDW38
C_PDW37 | C_PDW41
C_PDW38 | C_PDW41
C_PDW39 | C_PDW41
C_PDW40 | C_PDW33
C_PDW40 | C_PDW42
C_PDW40 | C_PDW43
C_PDW40 | C_PDW44
C_PDW40 | C_PDW45
C_PDW42 | C_PDW43
C_PDW42 | C_PDW44
C_PDW42 | C_PDW45
C_PDW43 | C_PDW44
C_PDW43 | C_PDW45
C_PDW44 | C_PDW45

## N
stage | number of station
1 | 1
2 | 2
3 | 1
4 | 1
5 | 1
6 | 1
7 | 1
8 | 1